## Sheet1
level_0 | index | activity | code | color | date | IADC_DESC | rig_no | remarks | well_name | well_no | month_wise | Time_count | rig_name | region_name
0 | 0 | DRILL 8 1/2'' HOLE SECTION FROM 10360 FT TO 10402 FT WITH 650 GPM, 3300 - 3595 PSI, 110 - 150 RPM, 5 - 22K TORQUE AND 10 - 15K WOB. REAM UP WITH 80 RPM AND REAM DOWN WITH 150 RPM. TAKE SURVEY AFTER CONNECTION. | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING 20. Directional Work CONNECTION 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I BIT 8.50 0.71 SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E MWD 6.80 112.27 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging HWDP 5.00 59.80 MANUFACT. SEC VISCOSITY 49 49 49 M JAR 6.50 29.50 TYPE PV/YP / / / O F. Other 4 HWDP 5.00 455.54 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 10,172.00 CUTTING STRUCTURE Mintreat25 8 Mintreat50 8 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION ecotrol 8 HOURS STANDBY KELLY DOWN TOTAL 10,829.82 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 220,000 REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 34 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING CUMULATIVE 118 CONNECTION ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1 | 1 | Extended Flow check well. Well static. Line up to trip tank and flow check well on trip tank, Well static. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.5 | ENTERPRISE | MENAM
2 | 2 | Back ream from 3151m MD to 2922m MD. with MW 1.39 SG SDF, 450 lpm, 120 rpm, 950-1000 psi, TQ; 9-10 kft-lbs. | 3 | WHITE | 2023-03-01 | REAMING | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 1.25 | ENTERPRISE | MENAM
3 | 3 | Extended flow check well. Observed flow back 1 bbls/ Hr. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.5 | ENTERPRISE | MENAM
4 | 4 | Circulate BTU with MW 1.39 SG SDF, 550 lpm, 80 rpm, 1830-2100psi, TQ: 9-10 K. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 1.25 | ENTERPRISE | MENAM
5 | 5 | Perform Static test 10 mins and MWD take survey at Bottom. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.5 | ENTERPRISE | MENAM
6 | 6 | Reduce flow rate from 541 lpm to 450 lpm. Pump LCM 20 bbls and continue circulate until LCM on surface with MW 1.39 SG SDF, U 450 lpm, 80 rpm, 1715-1900 psi, TQ: 10-11k. O T | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 2 | ENTERPRISE | MENAM
7 | 7 | Continue POOH 6-1/8" BHA (AGS/MLWD) with 4" DP from 2922 m to inside 7" Casing shoe at 1763 m. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 2 | ENTERPRISE | MENAM
8 | 8 | Reduce flow rate and check loss rate as per DSV instructions with MW 1.39 SG SDF. Flow rate 350 lpm, 120 rpm, 712-750 psi, TQ : 10-12 k. No loss. Flow rate 450 lpm, 120 rpm, 2066-2400 psi, TQ: 10-12 k. No loss. 1 Flow rate 541 lpm, 120 rpm, 2050-2500 psi, TQ: 10-12 k. Loss 6 bbls/ Hrs. R | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.75 | ENTERPRISE | MENAM
9 | 9 | Skid out cantilever and deploy Texas deck. Continue to skid out. cantilever and R/U CTU to Texas deck. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.25 | CHAOPHRAYA | SOUTH EAST ASIA
10 | 10 | HPJSM for skid out cantilever. | 23 | WHITE | 2023-03-01 | OTHER3 | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
11 | 11 | Lower hull to install mooring rope and jacking up to final operating air gap at 10:20 hrs. Remark: - Final Air gap 59 ft (MSL) - RKB to MSL: 125 ft. - Drill stem to PA-51 target = 1.44 m Remarks: Leg penetrations at final airgap: STBD 38.1 ft / BOW 38.3 ft / PORT 37.6 ft | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.75 | CHAOPHRAYA | SOUTH EAST ASIA
12 | 12 | Conduct riserless meeting and PJSM for P/U and RIH with casing drill in assembly. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 Night Tour Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-01 | OTHER3 | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.5 | CHAOPHRAYA | SOUTH EAST ASIA
13 | 13 | P/U and RIH with casing drill in assembly to 301' MD. | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.75 | CHAOPHRAYA | SOUTH EAST ASIA
14 | 14 | Continue perform general rig up. - Continue rig up on Texas deck, install access stair and handrail, install stoppers on Texas deck 2 - R/U CTU and function test. R - Install service hoses and overboard lines. U - Install mouse holes. O T - M/U 9-5/8" Spear. - M/U wellhead and running tool R/B on derrick. - P/U 5" DP and 5" HWDP - M/U 2 stands of 9-5/8" casing and R/B on derrick. - Tranfer cement, barite and SBM from supply vessel due to weather pick up. | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 10.75 | CHAOPHRAYA | SOUTH EAST ASIA
15 | 15 | Skid out cantilever and deploy Texas deck. Continue to skid out. HORIZ HORIZ HORIZ DEPTH DEV. DIcRa.ntilever TaVnDd R/U CDTISUP .to TeDxEaPs TdHeck. DEV. DIR. TVD DISP. DEPTH DEV. DIR. TVD DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.25 | CHAOPHRAYA | SOUTH EAST ASIA
16 | 16 | Performing trip drill with drill crew well secured within 30 sec. Flow well on trip tank for 10 mins, Well static. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
17 | 17 | Perform flow check before pulling BHA through BOP, well static. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
18 | 18 | Adams crew input DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-01 | OTHER3 | SDF | Shipyard work scope. 17. Plug Back Warm stack running routines. 18. Squeeze Cement Pit mapping. 19. Fishing Paint projects. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 Warm stack running routines. NO. OF DAYS Pit mapping. 0 FROM SPUD Paint projects. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 2 Date: 01-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
19 | 19 | Continue with shipyard work scope: Continue to install dog house paneling following window wiper troubleshooting. Drill and rivet as required. Continue to deep clean gumbo house. Remove items and organize. 1 Continue with paint projects on rig floor and moon pool. R Continue to troubleshoot leaking mud pit suction lines. U Hydrostatic test repaired suction valves as required. O T Housekeeping in drilling areas. | 23 | WHITE | 2023-03-01 | OTHER3 | SDF | Shipyard work scope. 17. Plug Back Warm stack running routines. 18. Squeeze Cement Pit mapping. 19. Fishing Paint projects. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 Warm stack running routines. NO. OF DAYS Pit mapping. 0 FROM SPUD Paint projects. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 2 Date: 01-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
20 | 20 | Nipple down BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 | 14 | WHITE | 2023-03-01 | N/UP BOP | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
21 | 21 | Make up tubing hanger with installed BPV. Terminate control line to hanger. Make up running tool and landing string. Land tubing hanger at 3140 m. Pressure test hanger seal to 6500 psi. Engage lock ring. Pull test 10 klbs over string weight. Release and POOH running tool. and rack back. | B | WHITE | 2023-03-01 | TUBING TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.5 | ENTERPRISE | MENAM
22 | 22 | Continue RIH with DHSV from 2968m to 3110 m. Meanwhile flushing WH through side outlet valves with SW. | B | WHITE | 2023-03-01 | TUBING TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
23 | 23 | POOH 6-1/8" BHA (AGS/MLWD) with 4" DP from 1763 m to 232 m. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 1.5 | ENTERPRISE | MENAM
24 | 24 | P/U DHSV and pressure test DHSV control line to 7500 psi for 5 min, keep pressure in control line 5000 psi. Meanwhile flushing WH through side outlet valves with SW. | B | WHITE | 2023-03-01 | TUBING TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.5 | ENTERPRISE | MENAM
25 | 25 | RIH 2-7/8" tubing from surface to 1773 m. ( inside 7" casing Shoe ) while fill up string on the fly with 1.39 SG SDF. P/U 150K. S/O O T 124k. | B | WHITE | 2023-03-01 | TUBING TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 2.25 | ENTERPRISE | MENAM
26 | 26 | P/U and RIH shoe track, Fill up with 1.39 SG SDF and checks float function and free of debris. U | B | WHITE | 2023-03-01 | TUBING TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
27 | 27 | PJSM for running 2-7/8" Completion string. R | 23 | WHITE | 2023-03-01 | OTHER3 | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
28 | 28 | Rig up 2-7/8" tubing handling equipment. Mean while flush wellhead through side out let valve with 1.47 SG SDF 800 lpm, 400 psi as per SPM well head engineer. 2 | B | WHITE | 2023-03-01 | TUBING TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
29 | 29 | Retrieve wear bushing. | 21 | WHITE | 2023-03-01 | RUN/RETRIVE RISER EQUIPMENT | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 0.25 | ENTERPRISE | MENAM
30 | 30 | Continue POOH 6-1/8" BHA (AGS/MLWD) with 4" HWDP from 232m to surface. Unload radioactive source. Plug in MLWD. Break out bit and rack back BHA. Clear and clean rig floor. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-01 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 1.25 | ENTERPRISE | MENAM
31 | 31 | Continue RIH with 2-7/8” tubing ( in open hole) from 1773 m to 2968 m and monitoring tubing displacement in trip tank, fill up 1.39 SG SDF every stand. P/U 165 K. S/O 133 k. | B | WHITE | 2023-03-01 | TUBING TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 0.25 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.75 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 6.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 6 FROM SPUD Stop the job if unsafe CUMULATIVE 46 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-7 Rpt No: 8 Date: 01-Mar-23 WIRE LINE | SDE-23-7 | PLWE- 22 | Mar-23 | 1.75 | ENTERPRISE | MENAM
32 | 32 | Adams crew input | 23 | WHITE | 2023-03-01 | OTHER3 | SDF | Shipyard work scope. 17. Plug Back Warm stack running routines. 18. Squeeze Cement Pit mapping. 19. Fishing Paint projects. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 Warm stack running routines. NO. OF DAYS Pit mapping. 0 FROM SPUD Paint projects. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 2 Date: 01-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
33 | 33 | HPJSM for skid out cantilever. | 23 | WHITE | 2023-03-01 | OTHER3 | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
34 | 34 | HPJSM for jacking to final air gap. | 23 | WHITE | 2023-03-01 | OTHER3 | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
35 | 35 | r/up tbg handling equips. recovered 2-7/8” tbg 153.6 m (16 jts). r/dn tbg handling tools. | B | WHITE | 2023-03-01 | TUBING TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
36 | 36 | pooh 7-7/8” o/shot assy f/1324 m to surf. b/off & l/dn o/shot. removed fish from o/shot. | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
37 | 37 | Drill 8 1/2" F/ 10382 ft T/ 11232 ft. WOB- 30 klbs, RPM-160, TRQ- 12-18k, 500-600 gpm, 1600-2500 psi. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 12 | ACHEIVER | MENAM
38 | 38 | Drill 8 1/2" F/ 10349 ft T/ 10382 ft. WOB- 20 klbs, RPM-40, TRQ- 10-14k, 500 gpm, 1600 psi. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 10382 11232 Drill 160 25000 2450 6.000 62 6.000 62 611.8656 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 10,430 53.78 117744..5533 8,247.0 10,619 54.05 117755..22 8,358.3 10,901 54.33 117777..0088 8,523.0 11,089 54.3 117755..9999 8,632.7 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.75 | ACHEIVER | MENAM
39 | 39 | Clean out shoe track F/ 10335 ft T/ 10349 ft. WOB- 20 klbs, RPM-40, TRQ- 10-14k, 500 gpm, 1600 psi. | 3 | WHITE | 2023-03-01 | REAMING | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
40 | 40 | dressed & rih 7-7/8” o/shot (3-11/16” bg & 3 ½” mcp) bha assy to 128 m. 1 | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
41 | 41 | Wash down F/ 10098 ft T/ 10224 ft. Re-log 10224 ft T/ 10335 ft with 550 gpm, 1900 psi. | 20 | WHITE | 2023-03-01 | DIRECTIONAL WORK | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
42 | 42 | Fill up string, break circ, wait on MWD signal. | 20 | WHITE | 2023-03-01 | DIRECTIONAL WORK | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
43 | 43 | RIH 8 1/2" RSS BHA on 5" DP F/ 5926 ft T/ 7813 ft. | 6 | WHITE | 2023-03-01 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
44 | 44 | Fill up string, break circ, wait on MWD signal. | 20 | WHITE | 2023-03-01 | DIRECTIONAL WORK | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
45 | 45 | RIH 8 1/2" RSS BHA on 5" DP F/ 3952 ft T/ 5926 ft. N | 6 | WHITE | 2023-03-01 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
46 | 46 | Fill up string, break circ, wait on MWD signal. I | 20 | WHITE | 2023-03-01 | DIRECTIONAL WORK | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
47 | 47 | RIH 8 1/2" RSS BHA on 5" DP F/ 2160 ft T/ 3952 ft. H G | 6 | WHITE | 2023-03-01 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
48 | 48 | RIH 8 1/2" RSS BHA on 5" DP F/ 7813 ft T/ 10098 ft. | 6 | WHITE | 2023-03-01 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
49 | 49 | Lower hull to install mooring rope and jacking up to final operating air gap at 10:20 hrs. Remark: - Final Air gap 59 ft (MSL) DEPTH INTERVAL DRILL - RKB to MSL:F O12R5M fAt.TION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP FROM TO RCEOARME NO. - Drill st(eSmHO toW P CAO-R5E1 RtaErCgOetV =E R1Y.4)4 m STAPEBELDE BOINT PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT Remarks: Leg penetrations at final airgap: STBD 38.1 ft / BOW 38.3 ft / PORT 37.6 ft | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.75 | CHAOPHRAYA | SOUTH EAST ASIA
50 | 50 | cont’ rih 7-7/8” o/shot assy f/ 128 m to 418 m in singles. total p/up 30 jts. R | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
51 | 51 | cont rih 7-7/8” o/shot assy f/1336 m to 1476 m & tagged the fish. w/down last stand. O T | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
52 | 52 | Prepare for preload operation. Commence single leg preload on STB 100% leg at Zero AG. Hold static 1 hr and dumping preload. (Preload STB leg total 1 cycles.) Remarks: Leg penetrations: STBD 38.5 ft/ BOW 38.0 ft / PORT 37.0 ft. | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.75 | CHAOPHRAYA | SOUTH EAST ASIA
53 | 53 | Prepare for preload operation. Commence single leg preload on H Port 100% leg at Zero AG. Hold static 1 hr and dumping preload. G I (Preload Port leg total 2 cycles.) N Remarks: Leg penetrations: STBD 37.4 ft/ BOW 38.0 ft / PORT 37.0 ft. | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 4.75 | CHAOPHRAYA | SOUTH EAST ASIA
54 | 54 | Prepare for preload operation. Commence single leg preload on BOW 100% leg at Zero AG. Hold static 1 hr and dumping R preload. (Preload Bow total 2 cycles.) U O Remarks: Leg penetrations: STBD 37.3 ft/ BOW 38 ft / PORT T 35.9 ft. T | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDC | HPJSM for skid out cantilever and R/U CTU Deck. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG,Pick up 8/1-2" BHA. Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 6 Date: 01-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1 | CHAOPHRAYA | SOUTH EAST ASIA
55 | 55 | Pooh with mule shoe assy F/1183 m to 82 m. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
56 | 56 | Direct wash @1183 m1-1/2 cycle with 300gpm, 60spm, 100 psi | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
57 | 57 | cont rih 7-7/8” o/shot assy f/ 418 m to 1336 m on 5-1/2” dp stds friip. U | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
58 | 58 | Pooh F/ 1530 m to 1183 m. | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
59 | 59 | Pumped 25 bbls hi-vis, change over well vol to 8.6 ppg gel mud. Circulate condition 1.5 cycle prior to cmt job. Checked S/l-14 bph & D/l-40 bph. 2 | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
60 | 60 | Make up 5” mule shoe with 5 ½” dp & Rih to 1530 m. reciprocated string f/1350 to 1530 m as per cmt plan. | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 4 | PARAMESHWARA | INDIA
61 | 61 | /up tbg handling equips. recovered 2-7/8” tbg 85.95 m (9 jts). r/dn tbg handling tools. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | B | WHITE | 2023-03-01 | TUBING TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
62 | 62 | pooh 7-7/8” o/shot assy bha 128m m to surf. b/off & l/dn o/shot. secured & removed fish from o/shot. | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
63 | 63 | : pooh 7-7/8” o/shot assy f/1476 m to bha 128M. | 6 | WHITE | 2023-03-01 | TRIPS | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2.5 | PARAMESHWARA | INDIA
64 | 64 | work on string to 120 kips o/pull in stages to release fish (7” hyd pkr), obsd no progress. backoff the string. | 19 | YELLOW | 2023-03-01 | FISHING | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
65 | 65 | Hook up cmt line flush & test line @3000 psi ok.Pump 25 bbls hi-vis,25 bbls drill water as pre flush,mix & pump 40 bbls 15.5 ppg cmt R slurry, 12 bbls drill water as post flush. Displace with 83 bbls gel mud by rig pump. U O T | 17 | WHITE | 2023-03-01 | PLUG BACK | PSW | Held PJSM PRIOR RIH WITH O/S ASSY.. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-448. 18. Squeeze Cement Wash pipe hours: 234 hrs. 19. Fishing 1.00 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I 1 MSUB 5.00 13.62 SIZE WEIGHT T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 3 STD. D.P. 5.50 253.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 269.85 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with myle shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-450. NO. OF DAYS Wash pipe hours: 234 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 21 Date: 01-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2.5 | PARAMESHWARA | INDIA
66 | 66 | Continue with shipyard work scope: Continue with rig floor red zone paint project 2 Continue with painting MPD frame work in moonpool. R Continue with mud pits suction line troubleshooting. U Housekeeping in drilling areas as required. O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 2 Date: 01-Mar-23 | 23 | WHITE | 2023-03-01 | OTHER3 | SDF | Shipyard work scope. 17. Plug Back Warm stack running routines. 18. Squeeze Cement Pit mapping. 19. Fishing Paint projects. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 Warm stack running routines. NO. OF DAYS Pit mapping. 0 FROM SPUD Paint projects. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 2 Date: 01-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
67 | 67 | Continue circulate hole due to solid control equipment failure with 800 gpm, 3680 psi, 120 rpm, torque -12-13, rot wt -235k | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.75 | MENTOR | WEST AFRICA
68 | 68 | FLOW CHECK, SERVICE TOP DRIVE. | 7 | WHITE | 2023-03-01 | LUBRICATE RIG | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
69 | 69 | POH 12 1/4'' REAMING BHA TO 13 3/8'' CSG SHOE ON ELEVATOR. F/C: STATIC. O T | 6 | WHITE | 2023-03-01 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.25 | HIGH ISLAND II | MENAM
70 | 70 | PUMPED SWEEPS & CHC. F/C: STATIC. U | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 3 | HIGH ISLAND II | MENAM
71 | 71 | HELD SAFETY STAND DOWN MEETING WITH ALL CREW & 3RD PARTY PERSONNEL. DISCUSSED HAZARD IDENTIFICATION, CRANE OPERATIONS ,RE-ENFORCE SWA, PROPER COMMUNICATION & TEAM WORK.*CIRCULATE WHILE HOLDING 1 MEETING R | 23 | WHITE | 2023-03-01 | OTHER3 | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
72 | 72 | CONTINUE RIH 12 1/4'' REAMING BHA IN OPEN HOLE ON ELEVATOR TO BTM 7544'. WASH DOWN LAST STD | 6 | WHITE | 2023-03-01 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.5 | HIGH ISLAND II | MENAM
73 | 73 | POH 12 1/4'' REAMING BHA ON 5'' DP FROM 4479' TO 753' | 6 | WHITE | 2023-03-01 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.25 | HIGH ISLAND II | MENAM
74 | 74 | Lay out rig up slings, diverter Running tool and clear rig floor while nipple down BOP from HP riser and raise for skidding to A-02. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | 23 | WHITE | 2023-03-01 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
75 | 75 | Nipple down Bell Nipple and lay down to deck. | 14 | WHITE | 2023-03-01 | N/UP BOP | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
76 | 76 | Install 60ft rig up slings on TDS and Nipple down Diverter / overshot - Keep suspended on rig floor. | 14 | WHITE | 2023-03-01 | N/UP BOP | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
77 | 77 | Hold PJSM for nipple down Diverter / overshot, Bell nipple and BOP. | 23 | WHITE | 2023-03-01 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
78 | 78 | Pick up dummy hanger and make up to running tool. RIH and set Hanger as per Cameron procedure. Perform 15k over pull test. O T Cameron pressure test Hanger seals 5000psi/15mins. Back out RT and rack back into Derrick. | 23 | WHITE | 2023-03-01 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
79 | 79 | Held PJSM with crew. Break / lay down Schlumberger tool string and all remaining E-line equipment. U | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1.5 | TENACIOUS | WEST AFRICA
80 | 80 | Transmit logging data to town for review. Meanwhile monitor well on trip tank. R | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1.5 | TENACIOUS | WEST AFRICA
81 | 81 | Install Diverter and Overshot in diverter housing. | 14 | WHITE | 2023-03-01 | N/UP BOP | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
82 | 82 | Schlumberger E-line start logging from 3250ft to 500ft and POOH to surface. 2 | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 2.5 | TENACIOUS | WEST AFRICA
83 | 83 | FLOW CHECK AT BHA: STATIC. POH 12 1/4'' REAMING BHA ON 5'' HWDP @ 290 | 6 | WHITE | 2023-03-01 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
84 | 84 | CLEAR AND CLEAN RIG FLOOR. | 6 | WHITE | 2023-03-01 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
85 | 85 | RIGD SKID RIG FLOOR TO CENTER AND SECURE SAME. PREPARING FOR RIG MOVE, CLOSE DUMP VALVE IN SHAKERS. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO N/UP X-MAS TREE WING VALVE, TBSM PRIOR TO RIG MOVE 17. Plug Back PREPARATION. 18. Squeeze Cement U/IBOP ---------3796 FUNCTIONS. 19. Fishing WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 20. Directional Work SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 21. Run/Retrieve Riser Equip. CHECKED COM, DLA, CMF – OK. 22. Surface Testing 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 3.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO R/DN MUD HOSES, TBSM PRIOR TO RIG MOVE PREPARATION. TOTAL DAYWORK 0.00 0.00 U/IBOP ---------3796 FUNCTIONS. NO. OF DAYS WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 39 FROM SPUD SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CUMULATIVE CHECKED COM, DLA, CMF – OK. ROTATING HOURS 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 HRS DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO N/UP X-MAS TREE WING VALVE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO R/DN MUD HOSES, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 | T02-23-1 NW#1Z | NW#1Z | Mar-23 | 10 | TRIDENT II | INDIA
86 | 86 | CONTINUE TO N/UP WING VALVE AND FLANGE. INSTALL BULL PLUG ON XMT TOP. | 14 | WHITE | 2023-03-01 | N/UP BOP | T02 | HELD PJSM PRIOR TO N/UP X-MAS TREE WING VALVE, TBSM PRIOR TO RIG MOVE 17. Plug Back PREPARATION. 18. Squeeze Cement U/IBOP ---------3796 FUNCTIONS. 19. Fishing WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 20. Directional Work SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 21. Run/Retrieve Riser Equip. CHECKED COM, DLA, CMF – OK. 22. Surface Testing 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 3.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO R/DN MUD HOSES, TBSM PRIOR TO RIG MOVE PREPARATION. TOTAL DAYWORK 0.00 0.00 U/IBOP ---------3796 FUNCTIONS. NO. OF DAYS WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 39 FROM SPUD SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CUMULATIVE CHECKED COM, DLA, CMF – OK. ROTATING HOURS 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 HRS DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO N/UP X-MAS TREE WING VALVE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO R/DN MUD HOSES, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 | T02-23-1 NW#1Z | NW#1Z | Mar-23 | 2 | TRIDENT II | INDIA
87 | 87 | BKR LOGGING RUN #5: PERFORM VIT STATION #1 AT 5271 FT. *MONITOR WELL ON TRIP TANK IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.75 | HIGH ISLAND II | MENAM
88 | 88 | PERFORMED STICKY TEST FOR 30 MIN AND MOVED STRING FREELY UP & DOWN | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
89 | 89 | RIH BKR RUN #5 TOOLS W/ CONTROLLED SPEED. PERFORM GR CORRELATION PASS | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.5 | HIGH ISLAND II | MENAM
90 | 90 | POOH 12-1/4" REAMER ASSY AND L/D SAME. | 6 | WHITE | 2023-03-01 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1 | HIGH ISLAND II | MENAM
91 | 91 | RIH SINKER BAR W/ WIRELINE. LATCH BKR DOWNHOLE TOOLS AND PERFORM FUNCTION TEST. INSTALL SES CLAMP, PERFORM PULL TEST - OK | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.5 | HIGH ISLAND II | MENAM
92 | 92 | CIRC 2 X STRING CAPACITIES TO CLEAN CONNECTOR HEAD U | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.75 | HIGH ISLAND II | MENAM
93 | 93 | RIH BKR RUN #5 TOOLS ON 5'' DP W/ CONTROLLED SPEED AS PER BKR LOG ENG FROM 162' TO 4421 R | 6 | WHITE | 2023-03-01 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.75 | HIGH ISLAND II | MENAM
94 | 94 | HELD SAFETY STAND DOWN MEETING, DISCUSSED: SWA, PJSM, LIFTING OPERATIONS, SLIP/TRIP HAZARDS, SUPERVISION DURING CREW CHANGE. HAND & FINGERS INJURIES. 2 | 23 | WHITE | 2023-03-01 | OTHER3 | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
95 | 95 | P/U & M/U BKR RUN #5 TOOLS: GR-RCX-WGI (SAMPLES). CHECKED LOGGING TOOLS AT SURFACE | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.25 | HIGH ISLAND II | MENAM
96 | 96 | P/U & M/U BKR RUN #5 TOOLS: GR-RCX-WGI (SAMPLES). CHECKED LOGGING TOOLS AT SURFAC DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.75 | HIGH ISLAND II | MENAM
97 | 97 | PJSM, R/U AND PU BAKER RUN #5 TOOL. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
98 | 98 | R/U BKR W/L SHEAVES, P/U & M/U BKR SES. O T | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS. 21. Run/Retrieve Riser Equip. PJSM: TRIPPING OPS. 22. Surface Testing TRIP DRILL: SECURE WELL IN 40 SEC. DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 34 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS. ROTATING HOURS PJSM: TRIPPING OPS WITH WIRE LINE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 R/U WIRE LINE SHIFE ON THE DERRICK . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS. TRIP DRILL: SECURE WELL IN 40 SEC. PIT DRILL:SECURE WELL IN 38 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS. PJSM: TRIPPING OPS WITH WIRE LINE . R/U WIRE LINE SHIFE ON THE DERRICK . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 34 Date: 01-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
99 | 99 | Schlumberger E-line set tool string depth and perform FPM pass from surface to 3250ft. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
100 | 100 | Schlumberger E-line rig up deflector sheaves in V-door. Power up and check sensors / calibrate head tension. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1.25 | TENACIOUS | WEST AFRICA
101 | 101 | Pick up E-Line USIT CBL Logging tool from catwalk and make up to E-line head on tool string . DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1.25 | TENACIOUS | WEST AFRICA
102 | 102 | Cameron pressure test tubing hanger 5000 psi / 5 minutes good test. Locked hanger by rotating 4 turns counter clockwise to positive stop. Rotated clockwise 1/4 turn. Pull tested 96 + 50 Klbs as per R Cameron. U O | E | WHITE | 2023-03-01 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
103 | 103 | Carry out Inventory of SDS Drilling Subs. Prepare Diverter system and R/T and install element for MODU inspection. Transfer fuel from tanker to Rig. Carry out housekeeping at the BOP set back and Heavy tools store. Carry out daily checks on all running equipment. Assist in changing out sewage pipeline. House keeping in engine room and machinery space. Continue jobs to Work and 2 support HVAC third party team to repairing HVAC units. Replaced mud condition motor at shaker area(top motor). Continue 180 days R PM on jacking brakes. Closed out completed drilling PM on JDE. U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 89 Date: 01-Mar-23 | 23 | WHITE | 2023-03-01 | OTHER3 | SDS | 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) TOTAL MUD COST ($) DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 89 Date: 01-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
104 | 104 | Carry out Inventory of SDS Drilling tools and equipment. Continue to clean Degassers #2 in preparation for MODU inspection. Prepare decks and Skid Cantilever deck out from 10ft to 30ft. Carry out daily checks on all running equipment. R Function test/troubleshoot Bow leg fixation. Assist for changed out sewage pipeline. U O Installed governor for engine # 4 and run test. T Close punch list for koomey unit. T Fix leak for hydraulic line in port forward crane’s engine cabin. H House keeping in engine room. G I Continue jobs to Work and support HVAC third party team to repairing HVAC units on AHU/ACCU-07 unit, N AHU/ACCU-03,cold rooms and job keep continue. Checked and troubleshooting on mud conditioner not working and job keep continue. Support team to power up on fixation units and function tested. Checked and troubleshooting on fixation Bow leg chord B and C. Checked and troubleshooting on ice machine and job keep continue. Replaced mud condition motor at shaker area(top motor). Continue 180 days PM on jacking brakes. Work with NSSL service technician on SSAS. Assisted OMCI service technicians. Checks and repairs to LER Room UPS. (UPS is currently in fault. Indicating DC feedback fault/Inverter inhibited) Checks and repairs to CCTV system since several cameras were found to be off as well as the drillers unit. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-01 | OTHER3 | SDS | 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) TOTAL MUD COST ($) DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 89 Date: 01-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
105 | 105 | While continue shoveling and clearing hip of cuttings on the deck. Meanwhile continue circulating and reciprocating pipe at 7514ft with 500gpm, 1792psi, 60rpm, 14-15k torque. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 5 | MENTOR | WEST AFRICA
106 | 106 | Cameron pressure test tubing hanger seals 5000 psi / 15 mins to confirm seals integrity. T | E | WHITE | 2023-03-01 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
107 | 107 | Observed over flow of cuttings on the deck. Stopped drilling due to Frigate solid control equipment failure. Pumped 30 bbls of hi vis R sweep and circulate hole clean with 650gpm, 2661psi, 100 rpm, 14-15 torque, while reciprocating pipe. Deployed more hands to U assist Frigate team in shoveling and clearing hip of cuttings on the deck O T | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 4 | MENTOR | WEST AFRICA
108 | 108 | Pumped 30 bbls of hi vis sweep and circulate same out with 800 gpm, 3709 psi, 100 rpm, 14-15 torque, work string at 7321ft DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 7321 7514 Drill 60 5000 6.500 35 6.500 35 397.2 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 7,348 26.58 11..1122 6,449.9 7,448 27.21 335577..5522 6,538.0 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.5 | MENTOR | WEST AFRICA
109 | 109 | Continue to drill 12 1/4'' hole section as per DD instruction from 7224ft to 7321ft pump with 800 gpm, 3747 psi, 120 rpm, 16 -17 O T torque , 5-10kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 300k, s/o wt-205k, Rot-wt 245k. Rop- 80 ft / hr ( INC 26.58 ,Azimuth -10.93) | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.5 | MENTOR | WEST AFRICA
110 | 110 | Circulate hole while trouble shooting solid control equipment with 800 gpm, 3709 psi, 120 rpm, rot-wt 235k, 13-14 torque U | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 2 | MENTOR | WEST AFRICA
111 | 111 | Continue circulate hole due to solid control equipment failure with 800 gpm, 3680 psi, 120 rpm, torque -12-13, rot wt -235k R | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 2.5 | MENTOR | WEST AFRICA
112 | 112 | RIH 12 1/4'' RSS drilling assy from 5689ft to 7036ft m/up TDS and wash down to 7128ft pump with 800gpm - 3677psi. 1 | 6 | WHITE | 2023-03-01 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.75 | MENTOR | WEST AFRICA
113 | 113 | Continue circulate hole due to solid control equipment failure with 800 gpm, 3680 psi, 120 rpm, torque -12-13, rot wt -235k | 6 | WHITE | 2023-03-01 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 2 | MENTOR | WEST AFRICA
114 | 114 | Continue to drill 12 1/4'' hole section as per DD instruction from 7321ft to 7514ft pump with 800 gpm, 3747 psi, 120 rpm, 16 -17 torque , 5-10kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 300k, s/o wt-205k, Rot-wt 245k. Rop- 80 ft / hr ( INC 27.21 ,Azimuth -357.52) 2 | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 357hrs (98HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 77 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 36/27 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 14/18 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.4 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 70 DP 5.00 6,730.15 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 20 caco3 4 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 7,514.05 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 300,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 17 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 421 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 369hrs ( 86HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 357hrs (98HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 369hrs ( 86HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 18 Date: 01-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 3 | MENTOR | WEST AFRICA
115 | 115 | Haliburton close TRSV by bleed of to control line to zero. T | E | WHITE | 2023-03-01 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
116 | 116 | Back out R/t. Pull out and rack back landing string. H Lay down hanger running tool. G I | B | WHITE | 2023-03-01 | TUBING TRIPS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
117 | 117 | Rig up Franks. 2 7/8'' tubing handling equipment. N | 23 | WHITE | 2023-03-01 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
118 | 118 | PJSM for pick up and make up E-line tool string. | 23 | WHITE | 2023-03-01 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
119 | 119 | Rig up E-line sheaves and pass line through same. Schlumberger prepare USIT & CBL tools on catwalk. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1.5 | TENACIOUS | WEST AFRICA
120 | 120 | Pull dummy hanger to surface and break out adapter sleeve. Rack back hanger running stand in derrick and lay down dummy hanger. | B | WHITE | 2023-03-01 | TUBING TRIPS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
121 | 121 | Fill riser / BOP stack with sea water through choke line from cement unit to confirm line up. Close middle pipe rams and perform 13 I 5/8" BOP connection test 250 / 5000 psi 5 / 5 mins. N | 22 | WHITE | 2023-03-01 | SURFACE TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
122 | 122 | Install 4 1/2" tubing elevator on TDS. Run in hole with hanger running stand and engage to dummy hanger as per Cameron. H G | B | WHITE | 2023-03-01 | TUBING TRIPS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
123 | 123 | Held PJSM and Nipple up 13 5/8'' BOP to HP riser. T | 14 | WHITE | 2023-03-01 | N/UP BOP | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
124 | 124 | Skid cantilever in board 12 ft and transverse drilling package to STBD over well A-08. T | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
125 | 125 | Rig up high pressure riser on well A-08 while moving slick line unit from under cantilever to cantilever deck. U O | 14 | WHITE | 2023-03-01 | N/UP BOP | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.75 | TENACIOUS | WEST AFRICA
126 | 126 | Transverse drilling package to center line and skidded cantilever to out board 12 ft. R | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
127 | 127 | Held PJSM for skidding. | 23 | WHITE | 2023-03-01 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.50 2.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 19:00 23:00 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 4 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 836 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3-1 Rpt No: 6 Date: 01-Mar-23 | Lifua A-08 | SDT-23-3-1 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
128 | 128 | Nipple down BOP from HP riser and raise in preparation for skidding. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | 14 | WHITE | 2023-03-01 | N/UP BOP | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
129 | 129 | Rig down Franks. 2 7/8'' tubing handling equipments. | 23 | WHITE | 2023-03-01 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
130 | 130 | POOH and lay down 3 Joints of 2 7/8'' tubing. | B | WHITE | 2023-03-01 | TUBING TRIPS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
131 | 131 | Pick up 2 7/8'' tubing, make up BPV running tool with BPV and run in hole and install 4'' BPV as per Cameron. | B | WHITE | 2023-03-01 | TUBING TRIPS | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards. 17. Plug Back Saver sub connections:0 18. Squeeze Cement TDS rotating hours: 0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 1.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 4.50 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards. TOTAL DAYWORK 0.00 0.00 Saver sub connections:0 NO. OF DAYS TDS rotating hours: 0 17 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 876 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-23-3 Rpt No: 19 Date: 01-Mar-23 | Lifua A-10 | SDT-23-3 | Mar-23 | 1.5 | TENACIOUS | WEST AFRICA
132 | 132 | Fill up string and perform Shallow test 400 Gpm 650 psi, 600 Gpm 1250 psi T | 20 | WHITE | 2023-03-01 | DIRECTIONAL WORK | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
133 | 133 | RIG MOVE PREPARATION.M/W CONT'D BACK LOADING MANIFESTED CARGO FROM RIG TO OSV OFFSHORE ENERGY,REP@ 15:00 HRS.IIP.(RIG RELEASED FROM WELL NW#1Z ON NW PLATFORM @15:30 HRS ON 01.03.2023-NEW LOCATION: N_19). 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO N/UP X-MAS TREE WING VALVE, TBSM PRIOR TO RIG MOVE 17. Plug Back PREPARATION. 18. Squeeze Cement U/IBOP ---------3796 FUNCTIONS. 19. Fishing WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 20. Directional Work SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 21. Run/Retrieve Riser Equip. CHECKED COM, DLA, CMF – OK. 22. Surface Testing 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 3.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO R/DN MUD HOSES, TBSM PRIOR TO RIG MOVE PREPARATION. TOTAL DAYWORK 0.00 0.00 U/IBOP ---------3796 FUNCTIONS. NO. OF DAYS WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 39 FROM SPUD SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CUMULATIVE CHECKED COM, DLA, CMF – OK. ROTATING HOURS 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 HRS DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO N/UP X-MAS TREE WING VALVE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO R/DN MUD HOSES, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-1 NW#1Z Rpt No: 39 Date: 01-Mar-23 | T02-23-1 NW#1Z | NW#1Z | Mar-23 | 3.5 | TRIDENT II | INDIA
134 | 134 | RIH 8 1/2" RSS BHA on 5" DP F/ 286 ft T/ 2160 ft. T | 6 | WHITE | 2023-03-01 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
135 | 135 | MWD plug in and test coms. R | 20 | WHITE | 2023-03-01 | DIRECTIONAL WORK | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
136 | 136 | PRESSURE TEST 13-5/8” BOP STACK ALL RAM, C& K HCR,MANUAL VALVE LOWER & UPPER IBOPS, FOSV,C & K HOSE TO 300/4000PSI. ANNULAR BOP TO 300/3500PSI-OK. 1 | 15 | WHITE | 2023-03-01 | TEST BOP | T12 | HELD PJSM ABOUT PRESSURE TEST BOP 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND 22. Surface Testing EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND C L EDARNILELDE RA:REA TO AVOID SLIP AND 23. Other 3 7.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - NO. OF DAYS TOTAL CONNECTION - 107 5 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVO I D D SRLIILPL AENRD: TRIP HAZARDS. STAYING IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT PRESSURE TEST BOP SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTION WITH MANUAL TONG. EFFECTIVE COMMUNICATION AND HANDS FREE OPERATION. Operations Activities (Continued...) HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. SAVER SUB CONNECTION - TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE USING HAMMER.CORRECT MANUAL HANDLING. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2.5 | TRIDENT XII | INDIA
137 | 137 | BREAK & L/DN 13-3/8” TEST ASSY R | 15 | WHITE | 2023-03-01 | TEST BOP | T12 | HELD PJSM ABOUT PRESSURE TEST BOP 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND 22. Surface Testing EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND C L EDARNILELDE RA:REA TO AVOID SLIP AND 23. Other 3 7.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - NO. OF DAYS TOTAL CONNECTION - 107 5 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVO I D D SRLIILPL AENRD: TRIP HAZARDS. STAYING IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT PRESSURE TEST BOP SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTION WITH MANUAL TONG. EFFECTIVE COMMUNICATION AND HANDS FREE OPERATION. Operations Activities (Continued...) HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. SAVER SUB CONNECTION - TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE USING HAMMER.CORRECT MANUAL HANDLING. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
138 | 138 | P/UP 3 JTS 5.5” HWDP FLUSHED & R/BACK. P/UP CSG SPEAR ASSY BREAK & L/DN. U | 6 | WHITE | 2023-03-01 | TRIPS | T12 | HELD PJSM ABOUT PRESSURE TEST BOP 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND 22. Surface Testing EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND C L EDARNILELDE RA:REA TO AVOID SLIP AND 23. Other 3 7.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - NO. OF DAYS TOTAL CONNECTION - 107 5 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVO I D D SRLIILPL AENRD: TRIP HAZARDS. STAYING IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT PRESSURE TEST BOP SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTION WITH MANUAL TONG. EFFECTIVE COMMUNICATION AND HANDS FREE OPERATION. Operations Activities (Continued...) HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. SAVER SUB CONNECTION - TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE USING HAMMER.CORRECT MANUAL HANDLING. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
139 | 139 | WAITING ON LOGISTICS TO DELIVER 12-1/4” DD TOOLS F/DS FOSSIL AND SOBM F/GS O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-01 | OTHER3 | T12 | HELD PJSM ABOUT PRESSURE TEST BOP 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND 22. Surface Testing EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND C L EDARNILELDE RA:REA TO AVOID SLIP AND 23. Other 3 7.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - NO. OF DAYS TOTAL CONNECTION - 107 5 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVO I D D SRLIILPL AENRD: TRIP HAZARDS. STAYING IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT PRESSURE TEST BOP SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTION WITH MANUAL TONG. EFFECTIVE COMMUNICATION AND HANDS FREE OPERATION. Operations Activities (Continued...) HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. SAVER SUB CONNECTION - TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE USING HAMMER.CORRECT MANUAL HANDLING. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 7 | TRIDENT XII | INDIA
140 | 140 | WAITING ON LOGISTICS TO DELIVER 12-1/4” DD TOOLS F/DS FOSSIL + NHAVA AND SOBM F/GS DIPTI. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 | 23 | WHITE | 2023-03-01 | OTHER3 | T12 | HELD PJSM ABOUT PRESSURE TEST BOP 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND 22. Surface Testing EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND C L EDARNILELDE RA:REA TO AVOID SLIP AND 23. Other 3 7.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - NO. OF DAYS TOTAL CONNECTION - 107 5 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVO I D D SRLIILPL AENRD: TRIP HAZARDS. STAYING IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT PRESSURE TEST BOP SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTION WITH MANUAL TONG. EFFECTIVE COMMUNICATION AND HANDS FREE OPERATION. Operations Activities (Continued...) HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. SAVER SUB CONNECTION - TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE USING HAMMER.CORRECT MANUAL HANDLING. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 12 | TRIDENT XII | INDIA
141 | 141 | HELD PJSM,: P/U & M/UP TEST PLUG ASSY & LAND IN TO B-SEC W/HEAD | 15 | WHITE | 2023-03-01 | TEST BOP | T12 | HELD PJSM ABOUT PRESSURE TEST BOP 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND 22. Surface Testing EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND C L EDARNILELDE RA:REA TO AVOID SLIP AND 23. Other 3 7.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - NO. OF DAYS TOTAL CONNECTION - 107 5 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVO I D D SRLIILPL AENRD: TRIP HAZARDS. STAYING IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT PRESSURE TEST BOP SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- PRESSURE TEST FULL BOP TEST HELD PJSM , DISCUSSED TBRA, INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTION WITH MANUAL TONG. EFFECTIVE COMMUNICATION AND HANDS FREE OPERATION. Operations Activities (Continued...) HELD PJSM ABOUT INSTALLING HLB DOWN LINK UNIT. SAVER SUB CONNECTION - TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- INSTALLING HLB DOWN LINK UNIT. INSPECTION TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE USING HAMMER.CORRECT MANUAL HANDLING. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 5 Date: 01-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
142 | 142 | ROTARY DRILL 8.5' HOLE FROM 9417' TO 9524' WITH 650 GPM , 150 RPM , 3336 PSI , 10 - 20K WOB , 18 K TQ , REAM UP AND REAM DOWN EVERY STAND DRILLED PUMP SWEEP EVERY OTHER STAND , TAKE SURVEY AFTER CONNECTION 1 | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING 20. Directional Work CONNECTION 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I BIT 8.50 0.71 SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E MWD 6.80 112.27 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging HWDP 5.00 59.80 MANUFACT. SEC VISCOSITY 49 49 49 M JAR 6.50 29.50 TYPE PV/YP / / / O F. Other 4 HWDP 5.00 455.54 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 10,172.00 CUTTING STRUCTURE Mintreat25 8 Mintreat50 8 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION ecotrol 8 HOURS STANDBY KELLY DOWN TOTAL 10,829.82 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 220,000 REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 34 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING CUMULATIVE 118 CONNECTION ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
143 | 143 | CONTINUE ROTARY DRILL 8.5' HOLE FROM 9524' TO10360' ' WITH 650 GPM , 160 RPM , 3336 PSI , 10 - 20K WOB , U 20 K TQ , REAM UP AND REAM DOWN EVERY STAND DRILLED PUMP SWEEP EVERY OTHER STAND , TAKE SURVEY O T AFTER CONNECTION DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 10360 10830 Drill 150 15000 3750 6.000 75 6.000 75 641.655 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 10,443 90.22 1188..1199 7,274.4 10,347 90.31 1177..2266 7,274.9 10,540 90.2 1188..7711 7,274.1 10,636 89.51 1199..0055 7,274.3 10,730 88.22 1199..7799 7,276.2 10,761 88.71 1199..9922 7,277.0 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING 20. Directional Work CONNECTION 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I BIT 8.50 0.71 SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E MWD 6.80 112.27 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging HWDP 5.00 59.80 MANUFACT. SEC VISCOSITY 49 49 49 M JAR 6.50 29.50 TYPE PV/YP / / / O F. Other 4 HWDP 5.00 455.54 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 10,172.00 CUTTING STRUCTURE Mintreat25 8 Mintreat50 8 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION ecotrol 8 HOURS STANDBY KELLY DOWN TOTAL 10,829.82 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 220,000 REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 34 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING CUMULATIVE 118 CONNECTION ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 10.5 | HIGH ISLAND IV | MENAM
144 | 144 | WAITING ON LOGISTICS TO DELIVER 200 MT DRILL WATER FOR CTC JOB SINCE 1200HRS 01.03.2023. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 | 23 | WHITE | 2023-03-01 | OTHER3 |  | HELD PJSM REGARDING RIH TUBING. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PRESSURE TEST PRODUCTION CHOKE MANIFOLD. TOOK TOFS @ TOTAL DAYWORK 0.00 0.00 16:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED NO. OF DAYS ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 70 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH TUBING. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PRESSURE TEST PRODUCTION CHOKE MANIFOLD. TOOK TOFS @ 16:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 12 | J T ANGEL | INDIA
145 | 145 | HELD SAFETY STAND DOWN MEETING. 2 | 23 | WHITE | 2023-03-01 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING 20. Directional Work CONNECTION 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I BIT 8.50 0.71 SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E MWD 6.80 112.27 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging HWDP 5.00 59.80 MANUFACT. SEC VISCOSITY 49 49 49 M JAR 6.50 29.50 TYPE PV/YP / / / O F. Other 4 HWDP 5.00 455.54 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 10,172.00 CUTTING STRUCTURE Mintreat25 8 Mintreat50 8 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION ecotrol 8 HOURS STANDBY KELLY DOWN TOTAL 10,829.82 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 220,000 REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 34 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING CUMULATIVE 118 CONNECTION ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
146 | 146 | DRILL 8 1/2'' HOLE SECTION FROM 10402 FT TO 10830 FT WITH 650 GPM, 3300 - 3750 PSI, 110 - 150 RPM, 5 - 22K TORQUE R AND 10 - 15K WOB. REAM UP WITH 80 RPM AND REAM DOWN WITH 150 RPM. TAKE SURVEY AFTER CONNECTION. U | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING 20. Directional Work CONNECTION 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I BIT 8.50 0.71 SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E MWD 6.80 112.27 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging HWDP 5.00 59.80 MANUFACT. SEC VISCOSITY 49 49 49 M JAR 6.50 29.50 TYPE PV/YP / / / O F. Other 4 HWDP 5.00 455.54 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 10,172.00 CUTTING STRUCTURE Mintreat25 8 Mintreat50 8 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION ecotrol 8 HOURS STANDBY KELLY DOWN TOTAL 10,829.82 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 220,000 REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 34 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING CUMULATIVE 118 CONNECTION ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 7.5 | HIGH ISLAND IV | MENAM
147 | 147 | PUMP 3 X HI-WT, HI-VIS PILL AND CIRCULATE WITH 650 GPM, 3648 PSI, 120 RPM AND 9K TORQUE. O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING 20. Directional Work CONNECTION 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I BIT 8.50 0.71 SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E MWD 6.80 112.27 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging HWDP 5.00 59.80 MANUFACT. SEC VISCOSITY 49 49 49 M JAR 6.50 29.50 TYPE PV/YP / / / O F. Other 4 HWDP 5.00 455.54 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 10,172.00 CUTTING STRUCTURE Mintreat25 8 Mintreat50 8 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION ecotrol 8 HOURS STANDBY KELLY DOWN TOTAL 10,829.82 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 220,000 REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 34 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING CUMULATIVE 118 CONNECTION ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 3 | HIGH ISLAND IV | MENAM
148 | 148 | SAFETY STAND DOWN MEETING R | 23 | WHITE | 2023-03-01 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING 20. Directional Work CONNECTION 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I BIT 8.50 0.71 SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E MWD 6.80 112.27 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging HWDP 5.00 59.80 MANUFACT. SEC VISCOSITY 49 49 49 M JAR 6.50 29.50 TYPE PV/YP / / / O F. Other 4 HWDP 5.00 455.54 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 10,172.00 CUTTING STRUCTURE Mintreat25 8 Mintreat50 8 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION ecotrol 8 HOURS STANDBY KELLY DOWN TOTAL 10,829.82 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 220,000 REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 34 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA DRILL 8.5" HOLE , MAKING CUMULATIVE 118 CONNECTION ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 34 Date: 01-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
149 | 149 | P/up and M/Up 4-1/2" ME plug RIH on slick line and set at 200ft. POOH lay down running tool. | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 1 | MAIN PASS I | MENAM
150 | 150 | Reeve Drill Line on Traveling Block. Pick up and position traveling block on rotary table. Install traveling block guards as required. 2 Carry out house keeping on the Rig floor. R | 23 | WHITE | 2023-03-01 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
151 | 151 | Break circulation in stages, 300lpm Pressure,120 psi. 400lpm, pressure 133 psi. 500 lpm, perssure 145 psi. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
152 | 152 | Continue RIH 5'' DP on 3 1/2'' stinger from 738m to 1055m. Trip restricted 2080 ft/hr (11 stands) of 5'' DP. While monitoring well on IADCDAILY DRILLT/ITN aGnd RchEecPk OT/TR foTr cFoOrreRct Mdis p-l aPceRmOenOt.F COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-01 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
153 | 153 | Continue RIH 5'' DP on 3 1/2'' stinger from 738m to 1055m. Trip restricted 2080 ft/hr (11 stands) of 5'' DP. While monitoring well on T/T and check T/T for correct displacement. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | 6 | WHITE | 2023-03-01 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
154 | 154 | Continue Pooh with 4 ½''Halliburton TCP guns assembly on 5" elevator F/ 6,994' T/ 1,891' ORKB.fill annulus with metal displacement + 10 BBL every hour. no visual on annulus fluid level. 1 | 6 | WHITE | 2023-03-01 | TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up Pooh 17. Plug Back with 4 1/2" Halliburton firing TCP Guns 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up Borest TOTAL DAYWORK 0.00 0.00 ESP pump NO. OF DAYS 32 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 4.5 | RIG 141 | MENAM
155 | 155 | Continue Pooh with 4 ½''Halliburton TCP guns assembly on 5" elevator F/ 1,891' to surface, L/D same. R - check packer condition, found same as before RIH. U - all 51 guns are all 100% fired. O T - fill annulus with metal displacement + 10 BBL every hour. - no visual on annulus fluid level. - total BBL'S pumped in annulus since losses started: 224 BBL (including metal displacement) DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-01 | TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up Pooh 17. Plug Back with 4 1/2" Halliburton firing TCP Guns 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up Borest TOTAL DAYWORK 0.00 0.00 ESP pump NO. OF DAYS 32 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 7.5 | RIG 141 | MENAM
156 | 156 | Install traveling block drill line guards, tighten up the nut and install safety pins okay. U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 | 23 | WHITE | 2023-03-01 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
157 | 157 | H.P.J.S.M Continue POOH and L/D For TCB Guns From Gun # 33 To Surface Total L/D 51 Guns . Monitor well On Trip Tank Pumping 10 BBL - 907 PPG eve5ry one Hr Brain Water . | 6 | WHITE | 2023-03-01 | TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up Pooh 17. Plug Back with 4 1/2" Halliburton firing TCP Guns 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up Borest TOTAL DAYWORK 0.00 0.00 ESP pump NO. OF DAYS 32 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2.5 | RIG 141 | MENAM
158 | 158 | P/U, M/U tubing hanger with 2 EA condition "B" landing TBG JTS, run same in THS, take mark for landing, pooh. R | B | WHITE | 2023-03-01 | TUBING TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up Pooh 17. Plug Back with 4 1/2" Halliburton firing TCP Guns 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up Borest TOTAL DAYWORK 0.00 0.00 ESP pump NO. OF DAYS 32 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2 | RIG 141 | MENAM
159 | 159 | 'HOLD PJSM with BORETS team and all involved personnel, discuss procedures & risk & mitigations while handling ESP dual string. U | 23 | WHITE | 2023-03-01 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up Pooh 17. Plug Back with 4 1/2" Halliburton firing TCP Guns 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up Borest TOTAL DAYWORK 0.00 0.00 ESP pump NO. OF DAYS 32 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 0.5 | RIG 141 | MENAM
160 | 160 | Pick up Make tested BORETS ,ESP pump O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | E | WHITE | 2023-03-01 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up Pooh 17. Plug Back with 4 1/2" Halliburton firing TCP Guns 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up Borest TOTAL DAYWORK 0.00 0.00 ESP pump NO. OF DAYS 32 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 6 | RIG 141 | MENAM
161 | 161 | Break bonnet bolt on lower and middle 13 5/8" BOP bonnet. Open lower and middle bonnet on 13 5/8" BOP. Remove the rams on lower and middle bonnet on 13 5/8" BOP. 1 Clean the BOP bonnet, rams and the cavity on 13 5/8" bonnet. R | 23 | WHITE | 2023-03-01 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
162 | 162 | Continue to Reeve Drill Line on Traveling Block. U Carry out house keeping on the Rig. O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-01 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 39 Date: 01-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
163 | 163 | Make up 11" test plug to 5'' DP stand, RIH & retrieve wear bushing, POOH & L/D same. 2 | 6 | WHITE | 2023-03-01 | TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up Pooh 17. Plug Back with 4 1/2" Halliburton firing TCP Guns 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up Borest TOTAL DAYWORK 0.00 0.00 ESP pump NO. OF DAYS 32 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 32 Date: 01-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1 | RIG 141 | MENAM
164 | 164 | RIH 3 1/2'' cement stinger on 5" DP from 304m to 738m. Trip restricted (1900 ft/hr 15 stands of 5'' DP). While monitoring well on T/T and check T/T for correct displacement. | 6 | WHITE | 2023-03-01 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
165 | 165 | Held safety stand down. Discussed emergency alarms, their identification and PPE. | 23 | WHITE | 2023-03-01 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.5 | MAIN PASS I | MENAM
166 | 166 | RMS drop ESP test leads from main power cable on tubing hanger, Close TRSSV and terminate control line. Back off landing jt from R hanger and rack back same. R/down ESP cable sheave from derrick. U | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 1.5 | MAIN PASS I | MENAM
167 | 167 | Held PJSM. Shallow test SLB MWD and LWD tools @ 250 gpm/ 1800 psi | 22 | WHITE | 2023-03-01 | SURFACE TESTING | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
168 | 168 | Held PJSM. Rih with 6 1/8” RSS/LWD/MWD assy. on 4” D/pipe from 1625 ft to 6766 ft. Monitor well thru trip tank hole static. 1 | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.5 | HIGH ISLAND IX | MENAM
169 | 169 | Held PJSM. Rih with 6 1/8” RSS/LWD/MWD assy. on 4” D/pipe in open hole from 6766 ft to 11016 ft. Monitor well thru trip tank hole R static. U | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
170 | 170 | Held PJSM. Re-log from 11016 ft to tag bottom @11164 ft. Pump 15 Hi-Vis sweep while re-log and circulate hole clean. O T | 3 | WHITE | 2023-03-01 | REAMING | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
171 | 171 | Held PJSM. Drill ahead 6 1/8" hole with SLB RSS from 11164 ft to 11377 ft. with 76pcf OBM & 100% circulation, drilling parameters: 290 gpm, 3700 psi, WOB 5-10 Klbs, 140 RPM, Torque 4-8 Kft.lbs. Wash up ream down take survey 30ft off bottom every stand prior connection & Pump 15 bbls sweeps every 2 stands drilled. Down-link as required. | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 3 | HIGH ISLAND IX | MENAM
172 | 172 | Held PJSM. Pump 15 bbls hivis sweep and circulate hole with 290 gpm, 3600psi while reciprocate the pipe and rotate with 80 rpm. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 2 PUMP NO 3 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 11377 11377 Drill 80 3700 5.500 41 5.500 41 294.298 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
173 | 173 | Held PJSM. Rih with 6 1/8” RSS/LWD/MWD assy. on 4” D/pipe from 875 ft to 1625 ft. Monitor well thru trip tank hole static. | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
174 | 174 | Held PJSM, Continue Circulate hole clean with 76 pcf OBM with 290 gpm, 3600psi while reciprocate the pipe and rotate with 80 rpm. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.75 | HIGH ISLAND IX | MENAM
175 | 175 | Held PJSM. POOH 6 1/6" SLB RSS assy on 4" D/P in open hole on elevator from 11377 ft to 6730 ft. Monitor well on trip tank. Well 2 static. R | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.75 | HIGH ISLAND IX | MENAM
176 | 176 | Held PJSM, Flow check well static, slug pipe. U | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
177 | 177 | Held PJSM. POOH 6 1/6" SLB RSS assy on 4" D/P & L/D 51 joints F/ 6730ft to 5220 ft. Monitor well on trip tank. Well static. O T | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
178 | 178 | Held PJSM. Pooh 6 1/6" SLB RSS assy on 4" D/Pipe from 5220 ft to 404 ft. inside 7" casing monitor well on trip tank, Well static. | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
179 | 179 | Held PJSM, POOH 6 1/8'' RSS assy on 8 joints 4'' HWDP, Drilling jar, X-O, Dog Leg reamer and 4 3/4'' PBL to 116 ft. monitor well on trip tank, Well static. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
180 | 180 | Held PJSM, Flow check well static. | 6 | WHITE | 2023-03-01 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 232 Hrs. 20. Directional Work SWL PKG---CIRC = 324.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 41 spm, 3700 psi for 6.5 hours. 22. Surface Testing 0.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.2 TIME 14:00 I 1 BIT 0.50 SIZE 6.13 WEIGHT 10.16 T C. Treating E 8 MWD 5.00 115.87 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1 OTHER 4.75 8.44 MANUFACT. REED VISCOSITY 65 M 1 XO 4.75 2.53 TYPE PV/YP / O F. Other 4 2 HWDP 5.00 61.48 SERIAL NO. S297109 GELS / C G. Other 5 1 OTHER 6.13 4.27 JETS 3x13 FL. LOSS H. Other 6 3 HWDP 5.00 91.74 TFA 0.389 pH TOTALS 12.00 12.00 1 JAR 4.75 26.85 DEPTH OUT 11,377 SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.00 92.40 DEPTH IN 11,164 2 (OFFICE USE ONLY) TOTAL DRILL 213 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 404.08 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 51 FROM SPUD SWL PKG----ROT = 234 Hrs. CUMULATIVE 219 SWL PKG---CIRC = 326.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 41 spm, 3700 psi for 2 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 68 Date: 01-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
181 | 181 | Pressure test 4-1/2" ME plug with 500psi, 10 min. Lay down slick line lubricator, BOP, SES, 4-1/2" TIW and surface lines. 1 | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.5 | MAIN PASS I | MENAM
182 | 182 | Held PJSM for slick line operations. | 23 | WHITE | 2023-03-01 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.25 | MAIN PASS I | MENAM
183 | 183 | PJSM prior to Nipple Down BOP. L/Down mouse hole Connect rig up lines Remove master bushings. O T | 23 | WHITE | 2023-03-01 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.5 | MAIN PASS I | MENAM
184 | 184 | Disconnect flow line elbow. Nipple Down bell nipple outer barrel. Disconnect inner barrel from annular and L/Down same. | 14 | WHITE | 2023-03-01 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 1.5 | MAIN PASS I | MENAM
185 | 185 | Rig down choke and kill line coflex hoses. | 14 | WHITE | 2023-03-01 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 2.5 | MAIN PASS I | MENAM
186 | 186 | R/down scaffolding around 13-5/8"10K BOP to risers level. | 23 | WHITE | 2023-03-01 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 1 | MAIN PASS I | MENAM
187 | 187 | Nipple down 13-5/" 10 k BOP from risers, move to set back back area and secure same on stump. | 14 | WHITE | 2023-03-01 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 2.5 | MAIN PASS I | MENAM
188 | 188 | R/Up lifting plate on risers and rig down scaffolding from riser to well head level. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-01 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.5 | MAIN PASS I | MENAM
189 | 189 | PJSM, Rig up Halliburton slick line Riser, BOP and lubricator. Flush and pressure test same to 300/2000 psi. Good test. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 2 | MAIN PASS I | MENAM
190 | 190 | Rig down scaffold around Riser. | 14 | WHITE | 2023-03-01 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.75 | MAIN PASS I | MENAM
191 | 191 | PJSM, Nipple up new 11" X 4-1/16" TBG Bonnet tighten same. BAKER terminate ESP cable through TBG bonnet & check cable 2 integrity ok.and SLB control line. R | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 2.25 | MAIN PASS I | MENAM
192 | 192 | Held safety stand down. Discussed Use the Safety Analysis Process to Plan Risk Assess and Monitor all tasks. U | 23 | WHITE | 2023-03-01 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.5 | MAIN PASS I | MENAM
193 | 193 | RMS terminate ESP cables on TBG Bonnet. Checked cable integrity O T | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 1.5 | MAIN PASS I | MENAM
194 | 194 | SBL Terminate TRSSSV C/Line on TBG Bonnet. Pressure test to 6000psi. Ok. | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 1 | MAIN PASS I | MENAM
195 | 195 | Pre Job Safety meeting for Nipple Up and Pressure test Production Tree. | 23 | WHITE | 2023-03-01 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.25 | MAIN PASS I | MENAM
196 | 196 | Nipple Up New 4 1/16" CIW Production Tree. orientate wing valve to original position set TWCV Pressure test Tree to 2500psi. Ok. Retrieve TWCV, | E | WHITE | 2023-03-01 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 2.5 | MAIN PASS I | MENAM
197 | 197 | PJSM, Nipple down 13-5/8" 10 M riser and DSA from well head and lay out same. | 14 | WHITE | 2023-03-01 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement Held safety stand down meeting, Held safety stand down Discussed. The first 12slides of the safety induction. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 23:30 I SIZE 3.75 WEIGHT 9.93 T C. Treating E IADC CODE GRADIENT 0.5154 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.00 9.25 M TYPE DSR6085 PV/YP / O F. Other 4 SERIAL NO. 1A/ S295592 GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1600 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 24 FROM SPUD all tasks. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 41 Date: 01-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 1 | MAIN PASS I | MENAM
198 | 198 | P/U 1 stand of 5'' dp from derrick, M/U crossover 3 1/2'' IF box X PH 6 pin and 4 1/2''IF box X 3 1/2'' IF pin to cement stinger . | 23 | WHITE | 2023-03-01 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
199 | 199 | Line trip tank to EKD (Early Kick Detection) sensor line by the flow return and flush through with the volume of mud in trip tank and recovered mud at shakers pit./active mud pit. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
200 | 200 | R/D 3 1/2'' tubing handling equipment and R/U 5'' DP elevator. Clear left finger set back area to enable RIH 5'' DP. | 23 | WHITE | 2023-03-01 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
201 | 201 | CONTINUE WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE ETC), 200MT D/WATER FOR MUD PREPARATION FOR 8-1/2” PHASE DRILLING, BACKLOAD BOAT FOR 1100 BBL SOBM (12.5PPG). 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-01 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:58 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 26 26 26 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 23.46 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 45 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 45 Date: 01-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 12 | RON TAPPMEYER | INDIA
202 | 202 | RIH with HSFT tools to bottom MD WLD with 12 points taken. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 4.25 | KRATHONG | SOUTH EAST ASIA
203 | 203 | Rig up wire line equipment and function test HSFT tools same. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.5 | KRATHONG | SOUTH EAST ASIA
204 | 204 | Hold PJSM for rig up wire line. | 23 | WHITE | 2023-03-01 | OTHER3 | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.25 | KRATHONG | SOUTH EAST ASIA
205 | 205 | POOH BHA from 100'MD to surface and Remove RA sources.plug in cable, Break off bit and rack back BHA. | 6 | WHITE | 2023-03-01 | TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 1 | KRATHONG | SOUTH EAST ASIA
206 | 206 | CONTINUE WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE ETC), 200MT D/WATER FOR MUD PREPARATION FOR 8-1/2” PHASE DRILLING, BACKLOAD BOAT FOR 1100 BBL SOBM (12.5PPG). 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 45 Date: 01-Mar-23 | 23 | WHITE | 2023-03-01 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:58 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 26 26 26 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 23.46 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 45 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 45 Date: 01-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 12 | RON TAPPMEYER | INDIA
207 | 207 | Continue pull out of hole with 4" HWDP from 1295’MD to100 MWD/LWD BHA. | 6 | WHITE | 2023-03-01 | TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.75 | KRATHONG | SOUTH EAST ASIA
208 | 208 | Continued to POOH from 6494'MD to 1295'MD. U | 6 | WHITE | 2023-03-01 | TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 1.5 | KRATHONG | SOUTH EAST ASIA
209 | 209 | Continue POOH from 11873'MD to 6494'MD in side casing shoe, And trip drill with crew 35 sec stab in TIW valve close same. R | 6 | WHITE | 2023-03-01 | TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 2 | KRATHONG | SOUTH EAST ASIA
210 | 210 | Pump and displace30bbl slug. Install jumping jack slips. 2 | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.5 | KRATHONG | SOUTH EAST ASIA
211 | 211 | POOH wet from 12912'MD to 11873'MD and monitor well on trip tank proper displace. | 6 | WHITE | 2023-03-01 | TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.75 | KRATHONG | SOUTH EAST ASIA
212 | 212 | Flow check well is static. | 6 | WHITE | 2023-03-01 | TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.25 | KRATHONG | SOUTH EAST ASIA
213 | 213 | At TD. Circulate 10 min. Static test 10 min and circulate 10 min. Perform swab test 1 stroke and circulate hole clean with 180 rpm, 48 1 spm, 4000 psi. 9.5 ppg. Static gas @ 33u/30u, Swab gas @ 30u/30u. R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 2.5 | KRATHONG | SOUTH EAST ASIA
214 | 214 | Flow check before pull out BHA well is static(mean while remove jumping jack slips), O T | 6 | WHITE | 2023-03-01 | TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.25 | KRATHONG | SOUTH EAST ASIA
215 | 215 | Continue drilling ahead 6 1/8" section from 11402' MD to 12912' MD 9793' TVD with 220 rpm, 16-18 klbs WOB, 300 gpm, 4100 psi. String weight P/U 210 klbs. S/O 160 klbs. R/T 210 klbs. Torque 18 k ft/lbs. | 2 | WHITE | 2023-03-01 | DRILL ACTUAL | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 21:00 I 1 BIT 6.13 0.65 SIZE 6.13 WEIGHT 9.50 T C. Treating E 1 NBS 5.00 2.15 IADC CODE GRADIENT 0.4931 PL DE.. TSewsatibnbging 1 AUTOTR 5.00 15.61 MANUFACT. BAKER VISCOSITY M 9 MWD 4.75 83.33 TYPE D504S PV/YP / O F. Other 4 36 HWDP 4.00 1,099.01 SERIAL NO. 5339806 GELS / C G. Other 5 1 XO 5.00 1.85 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,202.60 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 5 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 6 Date: 01-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 9.5 | KRATHONG | SOUTH EAST ASIA
216 | 216 | POOH & R/DN W/LINE SHEAVES AND TOOLS. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 3.5 | F G MCCLINTOCK | INDIA
217 | 217 | P/U + M/U OnTrak, MWD Stab, BCPM, NM sub-stop + Bit. RIH F/ surface T/ 66 ft. | 6 | WHITE | 2023-03-01 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
218 | 218 | CONTINUE LOWER 13 3/8"(BTC,68PPF,P110) CASING FROM 34M TO 171M.TOTAL LOWER 15 JNTS. INSTALL CENTRALIZER AS PER TALLY. F/UP EVERY 5 JNTS. FURTHER LOWER CASING I/P. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | 12 | WHITE | 2023-03-01 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
219 | 219 | HELD PJSM, P/UP & M/UP 13 3/8" SHOE TRACK (BTC,68PPF,P110)AND TAG WELD SHOE TRACK, CHECK NRV OK. LOWER UPTO 34 M.INSTALL CENTRALIZER AS PER TALLY. | 12 | WHITE | 2023-03-01 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2 | F G MCCLINTOCK | INDIA
220 | 220 | R/DN POLLUTION PAN & R/UP 13 3/8" CASING HANDLING EQUIPMENTS. | 12 | WHITE | 2023-03-01 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
221 | 221 | CONTINUE POOH 17 1/2" CLEAN OUT ASSY ON 5 1/2" DP,6 5/8 HWDP AND 8" DC FROM 500M TO RKB.(B/OFF & L/DN 1 SNG U 8" DC, 8"D/JAR, AND P/UP 1 SNG 8" DC, L/DN 17 1/2"S/STAB & PDC BIT) O T | 6 | WHITE | 2023-03-01 | TRIPS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2.75 | F G MCCLINTOCK | INDIA
222 | 222 | RECORDED LOG F/1662M TO 500M (CASING SHOE). | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
223 | 223 | FLOW CHECK WELL STATIC OK. R | 6 | WHITE | 2023-03-01 | TRIPS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.25 | F G MCCLINTOCK | INDIA
224 | 224 | FLOW CHECK WELL STATIC OK. | 6 | WHITE | 2023-03-01 | TRIPS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.25 | F G MCCLINTOCK | INDIA
225 | 225 | CONTINUE CIRCULATION AT BOTTOM TO HOLE CLEAN GPM900/1880PSI. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
226 | 226 | PUMPED 30 BBLS HI - VIS X 2 CIRCULATE AND HOLE CLEAN I/P. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-01 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2 | F G MCCLINTOCK | INDIA
227 | 227 | RIH WITH 5 1/2" DP F/98 M TO 1670 M,(CONTROL SPEED IN OPEN HOLE,FILL UP EVERY 15 STANDS.) O T | 6 | WHITE | 2023-03-01 | TRIPS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 3 | F G MCCLINTOCK | INDIA
228 | 228 | CONT. RIH F/ 98 M TO 500 M ( 20'' CSG SHOE)FILL UP STRING. U | 6 | WHITE | 2023-03-01 | TRIPS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
229 | 229 | MAKE ARRANGEMENT, P/UP AND M/UP 17 1/2" PDC BIT,B/SUB,1X 8" DC,STAB 17",4X 8" DC,8" JAR,3X 65/8" HWDP RIH UPTO 1 98M. R | 6 | WHITE | 2023-03-01 | TRIPS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
230 | 230 | POOH 17 1/2" C/OUT ASSY ON 5 1/2" DP IN OPEN HOLE FROM 1670M TO 500M (INSIDE 20"SHOE) 2 | 6 | WHITE | 2023-03-01 | TRIPS | FGM | HELD PJSM ABOUT WIRE LINE OPERATIONS .TBSM PRIOR TO RIH 17 1/2'' C/OUT ASSY. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.4 TIME 12:10 18:00 23:55 I SIZE 17.50 WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. SMITH VISCOSITY 70 70 70 P E. Testing M TYPE S519-P PV/YP / / / O F. Other 4 SERIAL NO. SD1686 GELS / / / C G. Other 5 JETS 16,3x14,6x12 FL. LOSS H. Other 6 TFA 1.310 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,479 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 2 CT S TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 WT OTH REMARKS: HELD PJSM ABOUT POOH 17 1/2" CLEAN OUT ASSY .TBSM PRIOR TO LOWERING 13 3/8" TOTAL DAYWORK 0.00 0.00 CASING. NO. OF DAYS SAVER SUB :- HT-55 - 98 CONNECTIONS 27 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 1 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. HELD TRIP DRILL 26 SEC . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 27 Date: 01-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 3.25 | F G MCCLINTOCK | INDIA
231 | 231 | Backer perform electrical test MWD tool. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | 6 | WHITE | 2023-03-01 | TRIPS | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 0.5 | KEY MANHATTAN | MENAM
232 | 232 | Drilling cement from 1754 m to 1762 m with 1500 lit/hr and 1400 psi. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 3 | WHITE | 2023-03-01 | REAMING | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1 | KEY MANHATTAN | MENAM
233 | 233 | RIH GR-VSP-Toolstring to 2364.6m and took GR shot. POOH to casing ringing vz1 and vz4 and shot @ 964m stack 31. Good shot @ 824m, no casing ringing.POOH GR -VSP -Tool string from 824m to surface. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 8.75 | BALTIC | WEST AFRICA
234 | 234 | Break out and lay down GR-VSP + Tool string.Meanwhile monitoring hole on trip tank. 1 | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
235 | 235 | Untie TDS hose and rig down Baker e-line sheaves.Meanwhile monitoring hole on trip tank. R | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
236 | 236 | Baker e-line prepare tools for back load. Meanwhile monitoring hole on trip tank. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.5 | BALTIC | WEST AFRICA
237 | 237 | Baker e-line prepare tools for back load. Meanwhile monitoring hole on trip tank. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 3 | BALTIC | WEST AFRICA
238 | 238 | R/U 3 1/2'' tubing handling equipment. Meanwhile monitoring hole on trip tank. 2 | 23 | WHITE | 2023-03-01 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
239 | 239 | Performed deck management on cantilever deck. R | 23 | WHITE | 2023-03-01 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
240 | 240 | Held PJSM with all personnel involved in the picking up of 3 1/2'' stinger. U | 23 | WHITE | 2023-03-01 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
241 | 241 | PU 3 1/2'' cement mule shoe clean flush with water and confirmed no debris inside. Lower mule shoe and secured in rotary with O T slips and safety clamps. PU, MU & RIH 3 1/2'' mule shoe on 3 1/2" tubing to 152m. Dropped 2" drift in every joint of 3 1/2" tubing picked and recover drift prior to M/U . Secured tubing stinger with slips and clamps on the rotary.Torque 3 1/2" PH 6 connection to 6300ft/lbs with HT 65 manual tong. | B | WHITE | 2023-03-01 | TUBING TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.5 | BALTIC | WEST AFRICA
242 | 242 | Held PJSM and discussed TBRA with all personnel involved in picking up 3 1/2'' stinger, drift same on the V-Door. | 23 | WHITE | 2023-03-01 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
243 | 243 | Continue P/U & M/U, RIH 3 1/2'' stinger from 152m to 304m. Dropped 2" drift in every joint of 3 1/2" tubing and recover drift prior to M/U . Secured tubing stinger with slips and clamps on the rotary.Torque 3 1/2" PH 6 connection to 6300ft/lbs with HT 65 manual tong. | B | WHITE | 2023-03-01 | TUBING TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.5 | BALTIC | WEST AFRICA
244 | 244 | Lay out 3 1/2'' TBG on cantilever deck and strap same. | 23 | WHITE | 2023-03-01 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 81 P E. Testing M TYPE PV/YP 42/15 O F. Other 4 SERIAL NO. GELS 11/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 48 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 48 Date: 01-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
245 | 245 | SLB RIH WITH CORROSION MTD/GR/CCL LOGGING TOOL TILL TAG EZSV· CR AT 5410' & PERFORM LOGGING TO SURFACE MONITOR WELL THRU TRIP TANK,WELL STATIC 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. E LINE. CONTINUOD 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:30 18:30 23:30 I 1 OTHER 9.63 4.95 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 XO 6.50 2.65 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 153 DP 4.00 4,783.66 MANUFACT. VISCOSITY 30 30 30 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE CLC 33 XPALEMAR 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION PAC LV 1 HOURS STANDBY KELLY DOWN TOTAL 4,791.26 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 68,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. CONTINUO I LINE . 18 FROM SPUD PRE JOB SAFETY METING. L/D I LINE CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN SHOOTING NIPPLE NIPPLE UP BELL NIPPLE. ROTATING HOURS PRE JOB SAFETY METING. P/U EZSV BHA DAILY MUD COST ($) 990.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING. P/U 4" DP . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 18 Date: 01-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 12 | HIGH ISLAND V | MENAM
246 | 246 | SLB RIH WITH CORROSION MTD/GR/CCL LOGGING TOOL TILL TAG EZSV· CR AT 5410' & PERFORM LOGGING TO SURFACE - RECORD REPEAT PASS FOR CORROSION LOG FROM 400' TO 200' & 3000' &2800'. 2 - SEND DATA TO ROD CONFIMR OK FOR R/D. R - KEEP MONITORING AND FILLING HOLE CONTINUOUSLY WITH 70 PCF VISCOUS BRINE, WELL STATIC. U | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. E LINE. CONTINUOD 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:30 18:30 23:30 I 1 OTHER 9.63 4.95 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 XO 6.50 2.65 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 153 DP 4.00 4,783.66 MANUFACT. VISCOSITY 30 30 30 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE CLC 33 XPALEMAR 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION PAC LV 1 HOURS STANDBY KELLY DOWN TOTAL 4,791.26 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 68,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. CONTINUO I LINE . 18 FROM SPUD PRE JOB SAFETY METING. L/D I LINE CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN SHOOTING NIPPLE NIPPLE UP BELL NIPPLE. ROTATING HOURS PRE JOB SAFETY METING. P/U EZSV BHA DAILY MUD COST ($) 990.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING. P/U 4" DP . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 18 Date: 01-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 4 | HIGH ISLAND V | MENAM
247 | 247 | HPJSM. R/D SLB WIRE LINE MTDE /GR/CCL CORROSION LOG TOOLS O T | 11 | WHITE | 2023-03-01 | WIRELINE LOGS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. E LINE. CONTINUOD 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:30 18:30 23:30 I 1 OTHER 9.63 4.95 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 XO 6.50 2.65 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 153 DP 4.00 4,783.66 MANUFACT. VISCOSITY 30 30 30 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE CLC 33 XPALEMAR 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION PAC LV 1 HOURS STANDBY KELLY DOWN TOTAL 4,791.26 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 68,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. CONTINUO I LINE . 18 FROM SPUD PRE JOB SAFETY METING. L/D I LINE CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN SHOOTING NIPPLE NIPPLE UP BELL NIPPLE. ROTATING HOURS PRE JOB SAFETY METING. P/U EZSV BHA DAILY MUD COST ($) 990.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING. P/U 4" DP . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 18 Date: 01-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
248 | 248 | Continue RIH Wash down with 1000 lit/hr and 1350 psi from 1694 m to 1754 m. Tag cement on 1754 m. | 3 | WHITE | 2023-03-01 | REAMING | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1 | KEY MANHATTAN | MENAM
249 | 249 | Change tripping bails to drilling bails. O T | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 0.5 | KEY MANHATTAN | MENAM
250 | 250 | RIH 8 1/2" drilling BHA on 5" DP from 251m to 1694 m. U | 6 | WHITE | 2023-03-01 | TRIPS | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 6.5 | KEY MANHATTAN | MENAM
251 | 251 | RIH 8 1/2" drilling BHA on 5" HWDP + Jar to 251 m. R | 6 | WHITE | 2023-03-01 | TRIPS | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1 | KEY MANHATTAN | MENAM
252 | 252 | Continue pick up, make up and RIH with 8 1/2" drilling BHA from 16 meters to 23 meters as per Baker DD. M/U 1st stand HWDP connect on TDS and perform shallow test as per DD instruction. 2 | 6 | WHITE | 2023-03-01 | TRIPS | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1.5 | KEY MANHATTAN | MENAM
253 | 253 | Backer perform electrical test MWD tool. | 6 | WHITE | 2023-03-01 | TRIPS | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 0.5 | KEY MANHATTAN | MENAM
254 | 254 | Pick up, make up and RIH to 16 m with 8 1/2" drilling BHA as per Baker DD instructions. 1D1E:P3T0H IN1TE2R:0V0AL D0.R5I0LL 6 Backer performFO eRleMcAtrTicIOaNl test MWD tool. ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-01 | TRIPS | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 3.5 | KEY MANHATTAN | MENAM
255 | 255 | Tidy up rig floor, preparing for pick up BHA. Meanwhile lubricate TDS. | 1 | WHITE | 2023-03-01 | RIG UP & TEAR DOWN | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 0.5 | KEY MANHATTAN | MENAM
256 | 256 | Pull out, B/Out and L/Down 11" test assembly. P/Up B/Out and L/Down Tam packer and preparing for back load. | 15 | WHITE | 2023-03-01 | TEST BOP | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1.5 | KEY MANHATTAN | MENAM
257 | 257 | Perform pressure test BOP and TDS as follow Test #1 -Bottom Ram 5" 1 -Upper IBOP 300/5000psi R Test #2 -Middle Ram 2 7/8" - 5" U -Lower kill co-flex hose O T -Lower IBOP no TDS 300/5000psi Test #3 -Top Ram 4 1/2" - 7" -Upper, lower, kill and choke HCR valve -FOSV 300/5000psi Test #4 -Top Ram 4 1/2" - 7" -Upper, lower kill and choke manual valve 300/5000pis Test #5 -Annular 13 5/8" 5K -Kelly hose on TDS 300/3500psi Test #6 -Shear Ram -Upper kill, upper choke and lower choke co-flex hoses 300/5000psi | 15 | WHITE | 2023-03-01 | TEST BOP | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 5 | KEY MANHATTAN | MENAM
258 | 258 | R/Up, M/Up and RIH with 11" test plug assembly. | 15 | WHITE | 2023-03-01 | TEST BOP | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3/5 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 52 STD. D.P. 5.00 4,925.98 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.43 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 5,781.37 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 16 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 132 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 16 Date: 01-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1 | KEY MANHATTAN | MENAM
259 | 259 | RIH WITH HALLIBURTON CMT STINGER WHILE P/U 4" DP FROM DECK RIH TO 3438 FT. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 18 Date: 01-Mar-23 | 6 | WHITE | 2023-03-01 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. E LINE. CONTINUOD 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:30 18:30 23:30 I 1 OTHER 9.63 4.95 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 XO 6.50 2.65 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 153 DP 4.00 4,783.66 MANUFACT. VISCOSITY 30 30 30 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE CLC 33 XPALEMAR 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION PAC LV 1 HOURS STANDBY KELLY DOWN TOTAL 4,791.26 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 68,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. CONTINUO I LINE . 18 FROM SPUD PRE JOB SAFETY METING. L/D I LINE CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN SHOOTING NIPPLE NIPPLE UP BELL NIPPLE. ROTATING HOURS PRE JOB SAFETY METING. P/U EZSV BHA DAILY MUD COST ($) 990.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING. P/U 4" DP . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 18 Date: 01-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 4.5 | HIGH ISLAND V | MENAM
260 | 260 | HPJSM, MIU 9-5/8" HALLIBURTON CMT STINGER. | 6 | WHITE | 2023-03-01 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. E LINE. CONTINUOD 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:30 18:30 23:30 I 1 OTHER 9.63 4.95 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 XO 6.50 2.65 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 153 DP 4.00 4,783.66 MANUFACT. VISCOSITY 30 30 30 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE CLC 33 XPALEMAR 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION PAC LV 1 HOURS STANDBY KELLY DOWN TOTAL 4,791.26 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 68,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. CONTINUO I LINE . 18 FROM SPUD PRE JOB SAFETY METING. L/D I LINE CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN SHOOTING NIPPLE NIPPLE UP BELL NIPPLE. ROTATING HOURS PRE JOB SAFETY METING. P/U EZSV BHA DAILY MUD COST ($) 990.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING. P/U 4" DP . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 18 Date: 01-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
261 | 261 | HPJSM. NID 9-518" SHOOTING NIPPL & NU BELL NIPPLE. | 23 | WHITE | 2023-03-01 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. E LINE. CONTINUOD 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:30 18:30 23:30 I 1 OTHER 9.63 4.95 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 XO 6.50 2.65 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 153 DP 4.00 4,783.66 MANUFACT. VISCOSITY 30 30 30 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE CLC 33 XPALEMAR 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION PAC LV 1 HOURS STANDBY KELLY DOWN TOTAL 4,791.26 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 68,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. CONTINUO I LINE . 18 FROM SPUD PRE JOB SAFETY METING. L/D I LINE CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN SHOOTING NIPPLE NIPPLE UP BELL NIPPLE. ROTATING HOURS PRE JOB SAFETY METING. P/U EZSV BHA DAILY MUD COST ($) 990.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING. P/U 4" DP . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 18 Date: 01-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
262 | 262 | Cont RIH 8 1/2" RSS BHA F/ 66 ft T/ 286 ft. U O | 6 | WHITE | 2023-03-01 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 3.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 650 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL 883 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS 13.75 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE pac l 15 soiufiake medium15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION Barofiber fine 15 caustic soda 15 HOURS STANDBY KELLY DOWN soda ash 10 max sheild 4 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON max guard 4 Lubricant 4 SEALS DULL PULLED WT. OF STRING marble fine 2 marble medeum 1 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 43 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 1,920.00 TOTAL MUD COST ($) 7,194.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 46 Date: 01-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
263 | 263 | CONTD RIH 4.5” 13 CR 12.6 PPF BGT-1 TBG CTC ASSY WITH POP F/1287M TO-2558M IN SGLS. DRIFTED ALL JTS PRIOR TO RIH. TORQUE ALL JOINTS WITH W/FORD TTM RIH IN SHIFT TOTAL 134 JOIN IN SHIFT (TOTAL 270 JOINS | B | WHITE | 2023-03-01 | TUBING TRIPS |  | HELD PJSM REGARDING RIH TUBING. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PRESSURE TEST PRODUCTION CHOKE MANIFOLD. TOOK TOFS @ TOTAL DAYWORK 0.00 0.00 16:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED NO. OF DAYS ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 70 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH TUBING. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PRESSURE TEST PRODUCTION CHOKE MANIFOLD. TOOK TOFS @ 16:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 11.5 | J T ANGEL | INDIA
264 | 264 | R/DN W/FORD EQUIPMENT. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | B | WHITE | 2023-03-01 | TUBING TRIPS |  | HELD PJSM REGARDING RIH TUBING. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PRESSURE TEST PRODUCTION CHOKE MANIFOLD. TOOK TOFS @ TOTAL DAYWORK 0.00 0.00 16:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED NO. OF DAYS ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 70 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH TUBING. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PRESSURE TEST PRODUCTION CHOKE MANIFOLD. TOOK TOFS @ 16:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 70 Date: 01-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
265 | 265 | Run Drill-in 9-5/8" casing with 9.2 ppg PHPA from 322' MD to 359' MD. Observed casing hange up. Fill up casing and continue to RIH to 622' MD. Observed casing off center through CTU and casing alignment is not straight down to MSL. Decesion made to POOH due IADCDAILY DRILLtoI sNidGe t rRacEk PonO MRL.T FORM - PROOF COPY | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
266 | 266 | Pump 100 bbls 200 PPB LCM and spot same. Allow LCM to soak. Pump 30 bbls mud cap every 30 mins. N | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
267 | 267 | Allow LCM to soak mean while pump 75 pcf 85 bbls mud in annulus, reciprocate string and rotate 10 rpm, 8- 10K trq, observed partial returns. Monitor annulus- | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2.25 | ACHEIVER | MENAM
268 | 268 | Cont to Pump 100 bbls 200 ppb LCM pill #4 and spot same. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
269 | 269 | Allow LCM to soak mean while pump 75 pcf 85 bbls mud in annulus, reciprocate string and rotate 10 rpm, 8- 10K trq,Line up Trip tank Observe 450 bbls p/hr losses. 2 | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2 | ACHEIVER | MENAM
270 | 270 | Allow LCM to soak mean while prepare LCM Cut down mud wt to 74 pcf.Pump 30 bbls mud cap every 30 mins. R | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2.25 | ACHEIVER | MENAM
271 | 271 | Pump 30 bbls 200 ppb LCM pill #5 and displace with 300 bbls of 74 pcf mud. Pump 70 bbls 200 ppb LCM and spot same with 74 pcf U mud. Reciprocate string and rotate 10 rpm, 8- 10K trq, No returns observed, O T | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
272 | 272 | Allow LCM to soak. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.25 | ACHEIVER | MENAM
273 | 273 | Pump 200 bbl 74 pcf mud in annulus.Line up Trip tank Observe 390 bbls p/hr losses. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
274 | 274 | pump 88 pcf 30 bbls mud in annulus every 30 mins, Pump 10bbls 74pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 4 | ACHEIVER | MENAM
275 | 275 | woc. m/w pooh with 5” m. shoe assy f/1183 m to surf & l/dn same. | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
276 | 276 | m/up 8-1/2” bit bha & rih the assy w/ 5-1/2” dp stds to 1127 m. | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 4 | PARAMESHWARA | INDIA
277 | 277 | woc. m/w service ‘a’ sec w/h bolts iip. 1 | 13 | WHITE | 2023-03-02 | WAIT ON CEMENT | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
278 | 278 | Pump 30 bbls 200 ppb LCM and displace in annulus. Allow LCM to soak mean while pump 75 pcf 85 bbls mud in annulus, reciprocate H string and rotate 10 rpm, 8- 10K trq, observed partial returns. Monitor annulus- G I | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 4 | ACHEIVER | MENAM
279 | 279 | woc. m/w service ‘a’ sec w/h bolts iip. R | 13 | WHITE | 2023-03-02 | WAIT ON CEMENT | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 4.5 | PARAMESHWARA | INDIA
280 | 280 | Cont circ bottoms up @ 300 gpm/150 psi. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
281 | 281 | Pooh 8 ½” slick bha F/1335 m to 152 m. | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
282 | 282 | Cont Pooh F/152 m to surf. Back off & lay down bit, bit sub & jar. 2 | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
283 | 283 | Make up 5” mule shoe with 5 ½” dp & Rih to 1330 m. R | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
284 | 284 | Pick up & make up test assy. circulate condition 1 cycle. U | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
285 | 285 | Hook up test assy. &surface line.Test cmt line @ 3500psi.Perform injec. test @1bpm -380psi. O T | 17 | WHITE | 2023-03-02 | PLUG BACK | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
286 | 286 | Pooh F/1330 m to 1320. Make up test assy. C&c prior cmt job. | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2.5 | PARAMESHWARA | INDIA
287 | 287 | Cont cmt job as per plan. Flush & test line @3500 psi ok. Pump 20 bbls drill water pre-flush, mix & pump 40 bbls (15.8 ppg) cmt slurry, 10 bbls Drill water post-flush. Displace with 70 bbls gel mud. | 17 | WHITE | 2023-03-02 | PLUG BACK | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
288 | 288 | Pooh F/ 1320 m to 1080 m. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
289 | 289 | Continue to RIH 9-5/8" casing with 12" drill-in shoe to 317' MD. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
290 | 290 | M/U Drilling Spear with TDS. R | 23 | WHITE | 2023-03-02 | OTHER3 | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.75 | CHAOPHRAYA | SOUTH EAST ASIA
291 | 291 | Spud well and drill-in 9-5/8" casing with 12" drill-in shoe to 645' MD. Hit hard formation. Attempted to drill with difference parameter - U O no success. T Note: T - 1st attempted drill with difference flow 400 - 800 gpm. H - 2nd attempted drill with difference RPM 40 - 80 RPM. G I - 3rd attempted drill with more WOB 10-12 Klbs(Max 18 Klbs). N | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.5 | CHAOPHRAYA | SOUTH EAST ASIA
292 | 292 | con't rih f/1127m to 1160m and w/dn f/1160m to 1335m to tag cmt @ 1335m with 10 kips . U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-02 | TRIPS | PSW | Held PJSM For RIH with 8.5 bit. 17. Plug Back 2.50 Saver sub 5 1/2 ' connection-456. 18. Squeeze Cement Wash pipe hours: 235 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 42 STD. D.P. 5.50 3,927.33 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,943.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-458. NO. OF DAYS Wash pipe hours: 235 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 22 Date: 02-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
293 | 293 | Displace well with 9.2 PHPA WBM. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
294 | 294 | POOH f/ 11276ft to 11110ft, Allow LCM to soak mean while pump 75 pcf mud in annulus, pump in string evry 10 mins, Reciprocate T string and rotate 10 rpm, 8- 10K trq, No returns observed, T | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2 | ACHEIVER | MENAM
295 | 295 | Drill 8 1/2" F/ 11232 ft T/ 11276 ft. WOB- 30 klbs, RPM-160, TRQ- 12-18k, 500-600 gpm, 1600-2500 psi. | 2 | WHITE | 2023-03-02 | DRILL ACTUAL | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
296 | 296 | Circulate 3x B/Up as per mud eng. instructions with 1800lit and 1850psi. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.50 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 5/8 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 9.8 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 17 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 17 Date: 02-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 2 | KEY MANHATTAN | MENAM
297 | 297 | Preparing and new mixing mud SW-SS-Extradrill for 8 1/2" hole section as per mud eng. instruction. 1 Meanwhile every 2hr perform break circulation and very 4hr circulate internal volume. R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.50 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 5/8 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 9.8 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 17 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 17 Date: 02-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 4.5 | KEY MANHATTAN | MENAM
298 | 298 | Preparing and mixing new mud SW-SS-Extradrill for 8 1/2" hole section as per mud eng. instruction. Meanwhile every 2hr perform break circulation and very 4hr circulate internal volume. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 17 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.50 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 5/8 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 9.8 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 17 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 17 Date: 02-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 12 | KEY MANHATTAN | MENAM
299 | 299 | POOH with HSFT-II HSDL tools from 12000' MD to surface. | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 1.75 | KRATHONG | SOUTH EAST ASIA
300 | 300 | Rig down wire line equipment. | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.5 | KRATHONG | SOUTH EAST ASIA
301 | 301 | Retrieve wear bushing. 1 | 23 | WHITE | 2023-03-02 | OTHER3 | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.25 | KRATHONG | SOUTH EAST ASIA
302 | 302 | Hold pre-job meeting rig up tubular handing and RIH 2-7/8" tubing. R | 23 | WHITE | 2023-03-02 | OTHER3 | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.25 | KRATHONG | SOUTH EAST ASIA
303 | 303 | Rig up tubing handling equipment. U | B | WHITE | 2023-03-02 | TUBING TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.25 | KRATHONG | SOUTH EAST ASIA
304 | 304 | Pick up shoe track, run 2-7/8” tubing as per tally from surface to 12434' MD. O T | B | WHITE | 2023-03-02 | TUBING TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 5 | KRATHONG | SOUTH EAST ASIA
305 | 305 | M/U TRSV test control line and TRSV to 7500 psi for 5 min, and bleed off to zero, pressure up to 4000 psi and keep pressure in control line 4000 psi.Continue RIH 2-7/8” TBG with TRSV from 12434' MD to12810' MD.(P/U 200 k, S/O 120 k) | B | WHITE | 2023-03-02 | TUBING TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.75 | KRATHONG | SOUTH EAST ASIA
306 | 306 | M/U 2-7/8" tubing hanger, connect control line and pressure test to 7500 psi 5 min. Bleeding off to Zero. Flush stack with s/w and drain riser prior to landing TBG. Continue RIH with 2-7/8” tubing hanger from 12810' MD to 12896' MD. Test seals to 6500 psi, Energize snap ring and pull test 10K overpull S/O WT. Release running tool and POOH to surface. | B | WHITE | 2023-03-02 | TUBING TRIPS | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.5 | KRATHONG | SOUTH EAST ASIA
307 | 307 | N/D BOP, on well MAWF-42 slot B. Skid Drilling Package to center line and R/Dn Riser. Note: Well MAWF-42 Cut off at 10:00am | 14 | WHITE | 2023-03-02 | N/UP BOP | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 0.75 | KRATHONG | SOUTH EAST ASIA
308 | 308 | Observed total losses at 11276ft, Drop SDD dart and activate PBL. Pump 50 bbls 150 ppb LCM and displace in annulus. mean while R reciprocate string and rotate 10 rpm, 8- 10K trq, No returns observed, U O | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2.25 | ACHEIVER | MENAM
309 | 309 | R/Up Cement Head. Commence circulating offline prior to cement job. Lay down 4" DP and all tubular on derrick. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 2 | KRATHONG | SOUTH EAST ASIA
310 | 310 | CONTINUE WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE ETC), 200MT D/WATER FOR MUD PREPARATION FOR 8-1/2” PHASE DRILLING, BACKLOAD BOAT FOR 1100 BBL SOBM (12.5PPG). 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 23.46 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 46 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 46 Date: 02-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 12 | RON TAPPMEYER | INDIA
311 | 311 | CONTINUE WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE ETC), 200MT D/WATER FOR MUD PREPARATION FOR 8-1/2” PHASE DRILLING, BACKLOAD BOAT FOR 1100 BBL SOBM (12.5PPG). 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 46 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 23.46 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 46 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 46 Date: 02-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 12 | RON TAPPMEYER | INDIA
312 | 312 | CONTINUE LOWER 13 3/8"(BTC,68PPF,P110) CASING FROM 171 M to 499 M.INSTALL CENTRALIZER AS PER TALLY. F/UP EVERY 5 JNTS. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2.5 | F G MCCLINTOCK | INDIA
313 | 313 | R/UP CIRC HEAD AND SURFACE LINES,BREAK CIRC @ SHOE WITH 250 GPM / 260 PSI.RIG UP SPIDER ELEVATOR AND 1 SPIDER SLIP. R | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
314 | 314 | CONTD LOWER 13 3/8" CSG (BTC,68PPF,P110) F / 499 M TO 1479 M.FILL UP EVERY 5 JOINTS.(TOTAL 130 JOINTS).FURTHER U IP. O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 8.5 | F G MCCLINTOCK | INDIA
315 | 315 | CONTINUE LOWERING 13 3/8"CASING (BTC,P110,68PPF) FROM1479M TO1669M(FILL EVERY 7 JNTS),TOTAL 147 JNTS | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2.5 | F G MCCLINTOCK | INDIA
316 | 316 | CIRCULATE & CONDITION MUD PRIOR TO CMT JOB. (GPM500,510PSI/GPM550,600PSI) | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2.5 | F G MCCLINTOCK | INDIA
317 | 317 | R/DN CIRCULATION HEAD & R/UP CMT HEAD,SURFACE LINE AND TEST CMT & MUD PUMPS LINES @2000PSI OK. 2 CIRCULATE & CONDITION MUD PRIOR TO CMT JOB. MEAN WHILE CHEMICAL MIXING ON BATCH MIXER. R | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2 | F G MCCLINTOCK | INDIA
318 | 318 | PUMP 20 BBLS BASE OIL FROM RIG MUD PUMP,PUMP 20 BBLS D/W & 250BBLS CMT SLURRY OF 15.5PPG, DROP TOP U PLUG, DISPLACE THE SAME WITH SOBM. BUMP PLUG @1250 PSI. BLEED OFF PRESSURE & CHECK NRV OK. O T | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 3 | F G MCCLINTOCK | INDIA
319 | 319 | CLOSE ANNULAR BOP & WAITING ON CMT (CLOSE BOP FOR 6HRS) IN PROGRESS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | 13 | WHITE | 2023-03-02 | WAIT ON CEMENT | FGM | HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO RIG UP SPIDER SLIP & ELEVATOR. 17. Plug Back SAVER SUB :- HT-55 - 98 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 1 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:55 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT RIH 13 3/8" CSG .TBSM PRIOR TO CEMENT JOB. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 98 CONNECTIONS NO. OF DAYS WASH PIPE :- 102 HRS. 28 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS CHECK C.O.M & CHOKE MANIFOLD OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 28 Date: 02-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2 | F G MCCLINTOCK | INDIA
320 | 320 | Circulate offline prior to cement job. Pump spacer followed by cement as per program. Cement in place at 16:00 hrs. Continued lay down 4" DP from derrick, Rig down cement head and R/Up X/Mas Tree and test same. Clean out Trip Tanks, Sand Traps and flow line. Open upper pipe ram Fwd/Aft bonnet for change operating piston seal, Disconnect S.Sub. Upper/lower IBOP from TDS main 2 shaft, Platform disconnect all service hose, move equipment basket to main deck, Rig up sling for lay down bell nipple over shots. R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | SDK | Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and 17. Plug Back KEMS. Performed daily drilling checks and greased crown blocks. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 6.50 NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME I SIZE 6.13 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE D504S PV/YP O F. Other 4 SERIAL NO. 5339806 GELS C G. Other 5 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 8,651 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Reviewed TBRA before do the task. Used PBED process. Checked all well control equipment and TOTAL DAYWORK 0.00 0.00 KEMS. Performed daily drilling checks and greased crown blocks. NO. OF DAYS 6 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDK Job:MAWF-42 Rpt No: 7 Date: 02-Mar-23 | MAWF-42 | MAWF-42 | Mar-23 | 12 | KRATHONG | SOUTH EAST ASIA
321 | 321 | Drilling cement from 1762 m to 1804 m with 1800 lit, 1800 psi, 80RPM and 10000-15000ft/pound TRQ. | 3 | WHITE | 2023-03-02 | REAMING | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.50 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 5/8 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 9.8 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 17 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 17 Date: 02-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 5.5 | KEY MANHATTAN | MENAM
322 | 322 | Pump out of the hole to ML with 9.2 ppg WBM, GPM:800. Pull out of the hole. L/D Drilling spear. Note: - L/D 8 singles joint of 9-5/8" casing side way. - Rack back 3 stands of 9-5/8" casing on the derrick. | 6 | WHITE | 2023-03-02 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.25 | CHAOPHRAYA | SOUTH EAST ASIA
323 | 323 | 2nd Spud well at 09:00 hours. Drill-in 9-5/8" casing with 9.2 ppg WBM (split stream) from 322' MD to 642' MD. Hit hard formation. Attempted to drill with difference parameter - no success. Note: Drill hard formation with WOB 3-5 Klbs. | 2 | WHITE | 2023-03-02 | DRILL ACTUAL | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2 | CHAOPHRAYA | SOUTH EAST ASIA
324 | 324 | Install 4 1/2'' elevator . Pike up 4-1/2" tubing stand with XOs assembly. Land and M/u to X-mas tree. Rig up SLB slick line pump-in H G tee, braided line BOPs and function test. M/u QTS sub, 33' lubricator and grease head. I | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 5.5 | TENACIOUS | WEST AFRICA
325 | 325 | Line up cement line fill up Tubing Riser from Xmas Tree + Lubricator with 9.5 ppg brine and pressure test against crown valve N 250/4500 psi, 5/5 mins OK. | 22 | WHITE | 2023-03-02 | SURFACE TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.75 | TENACIOUS | WEST AFRICA
326 | 326 | Open bleed off confirm pressure zero in slickline lubricator. Disconnect lubricator from QTS sub. | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
327 | 327 | Pick up Access ESP motor assembly from cantilever deck and lower in mouse hole. Pick up Schlumberger ESP protectors and make up on Access ESP motor assembly. | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 2.5 | TENACIOUS | WEST AFRICA
328 | 328 | Pick up SLB ESP protector and Access ESP Motor assembly from mouse hole and secure inside slick line BOP.Slick line connect GS tool string to ESP motor assembly. | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
329 | 329 | Connect lubricator and pressure test QTS 2000 psi/5 minutes. | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
330 | 330 | Open master valve. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
331 | 331 | Equalize WH pressure 600psi, open crown valve. SLB slck line RIH with AccessESP motor and Plug Arm. Unable to pass below Rig Floor. Close master valve. Bleed off Lubricator. Back out QTS and lay out AccessESP Motor. | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 3 | TENACIOUS | WEST AFRICA
332 | 332 | Held PJSM. Connect QTS. Cement unit bull head with 30bbls 9.5ppg brine 6bpm/3000psi. Close master valve. Bleed off pressure. 2 | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.75 | TENACIOUS | WEST AFRICA
333 | 333 | Back out QTS. Make up AccessESP motor/Plug Arm tool string. Connect QTS. R | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
334 | 334 | Equalize WH pressure to 600psi, Open master valve. SLB Slick line RIH with AccessESP motor/ Plug Arm to 7190ft. U | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 2.75 | TENACIOUS | WEST AFRICA
335 | 335 | Access ESP perform checks on ACP. No confirmation Motor latch into profile. Attempt to jar down to set Motor into profile. No O T success. POH and observed over pull at 7161ft. Work string and attempt to pull free. No success. Jar down and shear GS tool. | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 4.5 | TENACIOUS | WEST AFRICA
336 | 336 | POH with GS tool string to 3500ft. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | E | WHITE | 2023-03-02 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
337 | 337 | Skid transverse to PORT on well A-02. T | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
338 | 338 | HELD SAFETY STAND DOWN MEETING, DISCUSSED: SWA, PJSM, LIFTING OPERATIONS, SLIP/TRIP HAZARDS, 1 SUPERVISION DURING CREW CHANGE. HAND & FINGERS INJURIES R | 23 | WHITE | 2023-03-02 | OTHER3 | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
339 | 339 | BKR LOGGING RUN #5: PERFORM VIT STATION #1 AT 5271 FT. VOLUME OF FORMATION FLUID PO 195 LITRES. U *MONITOR WELL ON TRIP TANK O T | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 6.5 | HIGH ISLAND II | MENAM
340 | 340 | RIH & MOVE TO NEXT STATION @ 5286'.. | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
341 | 341 | BKR LOGGING RUN #5: PERFORM VIT STATION #T AT 5286 FT. *MONITOR WELL ON TRIP TANK DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 4.25 | HIGH ISLAND II | MENAM
342 | 342 | BKR LOGGING RUN #5: PERFORM VIT STATION #T AT 5286 FT. *MONITOR WELL ON TRIP TANK | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 4 | HIGH ISLAND II | MENAM
343 | 343 | 2 | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 5.75 | HIGH ISLAND II | MENAM
344 | 344 | POOH BKR LOGGING RUN #5: STIKE TEST& PERFORM PUMP OUT STATION # AT 5560 FT. R *MONITOR WELL ON TRIP TANK. U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.25 | HIGH ISLAND II | MENAM
345 | 345 | RIG MOVE PREPARATION.M/W CONT'D BACKLOAD MANIFESTED CARGO FROM RIG TO OSV OFFSHORE ENERGY. | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID TOTAL DAYWORK 0.00 0.00 CANTILEVER DECK TO TOW POSITION. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID CANTILEVER DECK TO TOW POSITION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 1 | TRIDENT II | INDIA
346 | 346 | MOVE ALL RIG TOOLS AND EQUIPMENTS FROM PLATFORM. WASH AND CLEAN PLATFORM. HOOK UP ALL SERVICE HOSES, DISCONNECT FLOODING LINE, REMOVE GANG WAY, FURTHER RIG MOVE PREPARATION IS IP. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID TOTAL DAYWORK 0.00 0.00 CANTILEVER DECK TO TOW POSITION. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID CANTILEVER DECK TO TOW POSITION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 11 | TRIDENT II | INDIA
347 | 347 | CONT'D CLEAR PLATFORM NW#1Z.DISCONNECTED ESD LINE FROM NW PLATFORM. | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID TOTAL DAYWORK 0.00 0.00 CANTILEVER DECK TO TOW POSITION. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID CANTILEVER DECK TO TOW POSITION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 1 | TRIDENT II | INDIA
348 | 348 | HELD PJSM. M/A & SKIDDED CANTILEVER TO TOW POSITION. FURTHER SECURING & SEA FASTENING IIP. | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID TOTAL DAYWORK 0.00 0.00 CANTILEVER DECK TO TOW POSITION. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID CANTILEVER DECK TO TOW POSITION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 5 | TRIDENT II | INDIA
349 | 349 | CONT'D SECURING & SEA FASTENING IIP. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID TOTAL DAYWORK 0.00 0.00 CANTILEVER DECK TO TOW POSITION. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO R/DN FLOODING LINE, TBSM PRIOR TO RIG MOVE PREPARATION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO DISCONNECT ESD LINE FROM PLATFORM, TBSM PRIOR TO SKID CANTILEVER DECK TO TOW POSITION. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 2 Date: 02-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 6 | TRIDENT II | INDIA
350 | 350 | BKR LOGGING RUN #5: PERFORM VIT STATION #1 AT 5271 FT. *MONITOR WELL ON TRIP TANK | 11 | WHITE | 2023-03-02 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 35 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE FOR RIG MOVE . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE . * CLEAN MUD PITS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 35 Date: 02-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
351 | 351 | P/U and RIH with new casing drill in assembly to 353' MD. Observed casing hang up. Attempted to work casing down with rotation - no success. M/U 9-5/8" casing spear and wash down casing - no success. Decision was made to spud new well. | 6 | WHITE | 2023-03-02 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 3 | CHAOPHRAYA | SOUTH EAST ASIA
352 | 352 | Skid cantilever outboard 12 ft. T | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
353 | 353 | Skid transverse to PORT center line. R | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
354 | 354 | Circulate and displace well with 9.2 ppg PHPA WBM. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
355 | 355 | Pump out of the hole with from 642' to 447' with 800 gpm. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-02 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.75 | CHAOPHRAYA | SOUTH EAST ASIA
356 | 356 | Continue to Pump out of hole with 9-5/8" casing from 447' MD to ML with 9.2 ppg WBM, GPM:800. Pull out of the hole. L/D Drilling spear. Note: 2 - L/D 8 singles joint of 9-5/8" casing side way. R - Rack back 3 stands of 9-5/8" casing on the derrick. U | 6 | WHITE | 2023-03-02 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.25 | CHAOPHRAYA | SOUTH EAST ASIA
357 | 357 | P/U and M/U BHA #3 with 12-1/4" Rock Bit with MWD. RIH 6 single joints of 6-3/4" Drill collar and 4" HWDP to 638' MD. Tag weight 5 O T Klbs. M/U TDS and take survey to confirm inside of hole (0.86deg). | 6 | WHITE | 2023-03-02 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 3.75 | CHAOPHRAYA | SOUTH EAST ASIA
358 | 358 | 3rd Spud well at 17:00 hours. Drill 12-1/4" hole with 9.2 ppg WBM from 638' MD to surface section TD at 825' MD / 825' TVD. Note: - Drilling hard formation from 638' MD to 647' MD with 65 RPM, 600 gpm 3-5 Klbs. - Pump 50 bbls HI-VIs Sweep while drill with hard formation. - Back ream full stand to make sure no obstruction. | 2 | WHITE | 2023-03-02 | DRILL ACTUAL | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.75 | CHAOPHRAYA | SOUTH EAST ASIA
359 | 359 | Circulate B/U with 9.2 ppg PHPA WBM. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
360 | 360 | Back ream out of the hole with 9.2 ppg WBM to 1 stand below mud line, GPM:800 RPM:120. Pump out the last stand to ML and pull out of the hole. Rack back BHA in derrick. Note: Observed TQ increase from 0.5 Klbs to 3 Klbs while back ream out of hole at 645' MD. Ream down/ up full stoke to make sure no obstruction. | 3 | WHITE | 2023-03-02 | REAMING | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
361 | 361 | Pull out of the hole to 444' MD and observed casing bend on stds #6. L/D bent joints side ways. NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2 | CHAOPHRAYA | SOUTH EAST ASIA
362 | 362 | Run Drill-in 9-5/8" casing with 9.2 ppg PHPA from 322' MD to 359' MD. Observed casing hange up. Fill up casing and continue to RIH to 622' MD. Observed casing off center through CTU and casing alignment is not straight down to MSL. Decesion made to POOH due to side track on ML. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
363 | 363 | Pull out of the hole to 444' MD and observed casing bend on stds #6. L/D bent joints side ways. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH with 9-5/8" CSG,Riser drilling with 12.1/4' BHA, Service all TOTAL DAYWORK 0.00 0.00 drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 7 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 7 Date: 02-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2 | CHAOPHRAYA | SOUTH EAST ASIA
364 | 364 | Shipyard work scope: Drill crew: Continue with housekeeping and paint projects 1 Continue to troubleshoot mud pit suction line issues. Changing seals and servicing as required. R Empty choke and kill manifold of preservation fluid. U Commence greasing and functioning choke and kill manifold valves. O T Perform Mapping of trip tank 2. Continue to repair and replace suction valve hold down bolts in pit room. Continue with water maker room chipping / buffing. Deck crew: Continue with chipping / buffing accommodation roof in preparation for painting. Continue with chipping / buffing cantilever hand rails in preparation for painting. Technical department: Continue with drilling office overhaul. Perform PM routines as per Shelf schedule. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | SDF | Shipyard work scope: 17. Plug Back Continue with paint and maintenance projects. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT T C. Treating E DC IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope: TOTAL DAYWORK 0.00 0.00 Continue with paint and maintenence projects. NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 3 Date: 02-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 12 | FORTRESS | NORTH SEA
365 | 365 | Shipyard work scope: Drill crew: Continue with housekeeping and paint projects 2 Continue greasing and functioning choke and kill manifold valves. R Re-fill choke and kill manifold with preservation fluid. U Continue to perform Mapping of trip tank 2. O T Continue to repair and replace suction valve hold down bolts in pit room. Continue with water maker room chipping / buffing. Replace damaged pipe lagging onto rig floor deluge line. Grease TDX dolly rollers. Assist technical department with drilling office over haul. Deck crew: Continue with chipping / buffing accommodation roof in preparation for painting. Continue with chipping / buffing cantilever hand rails in preparation for painting. Technical department: Continue with drilling office overhaul. Perform PM routines as per Shelf schedule. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 3 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | SDF | Shipyard work scope: 17. Plug Back Continue with paint and maintenance projects. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT T C. Treating E DC IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope: TOTAL DAYWORK 0.00 0.00 Continue with paint and maintenence projects. NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 3 Date: 02-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 12 | FORTRESS | NORTH SEA
366 | 366 | PJSM with crew prior to skid cantilever outboard. U O | 23 | WHITE | 2023-03-02 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
367 | 367 | Continue to drill 12 1/4'' hole section as per DD instruction from 7514ft to 7556ft pump with 800 gpm, 3817 psi, 120 rpm, 16 -17 1 torque , 5-10kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt R 300k, s/o wt-215k, Rot-wt 250k. Rop- 50 ft / hr ( INC 27.21 ,Azimuth -357.52) U | 2 | WHITE | 2023-03-02 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1 | MENTOR | WEST AFRICA
368 | 368 | Continue to drill 12 1/4'' hole section as per DD instruction from7556ft to7705ft pump with 800 gpm, 3799 psi, 120 rpm, 16 -17 O T torque , 5-10kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 300k, s/o wt-220k, Rot-wt 255k. Rop- 50 ft / hr ( INC 27.04 ,Azimuth -352.93) | 2 | WHITE | 2023-03-02 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 4 | MENTOR | WEST AFRICA
369 | 369 | Stop drilling,Wait on solid control equipment,Meanwhile circulate and reciprocate string with 800 gpm,3785psi, 100 rpm, torque15-16. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 7705 8319 Drill 120 15000 6.500 70 6.500 70 794.4 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 7,733 28.75 334400..88 6,977.5 7,830 30.23 335555..3311 6,878.2 7,926 31.78 332299..3322 6,960.7 8,022 33.64 332266..55 7,041.6 8,119 35.95 332233..3311 7,120.6 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1 | MENTOR | WEST AFRICA
370 | 370 | Waiting on solid control equipment, Meanwhile continue to circulate and reciprocate string with 800 gpm,3785psi, 100 rpm, torque15- 16. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1 | MENTOR | WEST AFRICA
371 | 371 | Continue to drill 12 1/4'' hole section as per DD instruction from7705ft to 8130ft. pump with 800 gpm, 3962 psi, 120 rpm, 17-18 2 torque , 15-18kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up- R wt 320k, s/o wt-220k, Rot-wt 260k. Rop- 150 ft / hr ( INC 33.64 ,Azimuth -326.50). U | 2 | WHITE | 2023-03-02 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 6 | MENTOR | WEST AFRICA
372 | 372 | Continue to drill 12 1/4'' hole section as per DD instruction from 8130ft to 8319ft. with 800 gpm, 3968 psi, 120 rpm, 17-18 torque , 15- O T 18kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 320k, s/o wt-220k, Rot-wt 260k. Rop- 150 ft / hr ( INC 33.64 ,Azimuth -326.50). | 2 | WHITE | 2023-03-02 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 3 | MENTOR | WEST AFRICA
373 | 373 | Made connection and staged up pumps to drilling rate after connection, observed loss in pressure from 3900 psi to 3400 psi. Troubleshoot same and observed wash out on DP connection. L/D washed out joints. Made connection, staged up pumps to drilling rate and observed relatively low standpipe pressure. troubleshoot same and observed standpipe bleed off manual and choke valves washed out. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | 8 | RED | 2023-03-02 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 2 | MENTOR | WEST AFRICA
374 | 374 | Drilling: Carry out Diverter function tests with MODU. R Function all valves. Continue function test tomorrow. U O Assist Mech dept work on Koomey unit. T Assist Mech dept trouble shoot and repair HawkJaw lift ram cylinder issue. T Prepare to remove Drill floor rotary for inspection and hose measuring for replacement. H Mech Dept: G I Mechanic and motor man daily check. N Top koomey fluid. Continue assist for changed out sewage pipeline. 4000 hrs.PM for compressor #3. Continue close punch list for koomey unit. Clean all air compressor’s air filter. Function test for emergency engine. House keeping in engine room. Today hrs Total hrs M/E#1 24 45897 M/E#20 44326 M/E#30 47440 M/E#40 45041 DEPTH INTERVAL DRILL M/E#50 F 4O4R9M6A5TION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP FROM TO RCEOARME NO. E-Gen 0(S H O W C O 1R7E2 5RECOVERY) STAPEBELDE BOINT PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT ET Dept: Work with NSSL service technician on SSAS and NDB. Checks to Cyber chair Purge loss. Unable to identify any leaks and chair was stared with purge system in bypass. HORIZ HORIZ HORIZ DEPTH DEV. DICRh.ecks anTdV rDepairs DtoIS MP.ain RDigE PHTPHU. DEV. DIR. TVD DISP. DEPTH DEV. DIR. TVD DISP. DEVIATION Attended close out meeting with OMCI. RECORD ET Dept: TIME LOG ELAPSED CODE Work with NSSL service technician on SSAS and NDB. DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. Checks to Cyber chair Purge loss. | 23 | WHITE | 2023-03-02 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
375 | 375 | UCnoavebrle t htoe imdeundt idfye gaansys leera kcso vaenrd a cfthear iMr wOaDsU s tianrsepde cwtiiothn p. Purrgeep asryes tteom re imn obvyep athses .rotary cover for inspection. Carry out daily checks on Calhl reucnknsi nagn de qreupipamirse ntot. M Haoinu sRei gk eHePpUin.g in engine room and machinery space, BOP setback, mud pump room, sack store and main Adettcekn.d Ceodn ctlionsuee otou tW moerke tainngd wsuithp pOoMrt CHIV.AC third party team to repairing HVAC units. Monitor the operation of the newly changed out 2 Emluedct cDoenpdti:tion motor at shaker area(top motor). Continue 180 days PM on jacking brakes. Closed out completed drilling PM on JDE. R Checked and troubleshooting on mud conditioner not working and job keep continue. U Support team to power up on fixation units and function tested. O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 Night Tour Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
376 | 376 | Drilling: Carry out Diverter function tests with MODU. Function all valves. Continue function test tomorrow. Assist Mech dept work on Koomey unit. Assist Mech dept trouble shoot and repair HawkJaw lift ram cylinder issue. Prepare to remove Drill floor rotary for inspection and hose measuring for replacement. Mech Dept: Mechanic and motor man daily check. Top koomey fluid. Continue assist for changed out sewage pipeline. 4000 hrs.PM for compressor #3. Continue close punch list for koomey unit. Clean all air compressor’s air filter. Function test for emergency engine. House keeping in engine room. Today hrs Total hrs M/E#1 24 45897 M/E#20 44326 M/E#30 47440 M/E#40 45041 M/E#50 44965 E-Gen 0 1725 ET Dept: Work with NSSL service technician on SSAS and NDB. Checks to Cyber chair Purge loss. Unable to identify any leaks and chair was stared with purge system in bypass. Checks and repairs to Main Rig HPU. Attended close out meeting with OMCI. ET Dept: Work with NSSL service technician on SSAS and NDB. Checks to Cyber chair Purge loss. Unable to identify any leaks and chair was stared with purge system in bypass. Checks and repairs to Main Rig HPU. Attended close out meeting with OMCI. Elect Dept: Checked and troubleshooting on mud conditioner not working and job keep continue. Support team to power up on fixation units and function tested. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 90 Date: 02-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
377 | 377 | PJSM with crew prior to skid transverse center line. | 23 | WHITE | 2023-03-02 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.75 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.75 12.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 30 Date: 02-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
378 | 378 | Continue shoveling and clearing hip of cuttings on the deck. Meanwhile continue circulating and reciprocating pipe at 7514ft with 500gpm, 1792psi, 60rpm, 14-15k torque. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 380hrs (70HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 19:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 17.7 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 5,512 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 76 DP 5.00 7,500.04 TOTAL HRS 83.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE caco3 6 Drum of RM63 0.5 T HOURS WITHOUT D.P. SNG. D.P. 5.00 31.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 5.00 TOTAL 8,319.94 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 18 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 445 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 380hrs (70HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, #5 for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 19 Date: 02-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 6 | MENTOR | WEST AFRICA
379 | 379 | Pump 100 bbls 200 ppb LCM pill #4 and spot same. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE xc polymr 48 Flotrol 30 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION marble fine 1 barite 100 HOURS STANDBY KELLY DOWN marble medium 2 caustic soda 16 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 44 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 2.00 TOTAL MUD COST ($) 7,196.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 47 Date: 02-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
380 | 380 | POH WITH HALLIBURTON 9-5/8" MST ON 4' DP TO 3400'. -MONITOR WELL THRU TRIP TANK WELL STATIC. | 6 | WHITE | 2023-03-02 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
381 | 381 | Rigged up 700 ton shackle on the traveling block and secured okay. Dressed up rams packing element 5 1/2" to 2 7/8" VBR to rams block. | 23 | WHITE | 2023-03-02 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
382 | 382 | Held PJSM prior to P/U and install TDS on traveling block. 1 Position traveling block at workable height above rotary table. R Pick up TDS from cantilever and position on rotary table. U Engage 700 ton shackle on traveling block to TDS. O T Pick TDS to workable height and disconnect rollers from TDS to enable TDS slide into dolly track beam. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
383 | 383 | Pick TDS, remove all restrictions from traveling path and position TDS on traveling beam as required. ok. Commence installation of rollers on the TDS. Carry out house keeping on the Rig floor as required. 2 | 23 | WHITE | 2023-03-02 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
384 | 384 | Install all bottom dolly rollers on the TDS. R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 40 Date: 02-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
385 | 385 | WAITING ON LOGISTICS TO DELIVER 12-1/4” DD TOOLS F/DS FOSSIL + NHAVA SINCE 01.03.2023 @ 05:00HRS. (OSV G.S. DIPTI REPORTED & UNDER THE CRANE@ 0454HRS AND DELIVED PREMIX AND 765 BBLS OF 11 PPG SOBM. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | T12 | HELD PJSM ABOUT OFFLOAD SOBM MUD. 17. Plug Back SAVER SUB CONNECTION - 0 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- OFF LOAD SOBM . INSPECTION OF CORRECT LINED UP AND BEFORE COMMENCING THE 22. Surface Testing OFF LOAD,KEEP UP GOOD COMMUNICATION . DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT ASSEMBLING HT-65 TONGS. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 0 NO. OF DAYS TOTAL CONNECTION - 107 6 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- ASSEMBLING HT-65 TONGS. ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 HAZARDS. STAYING CLEAR FROM LINE OF FIRE .CORRECT MANU A LD HRAILNLDELRI:NG. SAFE HAND/BODY IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 6 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT OFFLOAD SOBM MUD. SAVER SUB CONNECTION - 0 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- OFF LOAD SOBM . INSPECTION OF CORRECT LINED UP AND BEFORE COMMENCING THE OFF LOAD,KEEP UP GOOD COMMUNICATION . Operations Activities (Continued...) HELD PJSM ABOUT ASSEMBLING HT-65 TONGS. SAVER SUB CONNECTION - 0 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- ASSEMBLING HT-65 TONGS. ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE .CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 6 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 6 Date: 02-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 12 | TRIDENT XII | INDIA
386 | 386 | WAITING ON LOGISTICS TO DELIVER 12-1/4” DD TOOLS F/DS FOSSIL & NHAVA . 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 6 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | T12 | HELD PJSM ABOUT OFFLOAD SOBM MUD. 17. Plug Back SAVER SUB CONNECTION - 0 18. Squeeze Cement TOTAL CONNECTION - 107 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- OFF LOAD SOBM . INSPECTION OF CORRECT LINED UP AND BEFORE COMMENCING THE 22. Surface Testing OFF LOAD,KEEP UP GOOD COMMUNICATION . DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT ASSEMBLING HT-65 TONGS. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 0 NO. OF DAYS TOTAL CONNECTION - 107 6 FROM SPUD WASH PIPE HRS - 0 CUMULATIVE TOTAL WASH PIPE HRS: - 306.5 ROTATING HOURS DEBRIEF:2- ASSEMBLING HT-65 TONGS. ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 HAZARDS. STAYING CLEAR FROM LINE OF FIRE .CORRECT MANU A LD HRAILNLDELRI:NG. SAFE HAND/BODY IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 6 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT OFFLOAD SOBM MUD. SAVER SUB CONNECTION - 0 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- OFF LOAD SOBM . INSPECTION OF CORRECT LINED UP AND BEFORE COMMENCING THE OFF LOAD,KEEP UP GOOD COMMUNICATION . Operations Activities (Continued...) HELD PJSM ABOUT ASSEMBLING HT-65 TONGS. SAVER SUB CONNECTION - 0 TOTAL CONNECTION - 107 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:2- ASSEMBLING HT-65 TONGS. ARRANGED AND CLEANED AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE .CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 6 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 6 Date: 02-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 12 | TRIDENT XII | INDIA
387 | 387 | CONTINUE CIRC HOLE TILL SHAKER CLEAN WITH 150 RPM , 650 GPM , 3650 PSI | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
388 | 388 | PERFORM SAFETY STAND DOWN MEETING | 23 | WHITE | 2023-03-02 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
389 | 389 | FLOW CHECK AT BOTTOM MONITOR WELL ON TRIP TANK LOSSES RATE 1.6 BPH 1 | 6 | YELLOW | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
390 | 390 | POH FREELY WITH 5" DP ON 8.5" SLB DIRC ASSY FROM 10830 FT TO 7276 FT R | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.75 | HIGH ISLAND IV | MENAM
391 | 391 | Continue RIH with ESP completion string on 3 ½" TBG JT'S From Depth 147 Ft to 1042Ft IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 | B | WHITE | 2023-03-02 | TUBING TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 1.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.00 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 5.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 33 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 4 | RIG 141 | MENAM
392 | 392 | FLOW CHECK AT SHOE MONITOR WELL ON TRIP TANK U | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
393 | 393 | RIH WITH 5' DP FROM 7276' TO 10830' FILL UP STRING EVERY 15 STAND | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2 | HIGH ISLAND IV | MENAM
394 | 394 | PUMP SWEEP AND CIRC HOLE CLEAN WITH 650 GPM , 100 RPM , 3600 PSI , | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 3 | HIGH ISLAND IV | MENAM
395 | 395 | FLOW CHECK 2 BPH LOSSES RATE | 6 | YELLOW | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
396 | 396 | SPOT 250 BBLS GREASE PIL | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
397 | 397 | POH FREELY WITH 5' DP FROM 10830' TO 9079 FT DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
398 | 398 | POOH ( OPEN HOLE) WITH 8 1/2'' RSS ASSEMBLY ON 5'' DRILL PIPE FROM 9079 FT TO 7227 FT. | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1.5 | HIGH ISLAND IV | MENAM
399 | 399 | FLOW CHECK. WELL STATIC. MEAN WHILE HELD SAFETY STAND DOWN MEETING. | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
400 | 400 | POOH WITH 8 1/2'' RSS ASSEMBLY ON 5'' DRILL PIPE FROM 7227 FT TO 657 FT. 2 | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.75 | HIGH ISLAND IV | MENAM
401 | 401 | FLOW CHECK AT BHA WELL STATIC R | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
402 | 402 | POOH WITH 8.5" RSS ASSY ON 5" HWDP F/657 T/110 U | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
403 | 403 | HPJSM FOR RA SOURCE REMOVAL & L/D BHA O T | 23 | WHITE | 2023-03-02 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
404 | 404 | REMOVE RA SOURCE, L/D 8 1/2" RSS ASSY. | 6 | WHITE | 2023-03-02 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 3.25 | HIGH ISLAND IV | MENAM
405 | 405 | CLEAR & CLEAN RIG FLOOR. | 23 | WHITE | 2023-03-02 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
406 | 406 | SERVICE TOP DRIVE O T | 7 | WHITE | 2023-03-02 | LUBRICATE RIG | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
407 | 407 | Test cement surface line with test assembly. 500/4000 PSI 5/10 mints, hold OK. perform integrity test on SSD W/3500 PSI for 15 mints hold OK. L/D test assembly, R/U slick line upper & lower sheaves, RIH W/ pulling tool, retrieve prong then PX plug from SSD. | 22 | WHITE | 2023-03-02 | SURFACE TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 1.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.00 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 5.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 33 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1.5 | RIG 141 | MENAM
408 | 408 | Continue RIH with ESP completion string on 3 ½" TBG JT'S T/ 147' ORKB as follows: - 2 X 3 ½" 9.2 PPF, EUE TBG JT'S (COND A), 3-1/2'' EUE,L-80,2.81'' XD SSD, 1 X 3 ½" 9.2 PPF, EUE TBG JT'S (Cond A) - pass with y tool across wellhead area with caution. - prepare CMT test lines for SSD pressure test. -set PX plug in SSD and set prong at surface | B | WHITE | 2023-03-02 | TUBING TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 1.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.00 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 5.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 33 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1 | RIG 141 | MENAM
409 | 409 | Continue PU & MU with ESP-Y tool string with 2 7/8" bypass TBG as follows: ESP string assembly: EA guardian motor upper seal, 538 SER, BPBSL, HL, SS GAS separator 9000ht, single (SS) (series:538) Pump 538 SER, 538-5000, 80 HSG, 49 STG, CP-TA-HSS-SS Pump 538 SER, 538-5000, 70 HSG, 43 STG, CP-TA-HSS-SS Discharge head, 3-1/2" EUE box (series:538) discharge sub, 3-1/2" EUE (series:538) - 3 -1/2'' EUE,9.3#, L-80,10FT pump sub - 9 5/8'' X 3 1/2''Acme third ,53.5#, Y-TOOL - 3 1/2'' EUE BOX,6FT handling sub - ensure good cover around rotary table all time while P/U & M/U ESP ASSY. - KEEP 3 ½’’ EUE X 4 ½’’ IF safety X-OVER M/U with TIW ready for stab in. - M/U TQ 3 1/2" EUE JT:2,500 LB.FT. - Connect steel bands on control line as following (2 on upper seal, 1 on gas separator, 3 on lower pump SEC, 3 on upper pump sec, 1 on discharge sub, 4 below Y-tool). - install 3 EA universal clamp (total 4 clamps). - take reading after M/U upper pump (PH-PH = 6.9 balance PH-ground = 2200). - intake pressure (PI) 14.98 PSI, discharge pressure (PD) 15.63 PSI, intake temp (TI) 24 DEG C, motor temp (TM): 25 DEG C. - fill annulus with 9.7 PPG brine 10 BBL every 1 hour - total BBL'S pumped in annulus since losses started: 387 BBL. | E | WHITE | 2023-03-02 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 1.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.00 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 5.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 33 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 5.5 | RIG 141 | MENAM
410 | 410 | RIH 3 1/2" cement stinger on 5" drill pipe from 1055m to 1430m. Trip restricted RIH 13 stands within 45mins =1892 ft/hr . While monitored well on trip tank, confirmed string metal displacement. | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
411 | 411 | Carried out derrick management, moved 7 stands of 5'' HWDP + jar racked at front of HT55 drill pipes and re-racked in BHA fingers. 1 | 23 | WHITE | 2023-03-02 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.25 | BALTIC | WEST AFRICA
412 | 412 | R/D 5'' DP elevator from TDS baill and R/U 5 1/2'' DP elevator. R | 23 | WHITE | 2023-03-02 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
413 | 413 | P/U 5 1/2'' DP form derrick, M/U with XO 4 1/2'' IF pin X HT55 box. U | 23 | WHITE | 2023-03-02 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
414 | 414 | RIH 5 1/2'' DP on 5'' DP and 3 1/2'' cement stinger from 1430m to 1575mm. Trip restricted 1904 ft/hr (5 stands) of 5 1/2'' DP. While O T monitoring well on T/T and check T/T for correct displacement. | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
415 | 415 | Break circulation in stages, 300lpm Pressure,177 psi. 400lpm, pressure 197 psi. 500 lpm, pressure 225 psi. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
416 | 416 | RIH 5 1/2'' DP on 5'' DP / 3 1/2'' stinger from 1575m to 1872m. Trip restricted 1883 ft/hr (10 stands) of 5 1/2'' DP. While monitoring well on T/T and check T/T for correct displacement. | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
417 | 417 | M/U TDS, RIH slowly to 1880 above shoe, stage up pump slowly to 1800 lpm and circulate 1x cycle while reciprocating slowly( No rotation). Note: Run degasser during circulation. Stop circulation and take SCR mud pump. Mud pump 2. 20spm=200 psi 30 spm=260 psi 40 spm=350 psi. Mud pump 3 20 spm=170 spi 30 spm=260 psi 40 spm=350 psi | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
418 | 418 | Continue washing down with 500 lpm at 3 mins/std, 263 psi from 1880m to 2436m btm and tagged same with 5 kips set down weight. 1D0E:P3T0H IN1TE2R:0V0AL D1.R5I0LL 5 Stage up pumFpO aRnMdA cTirIOcuNlate 1 x bottoms uRpO wTAitRh Y180W0 Tlp.m, 1698 psi wPhUileM PreciprocatPinUgM sPtring. PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 3.25 | BALTIC | WEST AFRICA
419 | 419 | Circulate 1 x bottoms up with 1800 lpm, 1698 psi while reciprocating string | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
420 | 420 | PU 1m off bottom. Pumped 10m3 of 1.80sg viscous pill at 1200lpm, 648 psi while reciprocating string. Chase same with19.36m3 of 1.50 RDF from pit #4 and spot pill at bottom. 2 | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
421 | 421 | Flow check well on trip tank, well static. R | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
422 | 422 | Lay down pump joint and 2 x 5 1/2'' dp. POOH 5 1/2'' dp on elevator slowly from 2436m to 2300m. U | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
423 | 423 | MU TDS and circulate hole at 1000 lpm, 574 psi. O T | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
424 | 424 | Spaced out with mule shoe and SES Assy mule shoe at 2300m. MU SES assy onto string, connect TDS. Flush cement line from cement unit to rig floor with water. Connect line to Lo - Torque at SES. | 23 | WHITE | 2023-03-02 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
425 | 425 | Pressure test lines against closed Lo- Torque valve at SES 300/3000psi for 5/5mins ok. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
426 | 426 | Pumped 47.8 bbls of 1.65sg spacer with rig pump 400psi, 790 lpm. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
427 | 427 | Halliburton Cementer MIX and pumped 1.90sg tail slurry 60.3 bbls with 359 psi, at 5bpm. Rig pumped 1.65 sg spacer 28 .17 bbls with 400psi, 790 lpm. Cement unit pumped 68 bbls of 1.50 RDF. | 12 | WHITE | 2023-03-02 | RUN CASING & CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
428 | 428 | Break out SES assy and lay down same. | 23 | WHITE | 2023-03-02 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
429 | 429 | POOH slowly 5 1/2'' dp on elevator from 2300m to 2000m. | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.25 | BALTIC | WEST AFRICA
430 | 430 | Drop 7'' foam ball and circulate 2 x bottoms up with 1800 lpm, 1657 psi. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.25 | BALTIC | WEST AFRICA
431 | 431 | Break out TDS, POOH cement stinger on 5 1/2" drill pipe wet from 2000m to 1429m,monitored well on trip tank. | 6 | WHITE | 2023-03-02 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2 | BALTIC | WEST AFRICA
432 | 432 | P/U 3 single x 5 1/2'' DP L/D to V-door and rack back same on the derrick. | 23 | WHITE | 2023-03-02 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
433 | 433 | held PJSM and reviewed TBRA with all involved in P/U 5 1/2'' drill pipe 5'' dp / 3 1/2'' cement stinger, RIH to shoe and rack back. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
434 | 434 | Stage up pump and circulate 1 x bottoms up with 1800 lpm, 1698 psi while reciprocating string. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 1.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 49 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 49 Date: 02-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.5 | BALTIC | WEST AFRICA
435 | 435 | HPJSM, MU & RIH HALLIBURTON 9-5/8" RTTS PKR W/ STORM VALVE. SET RTTS PKR AT 180 FT. TEST RTTS PKR TO 1000 PSI. POH & LD RUNNING TOOL. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1.5 | HIGH ISLAND V | MENAM
436 | 436 | H.P.J.S.M Continue RIH with ESP completion string on 3 ½" TBG Joints From Depth 1042 Ft to 3933 Ft Fill up Hole Every one Hour 10 BBL - 9.7 PPG Brain Water . Total Pumping @ last @4 Hour 260 BBL . 2 Drift size 2 13/16 “ R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | B | WHITE | 2023-03-02 | TUBING TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 1.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.00 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 5.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 33 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 12 | RIG 141 | MENAM
437 | 437 | HPJSM PRIOR RETRIEVING WEAR BUSHING | 23 | WHITE | 2023-03-02 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
438 | 438 | M/U WEAR BUSHING RETRIEVING TOOL | 23 | WHITE | 2023-03-02 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
439 | 439 | Continue PU & MU with ESP-Y tool string with 2 7/8" bypass TBG as follows: ESP string assembly: EA guardian motor upper seal, 538 SER, BPBSL, HL, SS 1 GAS separator 9000ht, single (SS) (series:538) R Pump 538 SER, 538-5000, 80 HSG, 49 STG, CP-TA-HSS-SS U Pump 538 SER, 538-5000, 70 HSG, 43 STG, CP-TA-HSS-SS O T Discharge head, 3-1/2" EUE box (series:538) discharge sub, 3-1/2" EUE (series:538) - 3 -1/2'' EUE,9.3#, L-80,10FT pump sub - 9 5/8'' X 3 1/2''Acme third ,53.5#, Y-TOOL - 3 1/2'' EUE BOX,6FT handling sub - ensure good cover around rotary table all time while P/U & M/U ESP ASSY. - KEEP 3 ½’’ EUE X 4 ½’’ IF safety X-OVER M/U with TIW ready for stab in. - M/U TQ 3 1/2" EUE JT:2,500 LB.FT. - Connect steel bands on control line as following (2 on upper seal, 1 on gas separator, 3 on lower pump SEC, 3 on upper pump sec, 1 on discharge sub, 4 below Y-tool). - install 3 EA universal clamp (total 4 clamps). - take reading after M/U upper pump (PH-PH = 6.9 balance PH-ground = 2200). - intake pressure (PI) 14.98 PSI, discharge pressure (PD) 15.63 PSI, intake temp (TI) 24 DEG C, motor temp (TM): 25 DEG C. - fill annulus with 9.7 PPG brine 10 BBL every 1 hour DEPTH INTERVAL DRILL - total BBL'S pFuOmRpMeAdT iInO Nannulus since lossReOsT sAtRarYted:W 3T8.7 BBL. PUMP PUMP PUMP PUMP TOTAL CORE PUMP 0F5R:O30M 06:T3O0 R1C.EO0AR0ME NBO. Continu(eS HROIHW wCiOthR EE SRPEC cOoVmEpRleYt)ion string oSTnAP 3EB E½LDE" TBGBOI NTJT'SP RTE/ S1S47' LOSINIRZEKERB aSsP fMolloLwSINsIZ:EER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT - 2 X 3 ½" 9.2 PPF, EUE TBG JT'S (COND A), 3-1/2'' EUE,L-80,2.81'' XD SSD, 1 X 3 ½" 9.2 PPF, EUE TBG JT'S (Cond A) - pass with y tool across wellhead area with caution. - prepare CMT test lines for SSD pressure test. -set PX plug in SSD and set prong at surface HORIZ HORIZ HORIZ 06:30 08:0D0EPTH1.50DEV. 22 DITRe.st cemeTnVt DsurfaceD lIiSnPe. withD teEsPtT aHssemDbElyV. .500/400D0I RP.SI 5/10 TmViDnts, hoDldI SOPK.. DEPTH DEV. DIR. TVD DISP. DEVIATION perform integrity test on SSD W/3500 PSI for 15 mints hold OK. RECORD L/D test assembly, R/U slick line upper & lower sheaves, RIH W/ pulling tool, retrieve prong then PX plug from SSD. 08T:0IM0E LO12G:00 ELA4P.0S0ED COBDE Continue RIH with ESP completion string on 3 ½" TBG JT'S From Depth 147 Ft to 1042Ft DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-02 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 1.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.00 12.00 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 5.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 33 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 33 Date: 02-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 5.5 | RIG 141 | MENAM
440 | 440 | Held PJSM, Spot 180 bbls lubra-glide in open hole, Flow check well static. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 | E | WHITE | 2023-03-02 | TESTING | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
441 | 441 | CONTINUE WAITING ON LOGISTICS TO DELIVER 200 MT DRILL WATER FOR CTC JOB . 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 12 | J T ANGEL | INDIA
442 | 442 | HELD PJSM,M/A AND PREPARED 800 BBL 8.6 PPG FILTERED BRINE + 50 BBL CTC PILL-1 (HSD+ 5% SODA ASH + 5% GLYCOL). | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 3 | J T ANGEL | INDIA
443 | 443 | PUMPED 50BBL CTC PILL AS PER PROCEDURE W/600GPM 1230 PSI AND CIRC OUT CTC PILL-1. 2 | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
444 | 444 | M/A AND PREPARING 500 BBL 8.6 PPG FILTERED BRINE + 50BBL CTC PILL-2. R | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 3 | J T ANGEL | INDIA
445 | 445 | PUMPED 50BBL CTC PILL AS PER PROCEDURE W/600GPM 1230 PSI AND CIRC OUT CTC PILL -2. U | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
446 | 446 | DROPPED BALL. R/UP CMT LINE TO 4.5” CTC STRING & TESTED @ 4500PSI-OK. CHASED BALL & TESTED CTC STRING IN O T STAGES UP TO 4200 PSI-OK. & BREAK & L/DN TEST ASSY. | E | WHITE | 2023-03-02 | TESTING |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 2 | J T ANGEL | INDIA
447 | 447 | R/UP WEATHERFORD 4-1/2" TBG HANDLING EQUIPMENT. | B | WHITE | 2023-03-02 | TUBING TRIPS |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
448 | 448 | FLOW CHECK -OK. POOH 4-1/2" BGT,L-80 13-CR 12.6 PPF TUBING F/2558M TO2328M FURTHER POOH IS IN PROGRESS (WET POOH). IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | B | WHITE | 2023-03-02 | TUBING TRIPS |  | HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 1.50 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing 2.00 M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE sada ash 4 poly oil 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION fUEL 100 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 71 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING. SERVES MUD PUMP TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING PUMPING CTC PILL # 1. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 71 Date: 02-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
449 | 449 | RIH WITH HALLIBURTON CMT STINGER WHILE P/U 4" DP FROM DECK & TAGGED 9-5/8" EZSV-CR @ 5370'. -P/U & M/U 4" DP FROM PIPE DECK, (TOTAL 153 JTS). 1 -MONITOR WELL THRU TRIP TANK, WELL STATIC R | 6 | WHITE | 2023-03-02 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
450 | 450 | ACCUMULATED TIME FOR BREAK CIRC. EVERY 1500 FT, CIRCULATE ON TOP OF EZSV-CR WITH HIGH RATE U | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
451 | 451 | HPJSM.STING OUT OF EZSV-CR.SPACE OUT,M/U CMT HEAD AND CONNECT CEMENT LINE,PT CEMENT LINES FROM CEMENT UNIT 300/4000PSI | 18 | WHITE | 2023-03-02 | SQUEEZE CEMENT | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
452 | 452 | SPOT 30 BBL 95 PCF ARAMCO SPACER ON TOP EZSV-CR | 18 | WHITE | 2023-03-02 | SQUEEZE CEMENT | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
453 | 453 | BAKER PERFORMED SQZ CMT P&A EXISTING MOTHERBORE AS FOLLOWS: -PUMPED 20 BBLS OF VISCUS WATER AHEAD. -BATCH MIXED & PUMPED 90 BBLS OF 118 PCF CMT SLURRY 469 SACKS WI ADDITIVES (0.01GPS FP-12L , 0.4 BWOC FL-52, 0.3 BOWC CD-32, 0.03 GPS R-21LS) AS PER LAB RECIPE. -PUMP 20 BBL 95 PCF SPACER BEHIND. -DISPLACE 33 WITH 70 PCF BRINE OBSERVED PRESSURE REACH 1300 PSI LAST 10 BBL WITH 0.5 BPM (TOTAL CMT SLURRY SQUEEZED BELOW EZSV-CR = 80 BBLS). | 18 | WHITE | 2023-03-02 | SQUEEZE CEMENT | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
454 | 454 | STING OUT CLOSE BOP RVERSE CIRCULATE 2 STRING VOLUME, OPEN BOP AND NORMAL CIRCULATION W/ 10 BPM @ 1200 PSI-DROP ONE FOAM BALL AND CIRCULATE AT HIGH RATE WHILE RECIPROCATE STRING UP AND DOWN. DEPTH INTERVAL DRILL -PT EZSV-CRF TOORM 1A0T0I0O NPSI OK. ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP 0F9R:O30M 10:T0O0 R0C.EO5AR0ME N1O8. L/D CEM(SEHONWT SCUORREF ARCECEO LVIENREYS), PUMP INST SAPUEBEBLDE & TIWBOINT VALPVREESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2.5 | HIGH ISLAND V | MENAM
455 | 455 | POH WITH HALLIBURTON 9-5/8" MST ON 4' DP TO 3400'. -MONITOR WELL THRU TRIP TANK WELL STATIC. | 6 | WHITE | 2023-03-02 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
456 | 456 | HPJSM, MU & RIH HALLIBURTON 9-5/8" RTTS PKR W/ STORM VALVE. SET RTTS PKR AT 180 FT. TEST RTTS PKR TO 1000 PSI. POH & LD RUNNING TOOL. HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1.5 | HIGH ISLAND V | MENAM
457 | 457 | HPJSM, N/D BELL NIPPLE & FLOW LINE. | 14 | WHITE | 2023-03-02 | N/UP BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1.5 | HIGH ISLAND V | MENAM
458 | 458 | HPJSM, N/D BOPS & RELATED EQUIPMENT FOR WELLHEAD WORK | 14 | WHITE | 2023-03-02 | N/UP BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2.5 | HIGH ISLAND V | MENAM
459 | 459 | N/D DRILLING RISER 2 | 14 | WHITE | 2023-03-02 | N/UP BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
460 | 460 | N/D OLD CIW TUBING SPOOL OLD GRAY CSG HEAD SPOOL, CLEAN & INSPECT 9-5/8" CSG STUB. R -NO 9-5/8" CSG INSIDE 13-5/8" X 13-5/8" CASING HEAD SPOOL. U -13-5/8" X 13-3/8" LANDING BASE IN GOOD CONDITION O T | 23 | WHITE | 2023-03-02 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 3 | HIGH ISLAND V | MENAM
461 | 461 | HPJSM, WELD & RESTUB 9-5/8" CASING. INSTALL OLD GRAY 13-5/8" X 13-5/8" CASING SPOOL. -PT SEALS TO 1000 PSI GOOD TEST. | 23 | WHITE | 2023-03-02 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2.5 | HIGH ISLAND V | MENAM
462 | 462 | INSTALL GE 13-5/8" X 13-5/8" X 9-5/8" DSDPOF. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-02 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1.5 | HIGH ISLAND V | MENAM
463 | 463 | STING OUT CLOSE BOP RVERSE CIRCULATE 2 STRING VOLUME, OPEN BOP AND NORMAL CIRCULATION W/ 10 BPM @ 1200 PSI-DROP ONE FOAM BALL AND CIRCULATE AT HIGH RATE WHILE RECIPROCATE STRING UP AND DOWN. -PT EZSV-CR TO 1000 PSI OK. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2.5 | HIGH ISLAND V | MENAM
464 | 464 | L/D CEMENT SURFACE LINES, PUMP IN SUB & TIW VALVE | 18 | WHITE | 2023-03-02 | SQUEEZE CEMENT | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
465 | 465 | RIH RETRIEVE TOOL TO TUBING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | 23 | WHITE | 2023-03-02 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA TRIPPING PIPE 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 2.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:00 18:00 23:59 I SIZE 8.50 WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. SEC VISCOSITY 49 49 49 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. 61751 GELS / / / C G. Other 5 JETS 6x12 FL. LOSS H. Other 6 TFA 0.663 pH TOTALS 12.00 12.00 DEPTH OUT 10,830 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 7,279 2 (OFFICE USE ONLY) TOTAL DRILL 3,551 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 67 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 WT A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X NO TD REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 35 FROM SPUD CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 35 Date: 02-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
466 | 466 | Held PJSM, Circulate hole clean with 330gpm, 3400psi till shakers clean. Flow check well static. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
467 | 467 | Held PJSM, Rih w/ 6 1/8" Reaming assy on 4" Drill pipe @ controlled speed F/ 6715 ft to11377ft TD freely. Precautionary wash down last stand, Fill & break circulation every 20 stds. Monitor well on Trip tank, Well static. | 6 | WHITE | 2023-03-02 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.5 | HIGH ISLAND IX | MENAM
468 | 468 | STING IN 9 5/8" EZSV-CR.PT BACKSIDE TO 1000PSI/10MIN,PERFORMED INJECTIVITY TEST WITH 5 BPM-1000PSI O T | 18 | WHITE | 2023-03-02 | SQUEEZE CEMENT | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement 4.50 PRE JOB SAFETY METING. P/U 4'' D/P 19. Fishing PRE JOB SAFETY METING. R.I.H W/D 5'' D/P 20. Directional Work PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. MAN RIDING OPERATIONS 22. Surface Testing PRE JOB SAFETY METING. CEMENT JOB DRILLER: 23. Other 3 1.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 1 STINGE 5.00 4.95 SIZE WEIGHT 9.34 T C. Treating E 2 XO 6.50 2.65 IADC CODE GRADIENT 0.4847 PL DE.. TSewsatibnbging 3 DP 4.00 3,490.60 MANUFACT. VISCOSITY 40 M 4 RTTS 9.63 4.50 TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 37 STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,502.70 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 48,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. SET RTTS PACKER 19 FROM SPUD PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK CUMULATIVE PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD ROTATING HOURS PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. P/U 4'' D/P PRE JOB SAFETY METING. R.I.H W/D 5'' D/P PRE JOB SAFETY METING. PRESSURE TEST T.S.A AND S.S.A PRE JOB SAFETY METING. MAN RIDING OPERATIONS PRE JOB SAFETY METING. CEMENT JOB PRE JOB SAFETY METING. POOH WIT 5'' D/P AND 4'' D/P Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. SET RTTS PACKER PRE JOB SAFETY METING. NIPPLE DOWN BOP STACK PRE JOB SAFETY METING. NIPPLE DOWN WELLHEAD PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 19 Date: 02-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
469 | 469 | Held PJSM, Circulate hole clean with 330gpm, 3400psi, Flow check well static. R | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
470 | 470 | Held PJSM, POOH in open hole w/ 6 1/8" Reaming assy on 4" Drill pipe F/ 7845 ft to TOW @6715 ft. Monitor well thru trip tank hole U static. O T | 6 | WHITE | 2023-03-02 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
471 | 471 | Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation permits. 1 | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At 2:00 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 19. Fishing all tasks. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME I SIZE 3.75 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 4.50 M TYPE DSR6085 PV/YP O F. Other 4 SERIAL NO. 1A/ S295592 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 5.00 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 24 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 42 Date: 02-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.5 | MAIN PASS I | MENAM
472 | 472 | Close TRSSSV Secured BRRI 35 production tree R | E | WHITE | 2023-03-02 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At 2:00 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 19. Fishing all tasks. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME I SIZE 3.75 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 4.50 M TYPE DSR6085 PV/YP O F. Other 4 SERIAL NO. 1A/ S295592 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 5.00 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 24 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 42 Date: 02-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 0.5 | MAIN PASS I | MENAM
473 | 473 | Nipple Down E-Kill from TBG Spool secured BRRI-35. TBG spool valve. U ** End of reporting on BRRI-35 At 5:00 2nd March 2023 O T ** Next well BRRI 37 DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 42 Date: 02-Mar-23 | E | WHITE | 2023-03-02 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At 2:00 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 19. Fishing all tasks. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME I SIZE 3.75 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 4.50 M TYPE DSR6085 PV/YP O F. Other 4 SERIAL NO. 1A/ S295592 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 5.00 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 24 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 42 Date: 02-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 2 | MAIN PASS I | MENAM
474 | 474 | Held Pre Job safety meeting for preparation for skidding operations. | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
475 | 475 | Re Arrange cantilever deck prepare hoses and hand rails for skidding operations. | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 5 | MAIN PASS I | MENAM
476 | 476 | Held PJSM for skidding operations. 1 | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
477 | 477 | Transverse to center line Skid rig to BRRI 37. Secure walk ways and handrail. R | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1 | MAIN PASS I | MENAM
478 | 478 | R/Up Emerg/ Kill on BRRI 37. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-02 | RIG UP & TEAR DOWN | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
479 | 479 | PJSM, Nipple up E - Kill Line on THS side outlet valve. Build scaffolding around X - Mass tree. N/U New 4-1/16" Gate Valve on top Prod tree. | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2.25 | MAIN PASS I | MENAM
480 | 480 | Remove flow line spool. Installed blind flange on X- Mass Tree wing valve. 2 | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.75 | MAIN PASS I | MENAM
481 | 481 | Slick Line RIH and retrieve ME plug at 200ft POOH. RIH and retrieve ME plug at 5442ft POOH. R/Down Slick Line | E | WHITE | 2023-03-02 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At 2:00 hrs Held safety stand down Discussed. Use the Safety Analysis Process to Plan Risk Assess and Monitor 19. Fishing all tasks. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME I SIZE 3.75 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 4.50 M TYPE DSR6085 PV/YP O F. Other 4 SERIAL NO. 1A/ S295592 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 5.00 0.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 6,971 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 24 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 161.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-35 Rpt No: 42 Date: 02-Mar-23 | BRRI-35 | BRRI-35 | Mar-23 | 2 | MAIN PASS I | MENAM
482 | 482 | PJSM, Rig up Expro slick line risers, bop & lubricator, surface lines, pressure test 300/2000 psi,10mins. Good test. Pressure test E- U Kill line against existing THS valve to 300/1000psi,10 mins. O T | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 3 | MAIN PASS I | MENAM
483 | 483 | Held Safety Stand Down Meeting, Discussed: SWA, PJSM, tbra Different types of Energy isolation permits., R | 23 | WHITE | 2023-03-02 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
484 | 484 | Pressure test TCA to 1000 psi, 10/mins Good test. | 22 | WHITE | 2023-03-02 | SURFACE TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
485 | 485 | Held PJSM, POOH in open hole w/ 6 1/8" Reaming assy on 4" Drill pipe F/ 11377 ft to 7845 ft (1000 ft below window ). Monitor well thru trip tank, hole static. 2 | 6 | WHITE | 2023-03-02 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.5 | HIGH ISLAND IX | MENAM
486 | 486 | Held PJSM, Circulate hole clean with 330gpm, 3400psi, Flow check well static. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
487 | 487 | Held PJSM. Pump 2 X 20 bbls Hi-Vis sweep and circulate hole clean with 330gpm, 3400psi. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 2 PUMP NO 3 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 11377 11377 Drill 3400 5.500 45 5.500 45 323.01 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
488 | 488 | Held PJSM, Rih w/ 6 1/8" Reaming assy on 4" Drill pipe @ controlled speed f/ 6771 ft to11377 feet TD freely. Precautionary wash down last stand.Fill & break circulation every 20 stds. Monitor well on Trip tank. | 6 | WHITE | 2023-03-02 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 3 | HIGH ISLAND IX | MENAM
489 | 489 | Held PJSM, M/up 6 1/8" Stiff Reaming assy, 6 1/8" Welded Cone Bit, (S/N Z209YT), 6 1/8" NB Roller Reamer w/ Float, 1 x 4 3/4" DC, R 6 1/8" String Roller Reamer, 2 x 4 3/4" DC's, 6 1/8" DL Reamer, X/over, 9 joints of 4” HWDP, 4 ¾” jar, 30 joints of 4” HWDP and RIH to U 1334 ft. Monitor well on Trip tank, Well static. O T | 6 | WHITE | 2023-03-02 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
490 | 490 | Held PJSM. Clean and Clear Rig floor, Service TDS. and check for DROPS. 1 | 7 | WHITE | 2023-03-02 | LUBRICATE RIG | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
491 | 491 | Held PJSM, Rih w/ 6 1/8" Reaming assy on 4" Drill pipe F/ 1334 ft to 7" Window @ 6771ft, fill & break circulation every 20 stds. Monitor well on Trip tank, Well static. | 6 | WHITE | 2023-03-02 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.5 | HIGH ISLAND IX | MENAM
492 | 492 | Held PJSM, Pooh and L/down RSS / LWD/ MWD drilling BHA and 6 1/8" bit SLB Retrieve Radio active source, Monitor the well on trip tank. Well static. Bit grading 1-1-WT-A-X-I-No-TD | 6 | WHITE | 2023-03-02 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 236 Hrs. 20. Directional Work SWL PKG---CIRC = 328.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#2 and #3 with 45 spm, 3400 psi for 2 hours. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 BIT 6.13 0.64 SIZE WEIGHT 10.16 T C. Treating E 1 RR 6.13 5.20 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 DC 4.75 30.70 MANUFACT. VISCOSITY 65 M 1 RR 6.13 4.97 TYPE PV/YP / O F. Other 4 2 DC 4.75 61.37 SERIAL NO. GELS / C G. Other 5 1 RR 6.13 5.19 JETS FL. LOSS H. Other 6 1 XO 4.75 2.53 TFA pH TOTALS 12.00 12.00 9 HWDP 4.00 276.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 26.85 DEPTH IN 2 (OFFICE USE ONLY) 30 HWDP 4.00 921.16 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 4.00 9,997.16 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 4.00 31.40 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 11,363.50 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 110,000 REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 52 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#2 and #3 with 45 spm, 3400 psi for 4 hours. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 69 Date: 02-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
493 | 493 | Expro S-line perform the following: RIH with 3.833"" drift tag TRSSSV at 280ft. POOH. RIH With 2.833" drift to top of X- Nipple at 6199ft. POOH. RIH 2.75" drift to top of MFIV shifting toll at 6236ft'. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | E | WHITE | 2023-03-02 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2 | MAIN PASS I | MENAM
494 | 494 | bullhead tbg with 200 bbls 76 pcf brine, with 3.9bbl/min 800psi to 100psi. flow check well static. | 5 | WHITE | 2023-03-02 | CONDITION MUD & CIRCULATE | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.5 | MAIN PASS I | MENAM
495 | 495 | Apply 300psi againsr TRSSSV Open TRSSSV Open well Record SIWHP 820psi. | E | WHITE | 2023-03-02 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At01:00to 1:30 Held safety stand down. Discussed SWA., PJSM, TBRA, & Different types of energy isolation 19. Fishing permits. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 5.50 7.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 2.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 7.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 5 lime 2 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION xblmar 5 HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 1600 to 16:30:00 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE 0 FROM SPUD Alert, personal injury proper PPE, Housekeeping & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 70.00 TOTAL MUD COST ($) 70.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 1 Date: 02-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
496 | 496 | Flow check, well static. pooh 8-1/2” assy F/1200 m to 152m. R | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
497 | 497 | Cont Pooh bha F/152 to surface lay down jar, bit sub, bit. U | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
498 | 498 | Wash down f/970 m to 1200 m & tagged cmt top with 8 mt. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
499 | 499 | Cont make up & rih 8 ½” bit assy to 970m. | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 3 | PARAMESHWARA | INDIA
500 | 500 | p/up m/up 8 ½” bit assy iip. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
501 | 501 | Circ bottoms up @ 550 gpm/350 psi.test cmt plug @1000 psi in stages-ok. 2 | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
502 | 502 | pooh pooh mule shoe w/5 ½” dp f/911 m to surf.( l/dn x/over & mule shoe). | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
503 | 503 | m/up test assy& close bop. squeeze 22 bbls @ 960 psi got 5 bbl return. total squeeze-17 bbls. | 18 | WHITE | 2023-03-03 | SQUEEZE CEMENT | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
504 | 504 | bop closed, well kept under squeezed press @1500 psi. O T | 18 | WHITE | 2023-03-03 | SQUEEZE CEMENT | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 3 | PARAMESHWARA | INDIA
505 | 505 | closed the well under squeezed press iip. U | 18 | WHITE | 2023-03-03 | SQUEEZE CEMENT | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
506 | 506 | m/up test assy close bop. squeeze 08 bbl cmt slurry @ 1500 psi. R | 18 | WHITE | 2023-03-03 | SQUEEZE CEMENT | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
507 | 507 | open bop direct wash 1-1/2 cycle gpm-300/50 psi. pooh f/ 970 m to 911 m. 1 | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
508 | 508 | Pick uo & make up 5"mule shoe and x/o on 5-1/2" dp Rih to 850m. O T | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
509 | 509 | con't pooh f/ 1080 m to 970 m. | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
510 | 510 | bleed off squeezed press (1072 psi) got returns 0.5 bbl. opened bop, ‘closed b-sec”. break & l/dn test assy | 1 | WHITE | 2023-03-03 | RIG UP & TEAR DOWN | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
511 | 511 | Pump 35 bbls hi-vis & spot. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
512 | 512 | P/U and M/U BHA #5 with 12-1/4" Rock Bit with MWD. RIH 2 stands of 6-3/4" Drill collar and 4" HWDP to 353' MD. Tag weight 4 Klbs. | 6 | WHITE | 2023-03-03 | TRIPS | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.25 | CHAOPHRAYA | SOUTH EAST ASIA
513 | 513 | Circulate condition mud 1-1/2 cycle. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
514 | 514 | Back ream out of the hole with 9.2 ppg WBM to 1 stand below mud line, GPM:800 RPM:80. Pump out the last stand to ML and pull out of the hole. Rack back BHA in derrick. | 3 | WHITE | 2023-03-03 | REAMING | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
515 | 515 | Pump 50 bbl 240 PPB LCM Pill # 9 chase with 100 bbl normal mud 74 PCF pump again 50 bbl 240 PPB LCM IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
516 | 516 | Run Drill-in 9-5/8" casing with 9.2 ppg PHPA from 322' MD to 352' MD. Tag weight 3 Klbs. Decision was made to spud well with Drill in casing. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.25 | CHAOPHRAYA | SOUTH EAST ASIA
517 | 517 | Circulate B/U with 9.2 ppg PHPA WBM. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
518 | 518 | 5th C. Note: Drilling hard formation from 639' MD to 646' MD with 120RPM, 700 gpm 3-5 Klbs. | 2 | WHITE | 2023-03-03 | DRILL ACTUAL | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.5 | CHAOPHRAYA | SOUTH EAST ASIA
519 | 519 | R/U rig tong and P/U Drill in casing DS-2 in rotary table. Break out drill in casing with float collar and M/U with 9-5/8" single joint. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.5 | CHAOPHRAYA | SOUTH EAST ASIA
520 | 520 | Pump out of the hole to ML with 9.2 ppg WBM, GPM:800. Pull out of the hole. L/D Drilling spear. 2 Note: R - L/D 8 singles joint of 9-5/8" casing side way. U - Rack back 3 stands of 9-5/8" casing on the derrick. O T | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
521 | 521 | Circulate and displace well with 9.2 ppg PHPA WBM. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
522 | 522 | Continue attempts to drill with difference parameter at 642'MD - no success. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
523 | 523 | 4th Spud well at 08:45 hours. Drill-in 9-5/8" casing with 9.2 ppg WBM (split stream) from 353' MD to 642' MD. Hit hard formation. T H G I N DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 3.25 | CHAOPHRAYA | SOUTH EAST ASIA
524 | 524 | Continue RIH with casing drill in assembly and wash down to tag mud line at 353' MD. T | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
525 | 525 | P/U and RIH with casing drill in assembly to 317' MD. M/U 9-5/8" casing spear to TDS and function test. U O | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.25 | CHAOPHRAYA | SOUTH EAST ASIA
526 | 526 | Continue pull out of hole to and L/D bent casing side way. Note: Total bent casing, 9 joints and 1 pup joint. R | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 6.25 | CHAOPHRAYA | SOUTH EAST ASIA
527 | 527 | Hoock up cmt line. Test @2000psi ok.Pump 25 bbls drill water sa pri flush, 12 bbls cmt ip. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 | 17 | WHITE | 2023-03-03 | PLUG BACK | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
528 | 528 | Pooh F/850m to 700m make up test assy for cmt job. | 6 | WHITE | 2023-03-03 | TRIPS | PSW | Held PJSM For RIH with Mule shoe. 17. Plug Back 0.50 Saver sub 5 1/2 ' connection-460. 18. Squeeze Cement 7.50 Wash pipe hours: 236hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 MSUB 5.00 13.62 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 XO 7.00 2.69 IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 32 32 32 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.50 2,279.89 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,296.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 63,000 REMARKS: Held PJSM For RIH with Mule shoe. TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-471. NO. OF DAYS Wash pipe hours: 236hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 23 Date: 03-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
529 | 529 | Pump 10 bbls 74 pcf through string every 15 mins, Fillup 30 bbls in annulus every 30mins, reciprocate string and rotate 10 rpm, 8- 10K trq, | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
530 | 530 | HELD TBSM, ROUGH CUT 13 3/8" CSG. R | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
531 | 531 | Pump 10 bbls 74 pcf through string every 15 mins, Fillup 30 bbls in annulus every 30mins, reciprocate string and rotate 10 rpm, 8- 10K trq, | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
532 | 532 | Pump 245 bbl 74 pcf mud in annulus.Line up Trip tank Observe 420 bbls p/hr losses. T | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
533 | 533 | Pump 80 bbls 208 PPB LCM pill #6 and spot same. Allow LCM to soak. U O | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2.5 | ACHEIVER | MENAM
534 | 534 | Pump 88 pcf 30 bbls mud in annulus every 30 mins, Pump 10bbls 74pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq R | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 3 | ACHEIVER | MENAM
535 | 535 | PICK UP 13 5/8" BOP FROM STUMP, SKID BACK RIG FLOOR TO WELL. NIPPLE UP DSA,13 5/8" BOP,CHOKE & KILL U HCR,MANUAL VALVES & COFLEX HOSES, BOP CONTROL HOSES,BELL NIPPLE,FLOW LINE & POLLUTION PAN AND O T FUNCTION TEST BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | 14 | WHITE | 2023-03-03 | N/UP BOP | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 5.5 | F G MCCLINTOCK | INDIA
536 | 536 | FINAL CUT & DRESS 13 3/8" CASING @ WELL HEAD. INSTALL PRIMARY & SECONDARY PRESSURE PLATES/SEALS. RIG UP 2 B SECTION WELL HEAD TIGHTEN SAME. PRESSURE TEST WELL HEAD @1500 PSI,HOLD FOR 15 MIN OK. R | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 4 | F G MCCLINTOCK | INDIA
537 | 537 | CONTINUE NIPPLE DOWN 21 1/4"BOP, HCR & MANUAL VALVES. SKID RIG FLOOR AND RACK BACK 21 1/4"BOP AND SECURE THE SAME. | 14 | WHITE | 2023-03-03 | N/UP BOP | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2.5 | F G MCCLINTOCK | INDIA
538 | 538 | HELD TBSM, MAKE ARRANGEMENT N/DN 21 1/4" BOP IN PROGRESS. O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 14 | WHITE | 2023-03-03 | N/UP BOP | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
539 | 539 | L/DN 1 SINGLE & CUT PIECE, R/DN 350 TON CASING SPIDER ELEVATOR. U | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
540 | 540 | RAISE 21 1/4" BOP STACK & SET 13 3/8" CSG SLIP IN "C" SEC WELL HEAD. 1 | 14 | WHITE | 2023-03-03 | N/UP BOP | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
541 | 541 | CONTD WOC,MEANWHILE PREPARE TO R/DN CEMENT HEAD AND RIG DOWN THE SAME. | 13 | WHITE | 2023-03-03 | WAIT ON CEMENT | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2 | F G MCCLINTOCK | INDIA
542 | 542 | WOC.- BOP CLOSED FOR 6 HOURS. OPEN ANNULAR BOP.CONTD WOC. | 13 | WHITE | 2023-03-03 | WAIT ON CEMENT | FGM | HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR LAY DOWN CUT CSG. 17. Plug Back SAVER SUB :- HT-55 - 99 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 102 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:10 18:00 23:50 I SIZE WEIGHT 9.90 9.90 9.90 T C. Treating E IADC CODE GRADIENT 0.5138 0.5138 0.5138 L D. Swabbing MANUFACT. VISCOSITY 70 70 70 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM ABOUT NIPPLE DOWN BOP .TBSM PRIOR TO NIPPLE UP 'B' SEC WELL HEAD AND TOTAL DAYWORK 0.00 0.00 13 5/8" BOP. NO. OF DAYS SAVER SUB :- HT-55 - 99 CONNECTIONS 29 FROM SPUD WASH PIPE :- 102 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 29 Date: 03-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 6 | F G MCCLINTOCK | INDIA
543 | 543 | L/D single. M/U 9-5/8" casing spear to TDS and function test. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.5 | CHAOPHRAYA | SOUTH EAST ASIA
544 | 544 | CONTINUE WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE ETC), 200MT D/WATER FOR MUD PREPARATION FOR 8-1/2” PHASE DRILLING, BACKLOAD BOAT FOR 1100 BBL SOBM (12.5PPG). 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 47 Date: 03-Mar-23 | 23 | WHITE | 2023-03-03 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 26 26 26 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 23.46 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 47 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 47 Date: 03-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 12 | RON TAPPMEYER | INDIA
545 | 545 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq T | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
546 | 546 | Pump 78 bbl 74 pcf mud in annulus.Line up Trip tank Observe 152 bbls p/hr losses. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
547 | 547 | Pump 117 bbl 74 pcf mud in annulus.Line up Trip tank Observe 300 bbls p/hr losses. H | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
548 | 548 | Pump 84 bbl 74 pcf mud in annulus.Line up Trip tank Observe 240 bbls p/hr losses. N | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
549 | 549 | Space out and closed BOP, continue to pump @ 200 Gpm, 299 Psi and get returns via Choke. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
550 | 550 | Circulate w/ 74 Pcf Mud in/out same, 200 Gpm pressure 290 Psi, 10 Rpm, 8 - 13K Trq, Loss rate +/- 168 bbls / hr | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
551 | 551 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq, | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
552 | 552 | Pump 60 bbl 74 pcf mud in annulus.Line up Trip tank Observe 174 bbls p/hr losses. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
553 | 553 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
554 | 554 | Pump 50 bbl 240 PPB LCM Pill # 8 chase with 100 bbl normal mud 74 PCF pump again 50 bbl 200 PPB LCM and displace string O T volume with 250 GPM , 450 psi | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
555 | 555 | Pump 53 bbl 74 pcf mud in annulus.Line up Trip tank Observe 218 bbls p/hr losses. U | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
556 | 556 | Pump 52 bbl 74 pcf mud in annulus.Line up Trip tank Observe 190 bbls p/hr losses. R | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
557 | 557 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq 2 | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
558 | 558 | Pump 68 bbl 74 pcf mud in annulus.Line up Trip tank Observe 160 bbls p/hr losses. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
559 | 559 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
560 | 560 | Allow LCM to soak mean while F/C Observe 180 bbls p/hr. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
561 | 561 | Pump 85 bbls 208 PPB LCM pill # 7 and spot same.observed partial returns. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
562 | 562 | Pump 73 bbl 74 pcf mud in annulus.Line up Trip tank Observe 240 bbls p/hr losses. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
563 | 563 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
564 | 564 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq G I | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 116 STD. D.P. 5.00 10,945.63 CUTTING STRUCTURE caustic soda 8 xc polymer 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION flo trol 20 Barofiber medium288 HOURS STANDBY KELLY DOWN solo flake fine 80 solo flake medeu2m88 TOTAL 11,232.36 BEARINGS GAUGE OTHER REASON carb 50 200 marble medeum 11 SEALS DULL PULLED WT. OF STRING marble course 3 REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 45 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 1,568.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 48 Date: 03-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
565 | 565 | 6th Spud well at 23:45 hours. Drill-in 9-5/8" casing with 9.2 ppg WBM (split stream) from 352' MD to 360' MD. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for drilling 9 5/8" casing,Pump out off hole. TOTAL DAYWORK 0.00 0.00 Riser less drilling with 12.1/4'Service all drilling handling equipment and general housekeeping, KEMS is NO. OF DAYS operational and COM set. 8 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 8 Date: 03-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
566 | 566 | Rig Down Expro slick line lubricator, BOP, and Rig down surface lin | E | WHITE | 2023-03-03 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.5 | MAIN PASS I | MENAM
567 | 567 | Continue Drill 6-1/8" hole (Motor+ Agitator) from 3017 m-md toTD at 3162 m-MD/ 2092.56 mTVD with 1.15 SG SDF, WOB 8-12 klbs, 1110 lpm, 3690-4050 psi, 120 rpm, TQ: 9-12 kft-lbs. P/U 342 klbs, S/O 155 klbs, R/O 214 klbs. Note: Back ream full stand every slide. | 2 | WHITE | 2023-03-03 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 8 | ENTERPRISE | MENAM
568 | 568 | Close crown valve. Bleed off WH pressure 280psi. Re-dress GS and m/u ESP/SLB Pump assembly in mouse hole. U | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 6.25 | TENACIOUS | WEST AFRICA
569 | 569 | SLB slick line jar down and shear GS. POH to surface. R | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
570 | 570 | Pick up to 1st over pull at 7170ft with 2400lbs, continue pick up to 2nd over pull at 7150ft and plug arm activate. Slack off to 7174ft latch Motor into profile. Access ESP check and confirm good reading from ACP. 2 | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.5 | TENACIOUS | WEST AFRICA
571 | 571 | Slick line continue RIH with Access ESP Motor and Plug Arm from 5600 ft and tag No-go at 7202ft. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
572 | 572 | Slick line RIH with SLB ESP protector and Access ESP Motor assembly from surface to 5600 ft. HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
573 | 573 | Pick up SLB ESP protector and Access ESP Motor assembly from mouse hole and secure inside slick line BOP. Slick line connect GS tool string to ESP motor assembly. Connect lubricator and pressure test QTS 3000 psi/5 minutes. Line up cement unit and fill slickline lubricator with 9.5 ppg brine. Pressure up to 350 psi above crown valve to equalize well pressure. Close low torque valve at slickline PCE and bleed off pressure DEPTH INTERVAL DRILL from cement uFnOitR bMeAhTinIOdN low torque valve,ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP FROM TO RCEOARME NO. Open c(rSoHwOnW va ClvOeR aEn RdE oCbOsVeErvReYd) 290 psi onST ArPigEB ELflDEoor gBOaINuTge.PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
574 | 574 | Retrieve Access ESP motor assembly, Transfer to mouse hole for inspect same, redress plug arm & 4" GS running tool. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 3.25 | TENACIOUS | WEST AFRICA
575 | 575 | Bleed 300 psi trapped pressure from slickline lubricator. Disconnect lubricator. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
576 | 576 | Slick line POOH from 7123 ft to surface. Close crown valve. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 2.25 | TENACIOUS | WEST AFRICA
577 | 577 | Slick line RIH with 4" GS tool from surface to 7123 ft and latch on Access ESP motor/ Plug Arm. NOTE :- While RIH @ 5400 ft observed cable jumped off the sheave on drum. Inspected cable then continue RIH. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 2.75 | TENACIOUS | WEST AFRICA
578 | 578 | Connect lubricator and pressure test QTS 2000 psi/5 minutes. T Line up cement unit and fill slickline lubricator with 9.5 ppg brine. H Pressure up to 310 psi above crown valve to equalize well pressure. Close low torque valve at slickline PCE and bleed off pressure G I from cement unit behind low torque valve, N Open crown valve and observed 300 psi on rig floor gauge. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
579 | 579 | Bleed 300 psi trapped pressure from slickline lubricator. U O Disconnect lubricator and redress GS tool & picked up spring jar. T | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
580 | 580 | Slick line continue POOH with GS tool string from 3500ft to surface. Close crown valve. R | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
581 | 581 | Grease and function C&K, Cement & Standpipe manifold valves. Continue running shakers, Desilter/Desander pump and monitor. Flush sandtraps & fill. 2 Pump out and flush Koomy unit reservoir and top up. R Assist marine crew offload cargo and deck management. U Replace shaker bed rubbers. O T Ram blocks moved to main deck for dressing and installation w/ModuSpec. Housekeeping DW brake HPU cabinet. Housekeeping in Sackroom in preparation for sea fastening. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 91 Date: 03-Mar-23 | 23 | WHITE | 2023-03-03 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 91 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 91 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 91 Date: 03-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
582 | 582 | Held PJSM. M/u ESP/SLB pump tool string. Connect QTS, equalize WH pressure. O T | 23 | WHITE | 2023-03-03 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
583 | 583 | Change out Annular regulator valve on Koomey unit.. Pressure up Koomey to 3000psi and monitor pressure. Replace Drill floor rotary motor cover after Hydraulic hose inspection. Assist deck crew with loading equipment onto rig. Clean discharge cones on desander R and run unit for MODU inspection. Run all shakers and degassers for MODU inspection. Carry out daily check on all running U O equipment. Assist ABS for pressure tested sea water line. Changed regulator valve for Koomey unit annular pressure. Top up T hydraulic to auto choke HPU. Assists troubleshoot for hydraulic cathead. Assists DP for pressure test koomey unit. House keeping in T port aft auxiliary room. Change lub oil filter for engine #4. Check and tie up cables STBD jacking house chord #B area. Continue jobs H to Work and support HVAC third party team to repairing HVAC units and job keep continue . Continue install compound in cables G I MCTs between PCR room and workshop. Continue to checked and troubleshooting on ice machine and job keep continue. Continue N 180 days PM on all bug blower. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 91 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 91 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 91 Date: 03-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
584 | 584 | SLB Slick line RIH with AccessESP/SLB Pump to 3500ft. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 Night Tour Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
585 | 585 | Slick line RIH with SLB ESP protector and Access ESP Motor assembly from surface to 5600 ft. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
586 | 586 | CONTINUE WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE ETC), 200MT D/WATER FOR MUD PREPARATION FOR 8-1/2” PHASE DRILLING, BACKLOAD BOAT FOR 1100 BBL SOBM (12.5PPG). 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 26 26 26 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 23.46 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 47 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 47 Date: 03-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 12 | RON TAPPMEYER | INDIA
587 | 587 | CONT'D SEA FASTENING & SECURING.HELD PJSM, C/OUT BUMP TEST – OK. JACKED DN HULL TO 7’ DRAFT -- OK . JACKED UP HULL TO 15 FT AIR GAP. CONTINUED TO SEA FASTENING & SECURING. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 3 Date: 03-Mar-23 | 1 | WHITE | 2023-03-03 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO BUMP TEST AND CHIPPING AND PAINTING. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 U/IBOP ---------3796 FUNCTIONS. NO. OF DAYS WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 0 FROM SPUD SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CUMULATIVE CHECKED COM, DLA, CMF – OK. ROTATING HOURS 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 HRS DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 3 Date: 03-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 12 | TRIDENT II | INDIA
588 | 588 | SECURED CANTILEVER EXTENTION . TOW BOAT GS ASMI REPORT @ 04:00 HRS ON 03-MARCH-2023. SEA FASTENING IS IP. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-03 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO BUMP TEST AND CHIPPING AND PAINTING. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 U/IBOP ---------3796 FUNCTIONS. NO. OF DAYS WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 0 FROM SPUD SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CUMULATIVE CHECKED COM, DLA, CMF – OK. ROTATING HOURS 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 HRS DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 3 Date: 03-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 12 | TRIDENT II | INDIA
589 | 589 | CIRC & CONDITION OBM THRU FULLY OPENED CHOKE. F/C: STATIC. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.5 | HIGH ISLAND II | MENAM
590 | 590 | POOH W/ BKR LOGGING TOOLS ON 5" DP TO 13 3/8" CSG SHOE. SPACED OUT SES ABOVE BOP. | 6 | WHITE | 2023-03-03 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.75 | HIGH ISLAND II | MENAM
591 | 591 | RIH BKR LOGGING TOOLS TO 5,800'. CIRC OPEN HOLE CAPACITY. F/C: STATIC. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.75 | HIGH ISLAND II | MENAM
592 | 592 | BKR LOGGING RUN #5: PUMP OUT FROM STATION #7 AT 5,316 FT. VOLUME OF FM FLUID PO 1.94 BBL. U * PERFORMED 30 MIN STICKY TEST. MOVE STRING FREELY. O T | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 5 | HIGH ISLAND II | MENAM
593 | 593 | HELD SAFETY STAND DOWN MEETING, DISCUSSED: WORK ON HIGHT. DROP OBJECT. STOP WORK AUTHORITY. PTW & 2 JSA. HOUSEKEEPING. R | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
594 | 594 | BKR LOGGING RUN #5: PUMP OUT FROM STATION #6 AT 5,353 FT. ABORTED DUE TO LOW MOBILITY. * PERFORMED 30 MIN STICKY TEST. MOVE STRING FREELY. | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
595 | 595 | BKR LOGGING RUN #5: PUMP OUT FROM STATION #6 AT 5,353 FT. ABORTED DUE TO LOW MOBILITY. U * PERFORMED 30 MIN STICKY TEST. MOVE STRING FREELY. O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.5 | HIGH ISLAND II | MENAM
596 | 596 | BKR LOGGING RUN #5: COLLECT SAMPLE FROM STATION #5 AT 5,552 FT. VOLUME OF FM FLUID PO 2.42 BBL. R | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 6 | HIGH ISLAND II | MENAM
597 | 597 | MOVE TO NEXT STATION AND PERFORM STICKY TEST. 1 | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
598 | 598 | BKR LOGGING RUN #5: STIKE TEST& PERFORM PUMP OUT STATION #3 AT 5560 FT. *MONITOR WELL ON TRIP TANK. | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing * PREPARE FOR RIG MOVE GREASE SKID BEAM. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE LIME 30 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 36 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 CLEAN BOP. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . * PREPARE FOR RIG MOVE GREASE SKID BEAM. *CLEAN UNDER SAND TRAP . . * CLEAN MUD PITS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . CLEAN BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 36 Date: 03-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 3 | HIGH ISLAND II | MENAM
599 | 599 | Pick up SLB ESP protector and Access ESP Motor assembly from mouse hole and secure inside slick line BOP. Slick line connect GS tool string to ESP motor assembly. Connect lubricator and pressure test QTS 3000 psi/5 minutes. Line up cement unit and fill slickline lubricator with 9.5 ppg brine. Pressure up to 350 psi above crown valve to equalize well pressure. Close low torque valve at slickline PCE and bleed off pressure from cement unit behind low torque valve, Open crown valve and observed 290 psi on rig floor gauge. | E | WHITE | 2023-03-03 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 11.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 31 Date: 03-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
600 | 600 | R/ down pumping assembly, POOH with 5'' drill pipe wet from 8286ft to 7400 ft 2 | 6 | WHITE | 2023-03-03 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 390hrs (60HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 901.30 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 46.7777 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.28 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 27 DP 5.00 2,583.00 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,366.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 19 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs (60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1 | MENTOR | WEST AFRICA
601 | 601 | Pick up and make up 6-1/8” BHA (AGS + M/LWD/PWD). Make up bit and load radioactive source. RIH with 6-1/8" AGS BHA on 4" HWDP stands including jar to 232 m-MD. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.75 | ENTERPRISE | MENAM
602 | 602 | PJSM with all crew involve for P/U 6-1/8" AGS BHA and load radio active source. O T | 23 | WHITE | 2023-03-03 | OTHER3 | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
603 | 603 | Drain mud motor, Break out drill bit, TBS, Plug in MWD cable, Break out mud motor assy, Rack back BHA and L/D Mud motor. U | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
604 | 604 | Unload RA R | 20 | WHITE | 2023-03-03 | DIRECTIONAL WORK | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
605 | 605 | Con't POOH with 6-1/8" Mud motor BHA from 268 m-MD to surface. 2 | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1 | ENTERPRISE | MENAM
606 | 606 | Flow check prior to POOH BHA, well static. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
607 | 607 | POOH 6-1/8" BHA (Motor+Agitator) with 4" DP ( inside 7" Casing shoe ) from 1976 m-MD to 268 m-MD. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.5 | ENTERPRISE | MENAM
608 | 608 | POOH 6-1/8" BHA (Motor+Agitator) with 4" DP ( inside 7" Casing shoe ) from 2529 m-MD to 1976 m-MD. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 10375 10548 Drill 180 10 6.500 42 5.7 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 10,375 38.17 228888..5511 6,865.4 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
609 | 609 | Perform trip drill well secured with in 30 secs. Flow check on trip tank, hole static. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
610 | 610 | POOH 6-1/8" BHA (Motor+Agitator) with 4" DP from 2643 m-MD to inside 7" Casing shoe at 2529 m-MD. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
611 | 611 | Pump slug 30 bbls and follow by 10 bbls 1.15 SG SDF. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
612 | 612 | POOH with 6-1/8" BHA (Motor+Agitator) ( Open hole ) from 3162 m-MD to 2643 m-MD. O T | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.75 | ENTERPRISE | MENAM
613 | 613 | Flow check well on trip tank. Well static. U | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
614 | 614 | Circulate hole clean with 1.15 SG SDF, 80 RPM, 1111 l/m, 3750 psi. TQ: 10-12 kft-lbs. Static gas 0.07%, BG 0.06%. R | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.25 | ENTERPRISE | MENAM
615 | 615 | At TD MWD take survey at bottom. Circulate 10 mins. Static test 10 mins. Well static. 1 | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
616 | 616 | Shallow test AGS/MWD as per DD/MWD instruction with MW 1.15 SG SDF 950 lpm,2210 psi UG / 2930 psi FG | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
617 | 617 | Held PJSM with the crew on tripping out of hole. Continue POOH 12 1/4'' RSS drilling assy on 5'' DP from 7400ft to 2973ft R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | 8 | RED | 2023-03-03 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 390hrs (60HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 901.30 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 46.7777 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.28 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 27 DP 5.00 2,583.00 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,366.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 19 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs (60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 5 | MENTOR | WEST AFRICA
618 | 618 | RIH 6-1/8" BHA (AGS + M/LWD/PWD) with 4" DP from 232 m-MD to 2546 m-MD ,( Inside 7" casing shoe). Note: M/U TDS and Fill up pipe with MW 1.15 SG SDF every 30 stds. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 2.25 | ENTERPRISE | MENAM
619 | 619 | Continue RIH 6-1/8" BHA (AGS + M/LWD/PWD) with 4" DP (Open hole) from 2546m-MD to 3138 m-MD. | 6 | WHITE | 2023-03-03 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.75 | ENTERPRISE | MENAM
620 | 620 | While change out TDS wash pipe, No success , Work string every 1 /hr to confirm is free. Continue circulating with 300gpm,800 psi while attempting to change out TDS wash pipe, | 8 | RED | 2023-03-03 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 390hrs (60HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 901.30 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 46.7777 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.28 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 27 DP 5.00 2,583.00 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,366.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 19 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs (60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 6 | MENTOR | WEST AFRICA
621 | 621 | While attempting to change out TDS wash pipe , Work string every 1/ hr to confirm string is free. Continue circulating with 300gpm,800 psi. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 8 | RED | 2023-03-03 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 390hrs (60HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 901.30 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 46.7777 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.28 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 27 DP 5.00 2,583.00 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,366.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 19 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs (60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 5 | MENTOR | WEST AFRICA
622 | 622 | Observed leakage from wash pipe. Racked back 2 stands, M/up pumping sub on string, circulate @ 300gpm/820psi while changing U out wash pipe. O T | 8 | RED | 2023-03-03 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 390hrs (60HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 901.30 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 46.7777 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.28 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 27 DP 5.00 2,583.00 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,366.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 19 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs (60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 2 | MENTOR | WEST AFRICA
623 | 623 | Staged up mud pump and set parameters continue drilling 12 1/4'' hole section as per DD instruction from 8319ft to 8387ft pump with 1 800 gpm, 3968 psi, 120 rpm, 16 -19k torque , 5-10kWOB, R | 2 | WHITE | 2023-03-03 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 390hrs (60HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 901.30 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 46.7777 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.28 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 27 DP 5.00 2,583.00 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,366.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 19 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs (60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.5 | MENTOR | WEST AFRICA
624 | 624 | Made connection, staged up pumps to drilling rate and observed relatively low standpipe pressure, troubleshoot same and observed standpipe bleed off manual and choke valves washed out. rectified same. | 8 | RED | 2023-03-03 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe Total hrs = 390hrs (60HRS left). 22. Surface Testing Wash pipe inspected. OK. DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 901.30 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 46.7777 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 37/26 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.28 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 27 DP 5.00 2,583.00 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,366.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 19 FROM SPUD Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe Total hrs = 390hrs ( 60HRS left). DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs (60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 17 3/4" ID X 28" OD insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe Total hrs = 390hrs ( 60HRS left). Wash pipe inspected. OK. KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Four engines on line, Engine #1, #3, # 4, for 24 hours. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 20 Date: 03-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 3.5 | MENTOR | WEST AFRICA
625 | 625 | Shipyard work scope: Motor man carry out daily checks and equipment maintenance. Continue to chip / buff in water maker room. 1x RN assist motor man 1x AD supervise radio room. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 | 23 | WHITE | 2023-03-03 | OTHER3 | SDF | Continue with shipyard work scope: 17. Plug Back 18. Squeeze Cement 1x RN assisting night shift motorman 19. Fishing 1x AD supervising radio room. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 1x RN assisting night shift motorman 0 FROM SPUD 1x AD supervising radio room. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
626 | 626 | Shipyard work scope: Drill crew: Continue with housekeeping and paint projects Continue mapping of trip tank 2. Continue to repair and replace suction valve hold down bolts in pit room. Continue with water maker room chipping / buffing. Strip / repair lower shakers wilden pump. Service gauges on trip tank pumps. Deck crew: Continue with chipping / buffing accommodation roof in preparation for painting. Continue with chipping / buffing cantilever hand rails in preparation for painting. Lift FRC from deployment station to main deck for maintenance. Technical department: Continue with drilling office overhaul. Perform PM routines as per Shelf schedule. Perform 6 monthly PM on FRC. Continue with drilling office upgrade. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | SDF | Continue with shipyard work scope: 17. Plug Back 18. Squeeze Cement 1x RN assisting night shift motorman 19. Fishing 1x AD supervising radio room. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 1x RN assisting night shift motorman 0 FROM SPUD 1x AD supervising radio room. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
627 | 627 | Shipyard work scope: IADCDAILY DRILLMIoNtoGr m RanE caPrrOy oRutT d aFilyO cRheMcks - a PndR eqOuiOpmFe nCt mOaPintYenance. Continue to chip / buff in water maker room. 1x RNN aOssTis tL mIoCtoEr mNaSnED BY IADC Generated by RIMDrill Drilling Information System 1x AD supervise radio room. DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | SDF | Continue with shipyard work scope: 17. Plug Back 18. Squeeze Cement 1x RN assisting night shift motorman 19. Fishing 1x AD supervising radio room. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 1x RN assisting night shift motorman 0 FROM SPUD 1x AD supervising radio room. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
628 | 628 | Shipyard work scope: Drill crew: Continue with housekeeping and paint projects 2 Continue mapping of trip tank 2. R Apply weather protection to BOP side outlet penetrations. U Continue to repair and replace suction valve hold down bolts in pit room. O T Continue with water maker room chipping / buffing. Service gauges on trip tank pumps. Clear out and organize slip and cut locker. Troubleshoot rotary table hydraulic line / PS21 open/close signal issue. Deck crew: Continue with chipping / buffing accommodation roof in preparation for painting. Continue with chipping / buffing cantilever hand rails in preparation for painting. Lift FRC from deployment station to main deck for maintenance. Technical department: Continue with drilling office overhaul. Perform PM routines as per Shelf schedule. Perform 6 monthly PM on FRC. Continue with drilling office upgrade. | 23 | WHITE | 2023-03-03 | OTHER3 | SDF | Continue with shipyard work scope: 17. Plug Back 18. Squeeze Cement 1x RN assisting night shift motorman 19. Fishing 1x AD supervising radio room. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 1x RN assisting night shift motorman 0 FROM SPUD 1x AD supervising radio room. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
629 | 629 | Shipyard work scope: O T Drill crew: Continue with housekeeping and paint projects Continue mapping of trip tank 2. Continue to repair and replace suction valve hold down bolts in pit room. Continue with water maker room chipping / buffing. Strip / repair lower shakers wilden pump. Service gauges on trip tank pumps. Deck crew: Continue with chipping / buffing accommodation roof in preparation for painting. Continue with chipping / buffing cantilever hand rails in preparation for painting. Lift FRC from deployment station to main deck for maintenance. Technical department: Continue with drilling office overhaul. Perform PM routines as per Shelf schedule. DEPTH INTERVAL DRILL Perform 6 monFtOhRlyM PAMTI OoNn FRC. ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP FROM TO RCEOARME NO. Continu(eS HwOitWh dCrOillRinEg R oEfCficOeV uEpRgYr)ade. STAPEBELDE BOINT PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | SDF | Continue with shipyard work scope: 17. Plug Back 18. Squeeze Cement 1x RN assisting night shift motorman 19. Fishing 1x AD supervising radio room. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 1x RN assisting night shift motorman 0 FROM SPUD 1x AD supervising radio room. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
630 | 630 | Shipyard work scope: Motor man carry out daily checks and equipment maintenance. Continue to chip / buff in water maker room. 1 1x RN assist motor man R 1x AD supervise radio room. U | 23 | WHITE | 2023-03-03 | OTHER3 | SDF | Continue with shipyard work scope: 17. Plug Back 18. Squeeze Cement 1x RN assisting night shift motorman 19. Fishing 1x AD supervising radio room. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope: TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 1x RN assisting night shift motorman 0 FROM SPUD 1x AD supervising radio room. CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 4 Date: 03-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
631 | 631 | Drilling 6-1/8" hole (AGS/MLWD) from 3162 mMD to 3215 mMD / 2134.8 mTVD with MW 1.15 SG SDF, 950 lpm, 3200-3800psi, 180 rpm, TQ: 10-12 kft-lbs, WOB 10 klbs as per DD/MWD instruction. P/U 350 klbs, S/O 160 klbs, R/T 215 klbs. Note: back ream as per DSV instruction : cycle pump to UG/FG as per DD instruction before connection IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 | 2 | WHITE | 2023-03-03 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 2.25 | ENTERPRISE | MENAM
632 | 632 | Make up TDS fill up string. Ream down 6-1/8" BHA (AGS/MWD) MWD log down to bottom with speed 100 m/hr from 3138 m-MD to 3162 m-MD with MW 1.15 SG SDF 950 lpm, 3000-3200 psi, 150 rpm, TQ: 9-10 klbs-ft. | 3 | WHITE | 2023-03-03 | REAMING | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
633 | 633 | M/U TDS and fill string, check and function MWD/LWD tool as per MWD instructions with 950 LPM, 3600 psi FG / 3080 psi UG | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 4.4 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 9.60 T C. Treating E 1 OTHER 6.13 15.49 IADC CODE GRADIENT 0.4982 PL DE.. TSewsatibnbging 1 MWD 5.75 95.57 MANUFACT. NOV NOV VISCOSITY 60 M 5 HWDP 4.00 156.79 TYPE DSH416S-C3 TKC46-F1 PV/YP 16/12 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. E267955 F288279 GELS 8/12 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 10,375 SOLIDS 9.6 DAYWORK TIME SUMMARY DEPTH IN 8,369 10,374 2 (OFFICE USE ONLY) TOTAL DRILL 2,006 174 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 102 STD. D.P. 5.00 9,689.63 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.32 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 31.27 CT G 2 TOTAL 10,547.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 215,000 X ER BHA REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 5 FROM SPUD Stop the job if unsafe CUMULATIVE 35 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 7 Date: 03-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
634 | 634 | M/U 7" TEST ASSY R | 15 | WHITE | 2023-03-03 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
635 | 635 | Preparing and new mixing mud SW-SS-Extradrill for 8 1/2" hole section as per mud eng. instruction. Meanwhile every 2hr perform break circulation and very 4hr circulate internal volume. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 5/8 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 91 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 9.8 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 18 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 18 Date: 03-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 12 | KEY MANHATTAN | MENAM
636 | 636 | ESTD PARA & MILLING (CUT) WINDOW F/ 1130M T/1133.42M. WITH GPM-550, PR.- 1220PSI, RPM-60/100, WOM-8/44 KIPS, TRQ-6/15 KLBS. FURTHER MILLING IP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | 20 | WHITE | 2023-03-03 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 3.5 | TRIDENT XII | INDIA
637 | 637 | PUMP 30 BBL SPACER & C/OVER TO SOBM. C & C MUD. GPM-500, PR-1070 PSI. O T | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2 | TRIDENT XII | INDIA
638 | 638 | SCRIBE AND ORIENTED MWD TOOL & SETTING 13-3/8” WHIP STOCK TO 22 DEG LEFT. SET PACKER @ 1139.2M WITH 2 1500PSI, SHEAR BOLT BY 60 KIPS SLACK OFF WT. P/UP STRING & SLACK OFF WITH 70 KIPS TO CONFIRM PKR SET. TOP R OF WINDOW @1130M. U | 20 | WHITE | 2023-03-03 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
639 | 639 | CNTD RIH 13-3/8” W/STOCK- MWD ASSY ON 5-1/2” DP F/460M TO 1139M W/CONTROLLED SPEED. | 6 | WHITE | 2023-03-03 | TRIPS | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 3 | TRIDENT XII | INDIA
640 | 640 | CONTINUE RIH 13-3/8” W/STOCK- MWD ASSY BHA F/ 31 M TO 460 M W/CONTROLLED SPEED. | 6 | WHITE | 2023-03-03 | TRIPS | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2.5 | TRIDENT XII | INDIA
641 | 641 | RETRIEVED WEAR BUSHING | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
642 | 642 | RIH 13-3/8” W/STOCK- MWD ASSY BHA UP TO 31M. FURTHER RIH I.P. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 3707 3719 Drill MILLING CASING 100 40000 1220 6.500 53 6.500 53 548.338 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-03 | TRIPS | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
643 | 643 | SHALLOW TEST HLB MWD TOOLS-OK. RACK BACK MWD TOOL IN DERRICK. (GPM-410/450, PR-310/550 PSI). O T | 20 | WHITE | 2023-03-03 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
644 | 644 | P/UP & M/UP HLB MWD TOOL & PUP JOINT. U | 6 | WHITE | 2023-03-03 | TRIPS | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
645 | 645 | P/UP & M/UP W/FORD MILL ASSY & 1 JNT OF 8” DC. R | 6 | WHITE | 2023-03-03 | TRIPS | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
646 | 646 | HLB SURF PREPARATION OF MWD TOOLS. 1 | 20 | WHITE | 2023-03-03 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 5.5 | TRIDENT XII | INDIA
647 | 647 | Preparing and mixing new mud SW-SS-Extradrill for 8 1/2" hole section as per mud eng. instruction. Meanwhile performed H/P test Choke manifold ( 300 - 5000 psi ) , Stand Pipe manifold ( 300 - 5000 psi ) and Cement manifold ( 300 - 5000 psi ). Every 2hr perform break circulation and very 4hr circulate internal volume. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 18 Date: 03-Mar-23 | 23 | WHITE | 2023-03-03 | OTHER3 | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 10.32 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.5356 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 15/10 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 5/8 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 91 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 9.8 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 9 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 18 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 18 Date: 03-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 12 | KEY MANHATTAN | MENAM
648 | 648 | CONTD WAITING ON LOGISTICS TO DELIVER 12-1/4” DD TOOLS. M/W MIX & PREPARE SOBM IN PITS. | 23 | WHITE | 2023-03-03 | OTHER3 | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
649 | 649 | HELD PJSM. P/UP & M/UP 13-3/8” W/STOCK WITH HLB MWD ASSY. INSTALL SHEAR BOLT & SHEAR PINS (08 NOS). | 6 | WHITE | 2023-03-03 | TRIPS | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
650 | 650 | SAFETY STAND DOWN MEETING, DISCUSSED SAFETY LEADERSHIP, STOP WORK AUTHORITY AND HSE ALERTS. | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
651 | 651 | HPJSM, FOR M/U 7" TEST ASSY 1 | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
652 | 652 | TESTED ANNULAR ON 7" ASSY TO 300/2400 PSI 10 MIN. U | 15 | WHITE | 2023-03-03 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
653 | 653 | BREAK CIRCULATION AND RECORD PARAMETERS FOR RUNNING IN OPEN HOLE. R | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
654 | 654 | RIH 7'' LINER ON 5'' DRILL PIPE FROM 5285 FT TO 7190 FT. FILL UP STRING EVERY 10 STANDS. 2 | 6 | WHITE | 2023-03-03 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2 | HIGH ISLAND IV | MENAM
655 | 655 | HELD SAFETY STAND DOWN MEETING. MONITOR WELL ON TRIP TANK, WELL STATIC. | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
656 | 656 | RIH 7'' LINER ON 5'' DRILL PIPE FROM 4878 FT TO 5285 FT. FILL UP STRING EVERY 10 STANDS. LAY DOWN JAR. | 6 | WHITE | 2023-03-03 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
657 | 657 | RIH WITH 5" HWDP ON 7" LINER AT CONTROL SPEED FROM 3874 FT TO 4878 FT , FILL UP STRING EVERY 10 STANDS DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
658 | 658 | CIRC ONE STING VOLUME WITH 7 BPM , 440 PSI | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
659 | 659 | P/U & M/U 7" WEATHERFORD LINER HANGER FROM 3848 FT TO 3874 FT , FILL UP PBR WITH POLEMAR | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
660 | 660 | PJSM, FOR P/U 7" LINER HANGER | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
661 | 661 | CHANGE OUT HANDLING EQUIPMENT FROM 7" TO 5" | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
662 | 662 | P/U & M/U 7" 26# L-80 NEW VAM F/209' TO 3848' | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 3.75 | HIGH ISLAND IV | MENAM
663 | 663 | P/U & M/U 7" 26# L-80 NEW VAM, SHOE TRACK APPLY THREAD LOCK FIRST 5 JOINTS TO 209 FT AND TEST SHOE | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1.25 | HIGH ISLAND IV | MENAM
664 | 664 | HPJSM, FOR RUNNING 7" LINER | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
665 | 665 | RIG UP EXPRO CASING HANDLING EQUIPMENT | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
666 | 666 | HOJSM, FOR R/U CSG EQUIPMENT | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
667 | 667 | LAY DOWN TEST ASSY O T | 15 | WHITE | 2023-03-03 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
668 | 668 | Pick up and lay out stand pipe kelly hose on the floor, clean the thread ok. 2 Attempt to install stand pipe kelly hose on the TDS. No success. R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 | 23 | WHITE | 2023-03-03 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
669 | 669 | Continue to Assist Electrician on installation of supply cable, service lubes on TDS. Continue with house keeping around the rig floor. | 23 | WHITE | 2023-03-03 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
670 | 670 | Assist Electrician/Mechanic on installation of supply cable, service lubes on TDS. O T Grease TDS as require. Apply cable lube on drill line (Drawworks). Carry out house keeping around the rig floor. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-03 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
671 | 671 | Continue to Wait on cement. Meanwhile monitor well on trip tank O T | 13 | WHITE | 2023-03-03 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.25 | BALTIC | WEST AFRICA
672 | 672 | Pump OOH from 1957m to 1867m at 500 lpm, 225psi. U | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
673 | 673 | RIH 3 1/2'' stinger washing down from 1881m to 1957m with 500lpm, 225 psi, R | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
674 | 674 | RIH 3 1/2'' Stinger from 1841m to 1880m. Make up TDS and took UP/DN weight PUW =165 kips, SOW = 165kips. Break circulation with 300 lpm had returns and increase flow to 500lpm, 265 psi. 2 | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
675 | 675 | Wait on cement. Meanwhile monitor well on trip tank | 13 | WHITE | 2023-03-03 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.5 | BALTIC | WEST AFRICA
676 | 676 | Wait on cement. Meanwhile monitor well on trip tank DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 13 | WHITE | 2023-03-03 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.75 | BALTIC | WEST AFRICA
677 | 677 | Wait on cement . Mean while P/U, M/U 5 1/2'' DP in singles, RIH on 5'' DP and 3 1/2'' cement stinger from 1430m to 1841m. Drop 3" drift in each of DP at V-door, pick up same and recover drift prior to M/U. (pick 18 joints /hr = 674.5ft/Hr) | 13 | WHITE | 2023-03-03 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2 | BALTIC | WEST AFRICA
678 | 678 | Waiting on cement . Mean while Rig down 5'' dp elevator and R/U 5 1/2'' dp elevator. | 23 | WHITE | 2023-03-03 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
679 | 679 | Carry our derrick management. ( Move 8 X 5'' HWDP from derrick BHA center finger to derrick left finger with elevator and repositioned 8 1/2'' racked BHA on the derrick center finger). | 23 | WHITE | 2023-03-03 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.25 | BALTIC | WEST AFRICA
680 | 680 | R/D 5 1/2'' DP from elevator bail and R/U 5'' DP to elevator bail. | 23 | WHITE | 2023-03-03 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
681 | 681 | POOH wet on elevator from 1880m to 1430m while monitor well on trip tank and pipe for correct displacement volume. Racked U 15stda/hr =1476 ft/hr. O T | 6 | WHITE | 2023-03-03 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
682 | 682 | M/U TDS and circulate string volume at 1500lpm, presure1160psi. R | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
683 | 683 | P/U, M/U 5 1/2'' DP in singles and RIH on cement stinger from 1430m to 1880m. Drop 3" drift in each of DP at V-door, pick up same and recover drift. monitor well on trip tank for correct pipe displacement . (M/U 15 jst/hr) 1 | 6 | WHITE | 2023-03-03 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 3.25 | BALTIC | WEST AFRICA
684 | 684 | Held PJSM and discussed TBRA with all involved personnel prior to P/U 5 1/2'' DPin singles from deck. | 23 | WHITE | 2023-03-03 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
685 | 685 | RIH 3 1/2'' stinger washing down from 1867m to 2111m and tag top of cement plug # 1 with 8 kips. Pick up string and repeat tag at 2111m with 8kips, 500lpm, 225 psi, | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2 | BALTIC | WEST AFRICA
686 | 686 | RIH 7'' LINER ON 5'' DRILL PIPE FROM 7190 FT TO 10809 FT. FILL UP STRING EVERY 10 STANDS. U | 6 | WHITE | 2023-03-03 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.5 | HIGH ISLAND IV | MENAM
687 | 687 | PU cement stinger 1m above TOC. LU & pump 3.2 m' of 1.80 sg hi-vis pill and Chase same with 18 m' of 1.50 sg RDF lo spo t pill al bottom. FR = 1220 1pm. SPP = 820 psl | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.25 | BALTIC | WEST AFRICA
688 | 688 | Hold PJSM with all personnel involved prior to perform cement plug #2 operation. | 23 | WHITE | 2023-03-03 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
689 | 689 | Install all upper dolly rollers on the TDS. Connect grease fittings and grease hoses on TDS dolly rollers. Secured dolly bolt with binding wire. 1 Open man hole cover on Mud Gas Separator R Flush and clean inside Mud Gas Separator. Ok U | 23 | WHITE | 2023-03-03 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 30th of January 2022 17. Plug Back Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: July 29,2022. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 41 Date: 03-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
690 | 690 | Pick up make up TBG hanger 11” x 3 ½” EUE, 3" BPV (TYPE H). R/U W/L equipment, RIH, W/ PX plug, set same @ 517' ORKB, RIH with prong set same in PX plug. L/D same. - completion string WT 115 KLB. - total no. of steel bands installed: 90 - total no. of cross coupling installed: 190 - daily / total losses: 200 / 786 BBLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | E | WHITE | 2023-03-03 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 2.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 9.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 34 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2 | RIG 141 | MENAM
691 | 691 | Continue RIH with ESP completion string on 3 ½" TBG JT'S F/6,160' T/ 6,581' ORKB | E | WHITE | 2023-03-03 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 2.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 9.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 34 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 4.5 | RIG 141 | MENAM
692 | 692 | Make up ¼" C/L to gas vent valve, P/T same to 3,000 PSI for 10 min's, hold ok, keep 3,000 PSI on ¼" C/L while RIH. M/U cable penetrator to PKR, cut ESP cable, splice same & connect to penetrator. | E | WHITE | 2023-03-03 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 2.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 9.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 34 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2 | RIG 141 | MENAM
693 | 693 | Pick up make up 9 5/8" X 3 ½" giant ESP PKR with gas vent valve with 1/4" control line fitting. U - PKR fully set value @ 2,500 PSI O T - PKR dressed with 9 shear screw x 6 KLB for releasing 54 K.LB'S O/P | E | WHITE | 2023-03-03 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 2.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 9.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 34 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1 | RIG 141 | MENAM
694 | 694 | Rig up wire line equipment. R/up surface line from CMT unit to W/L pump in sub, test same against LTV TO 300/1,500 PSI FOR 5/10 MIN'S. - pressure test wireline lubricator against W/L swab valve to 1500 PSI, HOLD. 2 - RIH W/ PX PLUG, SET SAME IN SSD NIPPLE @ 5,903' ORKB, Then RIH & set prong at plug and HOLD with S/L. R | 22 | WHITE | 2023-03-03 | SURFACE TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 2.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 9.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 34 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2.5 | RIG 141 | MENAM
695 | 695 | Rig up wire line equipment. R/up surface line from CMT unit to W/L pump in sub, test same against LTV TO 300/1,500 PSI FOR 5/10 MIN'S. 1 - pressure test wire line lubricate against W/L swab valve to 1500 PSI, HOLD. R - RIH W/ PX plug set same IN SSD NIPPLE @ 5,903' ORKB, Then RIH & set prong at plug and HOLD with S/L. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-03 | WIRELINE LOGS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 2.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 9.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 34 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2.5 | RIG 141 | MENAM
696 | 696 | H.P.J.S.M Continue RIH with ESP completion string on 3 ½" TBG Joints F/3,871' T/6,160' ORKB | B | WHITE | 2023-03-03 | TUBING TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with 17. Plug Back ESP completion string on 3 ½" TBG 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing 2.50 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 9.50 NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 9.50 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for pick up make up RIH with TOTAL DAYWORK 0.00 0.00 ESP completion string on 3 ½" TBG NO. OF DAYS 34 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 34 Date: 03-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 9.5 | RIG 141 | MENAM
697 | 697 | Close lo-torq valve, break connection at SES & re-open lo-torq valve. Observe no vacuum or back flow B/O & L/O SES assembly & space out pup joints. POOH on cement stinger from 2051 to 1986 mMD/RT IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | 17 | WHITE | 2023-03-03 | PLUG BACK | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
698 | 698 | Pump 7.4 m' of 1.65 sg spacer with rig pump@ 800 1pm, 600 psi. Close upper FOSV/lower IBOP & trap 500 psi. Pump 9.1 m' of 1.90 sg cement slurry @ 800 Ipm, 400-130 psi. Bleed off pressure. Open upper FOSV & lower IBOP. LIU rig pumps & displace cement slurry with 3.8 m' of 1.65 sg spacer. Close upper FOSV with cement unit, continue to displace cement slurry with 10.7 m' of 1.50 sg RDF at 800 lpm, 200 psi Note 1: Reduce pump rate to 320 lpm, 200-500 psi for last 2 m' of displacement. Note 2: No losses/gain during cement operations. Note 3: Under-displace string of 2 m3. | 17 | WHITE | 2023-03-03 | PLUG BACK | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
699 | 699 | Flush cement line with water, ok. Connect same to SES lo-torq valve. Close lo-torq valve & PIT surface line to 30 0/3000 psi for 5/5 min - ok. Open SES lo-torq valve & confirm upper/lower FOSVs open. Note: Monitor well on trip tank, well static. 22:30 23IA:30DCD1A.00ILY D1R7ILLPuINmpG 7 .R4 mE' PofO 1.R65T s gF sOpaRceMr w i-th P rigR pOumOpF@ C80O0 1PpYm, 600 psi. Close upper FOSV/lower IBOP & trap 500 psi. Pump 9.1 m' of 1.90 sg cement slurry @ 800 Ipm, 400-130 psi. BleedN oOff Tpr eLssIuCreE. ONpSenE uDpp eBr YFO ISAVD & Clower IBOP. Generated by RIMDrill Drilling Information System LIU rig pumps & displace cement slurry with 3.8 m' of 1.65 sg spacer. Close upper FOSV with cement unit, continue to displace cement slurry with 10.7 m' of 1.50 sg RDF at 800 lpm, 200 psi Note 1: Reduce pump rate to 320 lpm, 200-500 psi for last 2 m' of displacement. Note 2: No losses/gain during cement operations. Note 3: Under-displace string of 2 m3. DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 22 | WHITE | 2023-03-03 | SURFACE TESTING | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
700 | 700 | PU & MIU SES assembly: 5 /" PJ + FOSV + SES c/w lo-torq valve + FOSV. Confirm mule shoe @ 2051 mMD/RT | 23 | WHITE | 2023-03-03 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
701 | 701 | Circulate to condition mud while reciprocating string. FR = 1000 Ipm. SP = 670 psi. Final YP = 15 Ibf/100 f. Record PUW/SOW @ 180/180 klbs. POOH from 2051 to 2046 mMD/RT & R/B 5 1/2 " DP stand in derrick. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.25 | BALTIC | WEST AFRICA
702 | 702 | POOH 3 1/2'' cement slinger from 2110 to 2051 mMD/RT (60 m above TOC). | 17 | WHITE | 2023-03-03 | PLUG BACK | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.75 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.75 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.25 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 50 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 50 Date: 03-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
703 | 703 | WASH DOWN FROM 10809 FT WITH 3 BPM, 500 PSI AND TAG BOTTOM AT 10830 FT WITH 20K DOWN WEIGHT. PICK UP AND O T RE-TAG AGAIN AT 10830 FT. CALCULATE SPACE OUT. RACK BACK STAND OF 5'' DRILL PIPE. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
704 | 704 | OSV ADWITA UNDER THE CRANE @0048 HRS. OFF LOAD HLB 12-1/4" DD TOOLS BASKETS & LAY OUT ON C/LEVER DECK. | 23 | WHITE | 2023-03-03 | OTHER3 | T12 | HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 108 19. Fishing WASH PIPE HRS - 0 20. Directional Work 6.50 4.50 TOTAL WASH PIPE HRS: - 306.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. 22. Surface Testing DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:45 I 1 OTHER 11.68 53.45 SIZE WEIGHT 8.60 8.60 10.20 T C. Treating E 1 DC 8.00 31.07 IADC CODE GRADIENT 0.4463 0.4463 0.5294 PL DE.. TSewsatibnbging 1 MWD 8.25 18.01 MANUFACT. VISCOSITY 27 27 90 M 6 DC 8.00 181.17 TYPE PV/YP / / / O F. Other 4 1 XO 8.00 3.68 SERIAL NO. GELS / / / C G. Other 5 12 HWDP 6.75 363.29 JETS FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA pH TOTALS 12.00 12.00 27 HWDP 5.50 825.33 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 DP 5.50 31.76 DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 23 STD. D.P. 2,187.21 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 19.98 TOTAL 3,718.57 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 210,000 REMARKS: HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 1 NO. OF DAYS TOTAL CONNECTION - 109 7 FROM SPUD WASH PIPE HRS - 3.5 CUMULATIVE TOTAL WASH PIPE HRS: - 310 ROTATING HOURS DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIO R D TROIL MLEILRL:ING. FOLLOW IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT 13-3/8'' WHIP STOCK ASSY. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 108 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 306.5 DEBRIEF:1- RIH WITH 13-3/8'' WHIP STOCK ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT CHANGE OVER WELL FLUID AND MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 109 WASH PIPE HRS - 3.5 TOTAL WASH PIPE HRS: - 310 DEBRIEF:2- PJSM WITH CREW, MAKE SURE PERSON UNDER STOOD TASK. CORRECT LINED UP PITS FOR CHANGE OVER WELL FLUID WITH SOBM. PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 7 Date: 03-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
705 | 705 | SET HANGER AS PER HALIBURTON HANGER ENGINEER INSTRUCTION. | 23 | WHITE | 2023-03-03 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
706 | 706 | RIH W/4.5" 12 SPF TAG-CCI GUN | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
707 | 707 | SURFACE PREPARATION FOR PERFORATION RUN -3. | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
708 | 708 | POOH W/4.5" 12 SPF TAG GUN.TOOL STRING L/DN & B/OFF. O T | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 2 | J T ANGEL | INDIA
709 | 709 | CORRELATION PASS RECORDING & PERFORATED @ CROSS INTERVEL F/ 2492-2486M W/4.5" 12 SPF TAG GUN. U | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
710 | 710 | RIH WITH 4.5”12 SPF TAG GUN R | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
711 | 711 | M/A SURFACE PREPARATION FOR PERFORATION RUN -2 . 2 | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
712 | 712 | HELD PJSM CONT RIH HLS 4.5" 5 SPF TAG GUN & PERFORATED F/2492M -2486M (RUN -1). POOH TO SURFACE & L/DN TOOL . | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 3 | J T ANGEL | INDIA
713 | 713 | HLS W/LINE RIH WITH 4.5" 5 SPF TAG GUN. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
714 | 714 | HLS W/LINE SURFACE PREPARATION FOR PERFORATION RUN-1 R | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
715 | 715 | P/UP SHOOTING NIPPLE, SPACE OUT AND PRESSURE TESTED@2500PSIOK. RIG UP HLS SHEAVES, W/LINE & EQUIPMENT. 1 | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 2 | J T ANGEL | INDIA
716 | 716 | R/DN WEATHERFORD 4-1/2" TBG HANDLING EQUIPMENT. | B | WHITE | 2023-03-03 | TUBING TRIPS |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
717 | 717 | POOH 4.5” L80 13 CR 12.6 PPF BGT-1 TBG CTC ASSY IN STDS FROM 2328M TO SURFACE. (TOTAL STDS POOH: 90 ). | B | WHITE | 2023-03-03 | TUBING TRIPS |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 7.5 | J T ANGEL | INDIA
718 | 718 | Held PJSM, RIH Innovex 41/2'' X 7'' liner hanger assy on drifted 4'' D/Pipe in open hole @ controlled speed from 6688 ft to 10717 ft, Fill up with Hose while Rih. Monitor well thru trip tank well static. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 | 6 | WHITE | 2023-03-03 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.5 | HIGH ISLAND IX | MENAM
719 | 719 | Held PJSM, Connect TDS in 1st stand 4'' DP & Circulate 1.5 string volume @ 4 BPM 520 PSI. Record p/u & s/o WT. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
720 | 720 | RECORDING CORRELATION PASS IS IN PROGRESS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | A | WHITE | 2023-03-03 | PERFORATION |  | HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION 17. Plug Back CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL 18. Squeeze Cement HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES 19. Fishing INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 4.00 12.00 O B. Tubing Trips 8.00 NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 72 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 4 1/2" TBG. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 72 Date: 03-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
721 | 721 | Held PJSM, RIH Innovex 41/2'' X 7'' liner hanger assy on drifted 20 stands 4'' HWDP + 2 x 4'' pup JT to 6688 ft Fill up with Hose while Rih. Monitor well thru trip tank well static. | 6 | WHITE | 2023-03-03 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
722 | 722 | INSTALL GE 13-5/8" X 13-5/8" X 9-5/8" DSDPOF. PT DSDPOF TO 1000 PSI AGINST UPPER AND LOWER SEALS. GOOD TEST. | 23 | WHITE | 2023-03-03 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
723 | 723 | PICK UP 2 X PUP JOINTS AND MAKE UP CEMENT HEAD. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
724 | 724 | HPJSM, PIU & MU 9-5/8" BAKER TRACKMASTER HYDRAULIC ANCHOR U TYPE LONG SLIDE 2 WHIPSTOCK, 4 EA X 6-1/2" CORETRIX STRING MAGNETS & MILLING BHA, SCRIBE MWD TO O T WHIPSTOCK HI SIDE, CONNECT HYDRAULIC LINES. - PIU 6 JTS DIC, FLUSH AND DRIFT DC. | 6 | WHITE | 2023-03-03 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 3.5 | HIGH ISLAND V | MENAM
725 | 725 | HPJSM, PIU & MIU SLB MWD, SHALLOW TEST MWD @ 310 GPM 1 510 PSI R | 6 | WHITE | 2023-03-03 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2.5 | HIGH ISLAND V | MENAM
726 | 726 | HPJSM WITH BAKER WHIPSTOCK, SLB & RIG CREW. 2 | 23 | WHITE | 2023-03-03 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.17 | HIGH ISLAND V | MENAM
727 | 727 | SERVICE TOP DRIVE | 7 | WHITE | 2023-03-03 | LUBRICATE RIG | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.83 | HIGH ISLAND V | MENAM
728 | 728 | HPJSM, MIU BOP TEST ASSY AND PT WELLHEAD, TUBING SPOOL VALVES 300/2500 PSI & LID TEST ASSY. | 15 | WHITE | 2023-03-03 | TEST BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
729 | 729 | HPJSM, MIU BOP TEST ASSY AND PT WELLHEAD, TUBING SPOOL VALVES 300/2500 PSI & LID TEST ASSY. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 15 | WHITE | 2023-03-03 | TEST BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
730 | 730 | POH WITH HALLIBURTON 9-5/8" MST ON 4" DP TO SURFACE & LID HALLIBURTON MST. - MONITORING AND FILLING HOLE CONTINUOUSLY THRU TRIP TANK WITH 80 PCF VISCOUS BRINE WELL STATIC. | 6 | WHITE | 2023-03-03 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
731 | 731 | RIH W/HALLIBURTON RTRV TOOL, CIRC. & ENGAGE 9-5/8" RTTS PKR WITH STORM VALVE @ 180', RELEASE PKR, POH & LID SAME. - MONITORING AND FILLING HOLE CONTINUOUSLY THRU TRIP TANK WITH 80 PCF VISCOUS BRINE WELL STATIC. | 6 | WHITE | 2023-03-03 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
732 | 732 | N/U BELL NIPPLE. | 14 | WHITE | 2023-03-03 | N/UP BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
733 | 733 | HPJSM, NIU 11" IOM X13-5/8" 3M DSA AND 13-5/8" X 13-5/8" 10M BOP SPACER SPOOL. | 14 | WHITE | 2023-03-03 | N/UP BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
734 | 734 | N/UP DRILLING RISER AND 11' ADAPTOR SPOOL | 14 | WHITE | 2023-03-03 | N/UP BOP | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
735 | 735 | N/U NEW "CIW" 13-5/8" X 11" 3M TUBING SPOOL W/ 2 X 2-1/16" "CIW" GATE VALVE. R -PT SEALS TO 1500 PSI GOOD TEST. U -PT CAVITY BETWEEN THS AND DSDPOF TO 1500 GOOD TEST. O T | 23 | WHITE | 2023-03-03 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2.5 | HIGH ISLAND V | MENAM
736 | 736 | MADE FINAL CUT ON 9-5/8" CSG STUB & DRESS STUB HEIGHT TO 4-7/8". 1 | 23 | WHITE | 2023-03-03 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1.5 | HIGH ISLAND V | MENAM
737 | 737 | Held PJSM, Connect TDS in 1st stand 4'' HWDP & Circulate 1.5 liner volume @ 3.10 BPM 100 PSI. Record P/up Wt = 110klbs & S/off O T Wt = 108klbs (liner weight = 50 Klbs.). | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.25 | HIGH ISLAND IX | MENAM
738 | 738 | RIH BAKER 9-5/8" WHIPSTOCK ASSY WITH SLB MWD ON 5" HWDP/DP AT CONTROL SPEED TO 4593'. - MONITOR WELL ALL TIME THROUGH TRIP TANK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | 6 | WHITE | 2023-03-03 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP 19. Fishing PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL 20. Directional Work PRE JOB SAFETY METING. NIPPLE UP BOP 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP 22. Surface Testing PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P DRILLER: 23. Other 3 4.50 0.17 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I 1 OTHER 8.13 3.48 SIZE WEIGHT 9.60 9.60 9.60 T C. Treating E 1 WHIPST 8.00 18.56 IADC CODE GRADIENT 0.4982 0.4982 0.4982 PL DE.. TSewsatibnbging 1 MILL 8.50 1.58 MANUFACT. VISCOSITY 40 40 40 M 1 WMMILL 8.50 5.70 TYPE PV/YP 0/0 0/0 0/0 O F. Other 4 1 HWDP 6.63 30.80 SERIAL NO. GELS 0/0 0/0 0/0 C G. Other 5 1 PCPM 7.33 9.00 JETS FL. LOSS 0 0 0 H. Other 6 1 FLEX 6.33 8.94 TFA pH 8.5 8.5 8.5 TOTALS 12.00 12.00 1 FLOAT 6.50 3.54 DEPTH OUT SOLIDS 0 0 0 DAYWORK TIME SUMMARY 1 MWD 6.89 41.58 DEPTH IN 2 (OFFICE USE ONLY) 6 DC 6.50 184.99 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 4 MAGNET 6.19 28.71 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 336.88 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.PRESSURE TEST BOP~S 20 FROM SPUD PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR CUMULATIVE PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 1,650.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 Tour 2 Remarks (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING. HOT WORK ON THE PLATFORM AND WELL CASING STUMP PRE JOB SAFETY METING.INSTALL NEW CASING SPOOL PRE JOB SAFETY METING. NIPPLE UP BOP PRE JOB SAFETY METING. PRESSER TEST I KILL AND BOP PRE JOB SAFETY METING.POOH WHIT 5'' AND 4'' D/P PRE JOB SAFETY METING. L/D B.H.A Operations Activities (Continued...) DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TIME. PRE JOB SAFETY METING.PRESSURE TEST BOP~S PRE JOB SAFETY METING. LAY OUT TEST ASSEMBLY AND HOUSEKEEPING ON RIG FLOOR PRE JOB SAFETY METING. P/UP 9 5/8" WHIP STOCK ASSEMBLY AND RUN ON HOLE WITH 5" DRILL PIPE IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 20 Date: 03-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 4 | HIGH ISLAND V | MENAM
739 | 739 | Held PJSM, M/U Innovex 7'' x 4 1/2" HDC liner hanger w/ HNBR liner top packer & TBR. assy. R | B | WHITE | 2023-03-03 | TUBING TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.25 | HIGH ISLAND IX | MENAM
740 | 740 | Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication 2 | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
741 | 741 | Continue Circulate TBG & TCA through choke and condition brine77pcf with 3 BPM, 830 psi. Flow check well, Static. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2.75 | MAIN PASS I | MENAM
742 | 742 | Circulate tubing and TCA with 76PCF brine thru MGS with 3bpm, at 750psi. (At 12:00, 76 PCF Brine pumped 370 Bbls). DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.75 | MAIN PASS I | MENAM
743 | 743 | "Expro slick line perform the following: - RIH 3-1/2"" PX Plug and set in ""X"" NIPPLE at 6162' . RIH with check set, POOH. - RIH and set prong, POOH. - Fill string with 28bbls of 77 PCF brine and pressure test 3 1/2" PX plug to 1000psi / 10mins. OK | E | WHITE | 2023-03-03 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2.75 | MAIN PASS I | MENAM
744 | 744 | Bull head TBG with TCA closed 120 bbls 76 brine with 4 bpm, 700psi. | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
745 | 745 | Expro slick line operation. O T RIH with brush and clean XN nipple profile. | E | WHITE | 2023-03-03 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1 | MAIN PASS I | MENAM
746 | 746 | Expro slick line RIH with 4-1/2" Interwell ME- Plug ,Set at 200 ft, POOH R pressure test TBG against ME Plug at 1000psi hold 10/min good test.& Pressure test ME-Plug from TCA at 1000psi good test. and U Pressure test TBG bonnet Cavity to1500psi good test O T | E | WHITE | 2023-03-03 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2 | MAIN PASS I | MENAM
747 | 747 | Bull head TCA with 450 BBLS of 76 PCF brine with tubing closed with 3bpm, at 500psi. U | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2.5 | MAIN PASS I | MENAM
748 | 748 | Expro slick line perform following operation. POH with 2.75" drift and lay down same. RIH with HAL 3-1/2" DPU puncher. Punch tbg at 6111ft. Had good indication for punch POH. 1 | E | WHITE | 2023-03-03 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 3 | MAIN PASS I | MENAM
749 | 749 | PERFORM CEMENT JOB AS PER ARAMCO PROCEDURE AND GAME PLAN. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
750 | 750 | LINE UP MUD PUMP AND PUMPED 100 BBLS SPACER. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
751 | 751 | CIRCULATE WITH 5 BPM AND 836 PSI. MEAN WHILE HELD PJSM FOR CEMENT JOB. | 5 | WHITE | 2023-03-03 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.5 | HIGH ISLAND IV | MENAM
752 | 752 | Held PJSM, Change handling equipments to 4'' DP. U | 1 | WHITE | 2023-03-03 | RIG UP & TEAR DOWN | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.25 | HIGH ISLAND IX | MENAM
753 | 753 | Held safety stand down. Discussed alerts 25-23, Coflex hose hit choke valve actuator and shelf HSE alert personal injury. R | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
754 | 754 | Held a PJS< with crew for rigging down EXPRO Slick line. | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
755 | 755 | FLUSH AND PRESSURE TEST LINE TO 4000 PSI, GOOD TEST. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 36 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA PICK UP AND RIH 7" LINER CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 36 Date: 03-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
756 | 756 | Held PJSM, R/up 4 1/2" Liner tubing handling equipment & Power Tong, Monitor well on Trip tank. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
757 | 757 | Held PJSM, Change handling equipments to 3 1/2'' DP. 2 | 1 | WHITE | 2023-03-03 | RIG UP & TEAR DOWN | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.25 | HIGH ISLAND IX | MENAM
758 | 758 | Held PJSM, P/up & Rih with 4 1/2" 12.6# N.Vam Tbg as per tally F/ 322ft to 1426 ft (Total 36Jnts) install 4 1/2" Blade runner Centralizers as per plan, Fill up Tbg with Hose while Rih. Drift all Tbg at V door. Monitor well on Trip tank, Well static. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
759 | 759 | Held PJSM, M/up 4 1/2" Liner Shoe track: 4 1/2" Reamer Shoe, 4 jnts x 4 1/2" 12.6# N.Vam Tbg Jnts, 4 1/2" INNOVEX Float Collar, 4 x 4 1/2" 12.6# N.Vam Tbg Jnts, 4 1/2" INNOVEX Landing Collar, Baker lock all Shoe track connections and RIH to 322 ft, Monitor well on Trip tank, Well static. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
760 | 760 | Held PJSM, Held Pre job Safety meeting with all personnel involved with running Tbg, discussed roles & responsibilities. Monitor well on Trip tank, Well static. | 23 | WHITE | 2023-03-03 | OTHER3 | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
761 | 761 | Held PJSM. Clean and Clear Rig floor, Service TDS. and check for DROPS. Monitor well on Trip tank, Well static. | 7 | WHITE | 2023-03-03 | LUBRICATE RIG | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
762 | 762 | Held PJSM, Pooh w/ 6 1/8" Reaming assy on 4" HWDP, L/D Jars, L/down Roller Reamers & Break of Bit. Rack back 4 3/4" DC. U Monitor well on Trip tank, Well static. O T | 6 | WHITE | 2023-03-03 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
763 | 763 | Held PJSM, P/up & Rih with 4 1/2" 12.6# N.Vam Tbg as per tally from 1426 ft to 4771 ft (Total 84Jnts) install 4 1/2" Blade runner Centralizers as per plan Fill Tbg with Hose while Rih. Drift all Tbg at V door. Monitor well on Trip tank, Well static. | 12 | WHITE | 2023-03-03 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 5 | HIGH ISLAND IX | MENAM
764 | 764 | Held PJSM, Pooh with 6 1/8" Stiff Reaming assembly on 4" Drill pipe from 6721 ft to 1334 ft. top of BHA, Monitor well on Trip tank, 1 Well static. R | 6 | WHITE | 2023-03-03 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.5 | HIGH ISLAND IX | MENAM
765 | 765 | Service THS lock down screws, IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.75 | MAIN PASS I | MENAM
766 | 766 | Nipple Down 4 1/16", 3m X-tree & existing bonnet. | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2 | MAIN PASS I | MENAM
767 | 767 | Rigged up and secured 4 1/16" 3M Production tree and Bonnet in preparation to nipple down. | E | WHITE | 2023-03-03 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.5 | MAIN PASS I | MENAM
768 | 768 | Held PJSM for N/D X-mass tree & Bonnet | 23 | WHITE | 2023-03-03 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
769 | 769 | Set 4 1/2" BPV in tubing hanger profile. | E | WHITE | 2023-03-03 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 3:00 to 3:30 Held safety stand down. HSE Alert 25-23, Co Flex hose hit choke valve actuator & shelf HSE Alert, 19. Fishing personal injury proper PPE, Housekeeping & communication. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 6.75 5.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcuim chloride 25 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 14:45 to 15:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and 0 FROM SPUD HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 75.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 2 Date: 03-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
770 | 770 | Held PJSM, Pooh with 6 1/8" Stiff Reaming assembly @ controlled speed in open hole on 4" Drill pipe from 11377 ft to 6721 ft. Hole in good condition, Flow check, Well static. Drop 2 1/16” hollow drift in string. | 6 | WHITE | 2023-03-03 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 65 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 53 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP#3 with 46 spm, 500 psi for 1 hour. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 70 Date: 03-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 3 | HIGH ISLAND IX | MENAM
771 | 771 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
772 | 772 | Pump 51 bbl 74 pcf mud in annulus.Line up Trip tank Observe 110 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
773 | 773 | r/up bop handling gears. n/dn inner & outer bbl. n/dn bop & orientation of same ip. O T | 14 | WHITE | 2023-03-04 | N/UP BOP | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 3 | PARAMESHWARA | INDIA
774 | 774 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq U | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
775 | 775 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
776 | 776 | Pump 50 bbl 240 PPB LCM Pill # 11 chase with 100 bbl normal mud 74 PCF pump again 50 bbl 240 PPB LCM displace LCM Pill 2 string volume with 250 GPM , 320 psi. R | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
777 | 777 | Pump 50 bbl 74 pcf mud in annulus.Line up Trip tank Observe 104 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
778 | 778 | Pump 54 bbl 74 pcf mud in annulus.Line up Trip tank Observe 142 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
779 | 779 | Pump 44 bbl 74 pcf mud in annulus.Line up Trip tank Observe 130 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
780 | 780 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.25 | ACHEIVER | MENAM
781 | 781 | Pump 50 bbl 240 PPB LCM Pill # 10 chase with 100 bbl normal mud 74 PCF pump again 50 bbl 240 PPB LCM displace LCM Pill string volume with 250 GPM , 320 psi. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
782 | 782 | Pump 57 bbl 74 pcf mud in annulus.Line up Trip tank Observe 131 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
783 | 783 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
784 | 784 | Pump 50 bbl 74 pcf mud in annulus.Line up Trip tank Observe 93 bbls p/hr losses. O T | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
785 | 785 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
786 | 786 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
787 | 787 | Drop PBL Closing Dart UCD, pump down till land on PBL seat, Pressure up to 2500 Psi to close PBL with no success, | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
788 | 788 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
789 | 789 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
790 | 790 | pooh f/ 410 m to surface & l/dn m/shoe. U | 6 | WHITE | 2023-03-04 | TRIPS | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
791 | 791 | direct wash 2 cycle @ 410 m. R | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
792 | 792 | pooh f/700 m to 410m(10 stds). 1 | 6 | WHITE | 2023-03-04 | TRIPS | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
793 | 793 | con't pumped 25 bbls d/w as pre-flush, mix & pump 12 bbls 15.2 ppg cmt slurry, 12 bbls d/w as post-flush. displace with 33 bbls gel mud. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
794 | 794 | Pump 35 bbl 74 pcf mud in annulus.Line up Trip tank Observe 97 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
795 | 795 | POOH F/ 11100 ft to 10962ft whille back ream tight spot 200 Gpm 2200 Psi, 150 Rpm 12 - 18K Trq, Dynamic losses 190 bbls/hr IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | 6 | WHITE | 2023-03-04 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
796 | 796 | n/dn 13 5/8 bop. | 14 | WHITE | 2023-03-04 | N/UP BOP | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
797 | 797 | Pump 50 bbl 240 PPB LCM Pill # 12 chase with 100 bbl normal mud 74 PCF, displace LCM Pill string volume with 250 GPM , 250 psi. .Line up Trip tank Observe 90 bbls p/hr losses | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.25 | ACHEIVER | MENAM
798 | 798 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.25 | ACHEIVER | MENAM
799 | 799 | CIRC hole clean with 250 GPM , 10 RPM , 8-10 TQ Observe 120 bbls p/hr losses | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
800 | 800 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
801 | 801 | Pump 35 bbl 74 pcf mud in annulus.Line up Trip tank Observe 98 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
802 | 802 | Cont attempt to close PBL while increasing pressure to 3500 psi gradually and moving string and bleeding off pressure, increased pressure to 4000 psi observed plug shifted and PBL closed, established circulation. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
803 | 803 | Pump 53 bbl 74 pcf mud in annulus.Line up Trip tank Observe 138 bbls p/hr losses. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
804 | 804 | M/UP TEST ASSY R/UP & TEST SURFACE LINE @ 2000 PSI OK. PERFORM SIT @ 1280 PSI EQUIVALENT TO 14.4 PPG. (HOLD 2 10 MIN), B/OFF & L/DN TEST ASSY R | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
805 | 805 | Pump 54 bbl 74 pcf mud in annulus.Line up Trip tank Observe 152 bbls p/hr losses. I | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
806 | 806 | M/UP 12-1/4” (RR) BIT, BIT SUB & RIH WITH SLICK BHA TO 151M. (P/UP & M/UP 8-1/8” JAR.) R | 6 | WHITE | 2023-03-04 | TRIPS | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
807 | 807 | M/UP 13-3/8” TEST PLUG ASSLY & SURFACE LINES. FLUSH & TESTED SURFACE LINES TO 250/6000PSI. OK. PRESSURE TESTED 13-5/8” BOP TOP RAM, MANUAL KILL & CHOKE VALVES,KILL & CHOKE HCR VALVES,KILL & CHOKE COFLEX HOSES,FOSV,UPPER & LOWER I-BOP"S @ 250/5000PSI. OK. R/DN TEST ASSLY. 1 | 15 | WHITE | 2023-03-04 | TEST BOP | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 3.5 | F G MCCLINTOCK | INDIA
808 | 808 | CONT WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE), PREPARATION FOR 8-1/2” PHASE DRILLING, SINCE 0400 HRS OF 27.02.2023. CONT RECEIVED 10 LIFTS OF CHEMICALS, BOAT PULLED OUT@1224HRS. SCI NALANDA AGAIN UNDER CRANE @1500HRS, RECEIVED REMAINING CHEMICALS & BACK LOAD 2 MANIFESTED CARGO. M/WHILE CLEANED PITS & MUD PREPARATION IP. R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 48 Date: 04-Mar-23 | 23 | WHITE | 2023-03-04 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 26 26 26 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE D/W 525 CAUSTIC SODA 4 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION SODA ASH 8 PAC lv 62 HOURS STANDBY KELLY DOWN 23.46 PAC RG 8 asapzan 11 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON KCL 160 SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 48 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 48 Date: 04-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 12 | RON TAPPMEYER | INDIA
809 | 809 | BOAT SCI NALANDA UNDER CRANE @ 0900 HRS. BACK LOADED 1034 BBL SOBM & OFF LOAD WBM CHEMICALS IP. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-04 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 26 26 26 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE D/W 525 CAUSTIC SODA 4 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION SODA ASH 8 PAC lv 62 HOURS STANDBY KELLY DOWN 23.46 PAC RG 8 asapzan 11 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON KCL 160 SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 48 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 48 Date: 04-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 3 | RON TAPPMEYER | INDIA
810 | 810 | WAITING FOR WBM CHEMICALS (KCL, PHPA, PA, POLYMERS, SOLTEX, POLYOL, EP-LUBE), 150MT D/WATER FOR MUD PREPARATION FOR 8-1/2” PHASE DRILLING, BACKLOAD BOAT FOR 1100 BBL SOBM (12.5PPG) | 23 | WHITE | 2023-03-04 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-0 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 176 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 26 26 26 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 4,737.53 CUTTING STRUCTURE D/W 525 CAUSTIC SODA 4 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION SODA ASH 8 PAC lv 62 HOURS STANDBY KELLY DOWN 23.46 PAC RG 8 asapzan 11 TOTAL 7,350.07 BEARINGS GAUGE OTHER REASON KCL 160 SEALS DULL PULLED WT. OF STRING 214,000 REMARKS: WASH PIPE HRS: 0 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 761 HRS. NO. OF DAYS SAVER SUB :-0 CONNECTION. 48 FROM SPUD TOTAL CONNECTIONS :- 176 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 48 Date: 04-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 9 | RON TAPPMEYER | INDIA
811 | 811 | CIRC @ 800 GPM / 1420 PSI. O T | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
812 | 812 | Fill up sandtraps with ne mud 1.75 sg | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 63 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 32/12.7 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/6 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 19 Date: 04-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1 | KEY MANHATTAN | MENAM
813 | 813 | Preparing and new mixing mud SW-SS-Extradrill for 8 1/2" hole section as per mud eng. instruction. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 63 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 32/12.7 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/6 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 19 Date: 04-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 8 | KEY MANHATTAN | MENAM
814 | 814 | Continue to preparing and new mixing mud SW-SS-Extradrill for 8 1/2" hole section as per mud eng. instruction. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 63 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 32/12.7 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/6 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 19 Date: 04-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 8 | KEY MANHATTAN | MENAM
815 | 815 | Perform Displacment active system. with new mud SW-SS-Extradrill 1.75sg for 8 1/2" hole section as per mud eng. instruction. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 63 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 32/12.7 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/6 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 19 Date: 04-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 3 | KEY MANHATTAN | MENAM
816 | 816 | n/dn riser. | 21 | WHITE | 2023-03-04 | RUN/RETRIVE RISER EQUIPMENT | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
817 | 817 | Preparing and new mixing mud SW-SS-Extradrill for 8 1/2" hole section as per mud eng. instruction. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 63 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 32/12.7 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/6 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 19 Date: 04-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1 | KEY MANHATTAN | MENAM
818 | 818 | Repair drilling instrumentation ( Spectrum 1000 and rigsense ) Continue with circulation and mixing mud in pit #4. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 19 Date: 04-Mar-23 | 8 | RED | 2023-03-04 | REPAIR RIG | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 63 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 32/12.7 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/6 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.00 5,021.36 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.89 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 10.43 2 TOTAL 5,918.64 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 138 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 19 Date: 04-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 3 | KEY MANHATTAN | MENAM
819 | 819 | M/UP SIDE ENTRY SUB ASSY & SURFACE LINE,TESTED SURFACE LINE TO 250 / 2000 PSI,OK.PRESSURE TESTED 13 3/8" CSG TO 250 / 1835 PSI.(EQUAL TO S/WATER @2200 PSI) | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
820 | 820 | SET PARAMETERS DRILL OUT FLOAT COLLAR & CEMENT F / 1646 M TO 1646.40 M WITH 750 GPM / 1250 PSI, 65 RPM, WOB 10 - 15. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 3 | WHITE | 2023-03-04 | REAMING | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
821 | 821 | CONTINUE DRILL/CLEAR FLOAT COLLAR, CMT & SHOE FROM 1646.40 M TO 1669.50 M. TAG SHOE @ 1669 M. | 3 | WHITE | 2023-03-04 | REAMING | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2.5 | F G MCCLINTOCK | INDIA
822 | 822 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq H G | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
823 | 823 | Pump 53 bbl 74 pcf mud in annulus.Line up Trip tank Observe 138 bbls p/hr losses. T | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
824 | 824 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq T | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
825 | 825 | Pump 58 bbl 74 pcf mud in annulus.Line up Trip tank Observe 150 bbls p/hr losses. U O | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
826 | 826 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq R | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
827 | 827 | Displace LCM Pill string volume with 250 GPM , 295 psi | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
828 | 828 | P/UP & M/UP PBL SUB. FURTHER M/UP DP FOR TESTING IP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | 6 | WHITE | 2023-03-04 | TRIPS | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
829 | 829 | P/UP & M/UP 3 JNTS 6 5/8" HWDP & FLUSH THE SAME. CONTINUE POOH TO 112M (B/OFF & L/DN 8" D/JAR), | 6 | WHITE | 2023-03-04 | TRIPS | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
830 | 830 | POOH 12 1/4" SLICK BHA ASSY F/1674.5 M TO 150M. | 6 | WHITE | 2023-03-04 | TRIPS | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2.25 | F G MCCLINTOCK | INDIA
831 | 831 | FLOW CHECK WELL STATIC OK. | 6 | WHITE | 2023-03-04 | TRIPS | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.25 | F G MCCLINTOCK | INDIA
832 | 832 | M/UP TEST ASSY R/UP & TEST SURFACE LINE @ 4000PSI OK. PERFORM LOT PRESSURE DROP @ 1485PSI .PUMP 7.8 BBLS GET RETURN 6.8 BBLS. B/OFF & L/DN TEST ASSY. | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
833 | 833 | CIRCULATE OUT BTM UP @ BOTTOM PRIOR TO FIT (GPM800/1430 PSI) | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
834 | 834 | SET PARAMETER DRILL 12 1/4" NEW FORMATION F/ 1669.5 M TO 1674.50 M .(GPM 800/1430 PSI,RPM 75/TQ,1-2 KFT-LBS. U WOB 10-15K) O T | 2 | WHITE | 2023-03-04 | DRILL ACTUAL | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
835 | 835 | PUMP HI-VIS @ BOTTOM CIRCULATE OUT TO HOLE CLEAN PRIOR TO SIT (GPM770/1340PSI) | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
836 | 836 | Pump 10 bbls 74 pcf through string every 15 mins, reciprocate string and rotate 10 rpm, 8- 10K trq N | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:30 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 115 STD. D.P. 5.00 10,851.47 CUTTING STRUCTURE mica coarse 40 Baro fiber medium80 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION soliflag.f 40 marble medeum 6 HOURS STANDBY KELLY DOWN caustic soda 4 marble fine 2 TOTAL 11,138.20 BEARINGS GAUGE OTHER REASON mintreat 25 SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 46 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 49 Date: 04-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
837 | 837 | n/dn dual A' sec old well head & side outlet valves. | 23 | WHITE | 2023-03-04 | OTHER3 | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
838 | 838 | CONTD. RIH 12-1/4” SLICK ASSY ON 5-1/2” DP F/151 M TO 1646 M.TAG FLOAT COLLAR.(FILL UP EVERY 15 STANDS.) U | 6 | WHITE | 2023-03-04 | TRIPS | FGM | HELD PJSM ABOUT TEST BOP .TBSM PRIOR TO M/UP 12 1/4" SLICK BHA. 17. Plug Back SAVER SUB :- HT-55 - 102 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 104 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. CHECK C.O.M & CHOKE MANIFOLD OK. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 1.02 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 1 BS 8.00 2.85 IADC CODE 117 GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 3 DC 8.00 90.91 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.00 2.79 TYPE XR + CPS PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. RK0928 GELS / / / C G. Other 5 JETS 3x20 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 5,400 2 (OFFICE USE ONLY) TOTAL DRILL 94 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 4 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE BARITE 3 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 368.93 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 96,000 REMARKS: HELD PJSM ABOUT DRILL F/COLLAR,CMT & SHOE .TBSM PRIOR TO M/UP TEST ASSY FOR TOTAL DAYWORK 0.00 0.00 SIT. NO. OF DAYS SAVER SUB :- HT-55 - 103 CONNECTIONS 30 FROM SPUD WASH PIPE :- 108 HRS. CUMULATIVE 28 13 5/8" ANN :- 2 C/O ROTATING HOURS 21 1/4'' ANN :- 4 C/O DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 CHECK C.O.M & CHOKE MANIFOLD OK. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 30 Date: 04-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 3.5 | F G MCCLINTOCK | INDIA
839 | 839 | install 13 5/8 riser on a sec well head. | 21 | WHITE | 2023-03-04 | RUN/RETRIVE RISER EQUIPMENT | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
840 | 840 | Slick line RIH with Access ESP tubing stop from 6500 ft and set AccessESP tubing stop at 7102ft. POH to surface. | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.25 | TENACIOUS | WEST AFRICA
841 | 841 | Slick line RIH with Access ESP tubing stop from surface to 6500 ft . DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
842 | 842 | Bleed 300 psi trapped pressure from slickline lubricator. Disconnect lubricator. Slick line redress GS tool and make up Access ESP tubing stop to tool string. Connect QTS and pressure test QTS 3000 psi/5 minutes., equalize WH pressure. Open crown valve and observed 300 psi on rig floor gauge. | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.75 | TENACIOUS | WEST AFRICA
843 | 843 | Slick line POOH with GS tool from 7104 ft to surface.Close crown valve. | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.25 | TENACIOUS | WEST AFRICA
844 | 844 | Perform pressure test down the tubing 1000 psi. for 10 min. | 22 | WHITE | 2023-03-04 | SURFACE TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
845 | 845 | Slick line RIH with Access ESP pack off from surface to 7104 ft and set the same. N | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 2.25 | TENACIOUS | WEST AFRICA
846 | 846 | Pressure test Tubing 3000psi/30mins. Bleed off pressure. | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.25 | TENACIOUS | WEST AFRICA
847 | 847 | Bleed 300 psi trapped pressure from slickline lubricator. U O Disconnect lubricator. T Slick line redress GS tool and make up heavier tool string. T Make up Access ESP pack off to tool string. Connect QTS and pressure test QTS 3000 psi/5 minutes., equalize WH pressure. H Open crown valve and observed 300 psi on rig floor gauge. G I | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 2.25 | TENACIOUS | WEST AFRICA
848 | 848 | Slick line continue RIH with Access ESP/SLB Pump from 3500 ft to 7143 ft and set the same. | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 3 | TENACIOUS | WEST AFRICA
849 | 849 | Fill C&K manifold w/fresh water and line up for pressure testing. Trouble shoot test pump. Replace check valve. Assist deck crew w/deck management. 2 Prepare C&K HCR, manual valve and block on main deck for install on BOP setback area. R Begin Seafastening in MP room and pit room. U Tear out aux cooling water hoses hoses in pump room. O T PM's as required. General housekeeping and prep for rig move. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 92 Date: 04-Mar-23 | 23 | WHITE | 2023-03-04 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 92 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 92 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 92 Date: 04-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
850 | 850 | Continue to mentor and monitor Crew progress. Perform daily checks on drilling equipment. Trouble shoot pressure drop at the koomey unit, Ok. Assist turbstar inspectors on LGI at the derrick and under the Rig Floor. Carry out running equipment daily checks. R Change hydraulic hose for online hawk jaw. Transfer engine oil M 154 to storage tank in engine room. Changed valve for hot water U O line. Changed new pipe for hot water line. Assist drill crew clean BOP fluid tank. Troubleshoot for BOP hoist. Troubleshoot for high T pressure wash down gun on main deck. Checked spare part for overhaul engine #1. House keeping in port aft auxiliary room. T Continue check spare part for engine#1. Pressure test for sea water and drill water line. 90 days PM for all jacking gear boxes. H Change lub oil filter for engine #4. Assist for install fixation rack. G I N DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-04 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 92 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 92 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 92 Date: 04-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
851 | 851 | Observed leaks from wash pipe. Stop drilling, racked back 1 stands, M/up pumping sub on string, circulate @ 300gpm/820psi while changing out wash pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | 8 | RED | 2023-03-04 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 3.5 | MENTOR | WEST AFRICA
852 | 852 | Slick line POOH with GS tool from 7129 ft to surface.Close crown valve. R | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
853 | 853 | Continue to drill 12 1/4'' hole section as per DD instruction from 8479ft to 8506ft. with 800 gpm, 4353 psi, 120 rpm, 18-20 torque , 15- O T 20kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 320k, s/o wt-220k, Rot-wt 260k. Rop- 150 ft / hr ( INC 42.47 ,Azimuth -310.98). | 2 | WHITE | 2023-03-04 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.5 | MENTOR | WEST AFRICA
854 | 854 | Held PJSM for rig down SLB Slick line. 2 | 23 | WHITE | 2023-03-04 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
855 | 855 | WAITING ON LOGISTICS . MEAN WHILE CONT'D SEA FASTENING & SECURING FOR RIG MOVE. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 | 1 | WHITE | 2023-03-04 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 TBSM PRIOR TO JETTING ON STBD & PORT LEGS. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD & PORT LEGS. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 4 | TRIDENT II | INDIA
856 | 856 | PULLING/JETTING ON PORT LEG . PORT LEG RELEASED 5 FT. | 1 | WHITE | 2023-03-04 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 TBSM PRIOR TO JETTING ON STBD & PORT LEGS. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD & PORT LEGS. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 5 | TRIDENT II | INDIA
857 | 857 | C/OUT 1ST CYCLE OF PULLING/JETTING ON STBD LEG. STBD LEG RELEASED 5 FT. | 1 | WHITE | 2023-03-04 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 TBSM PRIOR TO JETTING ON STBD & PORT LEGS. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD & PORT LEGS. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 3 | TRIDENT II | INDIA
858 | 858 | GS ASMI REPORTED AT 08:30HRS, TRANSFERRED RIG MOVER TO GS ASMI FOR INSPECTION, CONNECT FRONT TOW LINE TO GS ASMI, JACK DOWN TO FLOATING DRAFT, CONNECT JETTING LINES TO STBD LEG, JET STBD LEG, FURTHER 1 JETTING OF STBD LEG IS IP. R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-04 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 TBSM PRIOR TO JETTING ON STBD & PORT LEGS. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD & PORT LEGS. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 3.5 | TRIDENT II | INDIA
859 | 859 | CONT'D SEA FASTENING & SECURING FOR RIG MOVE. | 1 | WHITE | 2023-03-04 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. 17. Plug Back U/IBOP ---------3796 FUNCTIONS. 18. Squeeze Cement WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 19. Fishing SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 20. Directional Work CHECKED COM, DLA, CMF – OK. 21. Run/Retrieve Riser Equip. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 22. Surface Testing HRS DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 TBSM PRIOR TO JETTING ON STBD & PORT LEGS. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 7" FT DRAFT TO CHECK WATER INTEGRITY. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 16" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD & PORT LEGS. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 4 Date: 04-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 8.5 | TRIDENT II | INDIA
860 | 860 | Close crown valve. Bleed off riser. Break and lay out tool string, Rig down Slick line. R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | E | WHITE | 2023-03-04 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.50 4.25 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 4.50 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 26 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 576 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-15 Rpt No: 32 Date: 04-Mar-23 | Lifua A-02 | SDT-22-15 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
861 | 861 | SAMPLE @ 5270'. | 11 | WHITE | 2023-03-04 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 11.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 37 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . *CHANG OUT DERRICK ESCAPE LINE. . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 8 | HIGH ISLAND II | MENAM
862 | 862 | BKR LOGGING RUN #5: COLLECT SAMPLE FROM STATION #9 AT 5270 FT -PERFORMED 30 MIN STICKY TEST. MOVE -STRING FREELY. -MONITOR WELL ON TRIP TANK. STATIC. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 11 | WHITE | 2023-03-04 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 11.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 37 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . *CHANG OUT DERRICK ESCAPE LINE. . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.75 | HIGH ISLAND II | MENAM
863 | 863 | BKR LOGGING RUN #5: COLLECT SAMPLE FROM STATION #8 AT 5,298 FT. VOLUME OF FM FLUID PO 2.05 BBL. O T | 11 | WHITE | 2023-03-04 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 11.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 37 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . *CHANG OUT DERRICK ESCAPE LINE. . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 6.5 | HIGH ISLAND II | MENAM
864 | 864 | RIH W/ BKR LOGGING TOOLS ON 5'' DP W/ CONTROLLED SPEED. FROM 4230 TO 5359' U | 11 | WHITE | 2023-03-04 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 11.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 37 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . *CHANG OUT DERRICK ESCAPE LINE. . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.25 | HIGH ISLAND II | MENAM
865 | 865 | HELD SAFETY STAND DOWN MEETING, DISCUSSED: SWA, PJSM, LIFTING OPERATIONS, SLIP/TRIP HAZARDS, SUPERVISION DURING CREW CHANGE. HAND & FINGERS INJURIES 1 *FLOW CHECK, STATIC. R | 6 | WHITE | 2023-03-04 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 11.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 37 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . *CHANG OUT DERRICK ESCAPE LINE. . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
866 | 866 | CONTINUE CIRCULATE THRU THE CHOKE WITH 160 GPM,300 PSI . | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 11.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 37 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . *CHANG OUT DERRICK ESCAPE LINE. . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
867 | 867 | SAMPLE @ 5247'. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | 11 | WHITE | 2023-03-04 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 11.50 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 37 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE OPS WITH 5'' D/P. ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . *CHANG OUT DERRICK ESCAPE LINE. . Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 37 Date: 04-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 4 | HIGH ISLAND II | MENAM
868 | 868 | Set drilling parameters and continue to drill 12 1/4'' hole section as per DD instruction from 8387ft to 8479ft. with 800 gpm, 4353 psi, 2 120 rpm, 18-20 torque , 15-20kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before R connection. Up-wt 320k, s/o wt-220k, Rot-wt 260k. Rop- 150 ft / hr ( INC 42.47 ,Azimuth -310.98). U | 2 | WHITE | 2023-03-04 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 3.5 | MENTOR | WEST AFRICA
869 | 869 | Continue RIH with 5'' drill pipe from 5689ft to 8387ft, Fill up string every 20 stands | 8 | RED | 2023-03-04 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 2.5 | MENTOR | WEST AFRICA
870 | 870 | Stop RIH, due to high wind speed at 32 knt /hr, Meanwhile make up TDS and circulate at 400 gpm, 2194 psi, reciprocate string | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1 | MENTOR | WEST AFRICA
871 | 871 | Circulate B/U with 9.2 ppg PHPA WBM. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
872 | 872 | 7th Spud well at 07:45 hours. Drill 15-3/4" hole with 9.2 ppg WBM from 358' MD to surface section TD at 825' MD / 825' TVD. Note: Drilling hard formation from 638' MD to 649' MD with 100 RPM, 800 gpm 3-5 Klbs. | 2 | WHITE | 2023-03-04 | DRILL ACTUAL | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
873 | 873 | P/U and M/U BHA #7 with 15-3/4" Digger Bit with MWD. RIH 2 stands of 6-3/4" Drill collar and 4" HWDP to 336' MD. Wash down to N 358' MD and tag weight 3 klbs. | 6 | WHITE | 2023-03-04 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
874 | 874 | Pump out of the hole to ML with 9.2 ppg WBM. Pull out of the hole. L/D Drilling spear. T Note: T - L/D 8 singles joint of 9-5/8" casing side way. H - Rack back 3 stands of 9-5/8" casing on the derrick. G I | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.25 | CHAOPHRAYA | SOUTH EAST ASIA
875 | 875 | Continue Drill-in 9-5/8" casing with 9.2 ppg WBM (split stream) from 360' MD to 637' MD. Observed pressure drop 215 psi and casing alignment is not straight down to MSL while drilling. R Decision made to pump out of hole to verify casing condition. U O | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 4 | CHAOPHRAYA | SOUTH EAST ASIA
876 | 876 | Back ream out of the hole with 9.2 ppg WBM to 1 stand below mud line, GPM:800 RPM:120. Pump out the last stand to ML and pull out of the hole. Rack back BHA in derrick. | 3 | WHITE | 2023-03-04 | REAMING | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1 | CHAOPHRAYA | SOUTH EAST ASIA
877 | 877 | Sat parameters gpm-500, press-300 psi, rpm-25/35, torq-5k, wob- 3-4k. Drill cmt.F/716 m to 761 m. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 | 3 | WHITE | 2023-03-04 | REAMING | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 3 | PARAMESHWARA | INDIA
878 | 878 | Cont Rih F/ 153 m to 440 m. U | 6 | WHITE | 2023-03-04 | TRIPS | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
879 | 879 | Pick up & Make up 8-1/2” bit assy & Rih to 153 m. R | 6 | WHITE | 2023-03-04 | TRIPS | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
880 | 880 | Rih cup tester and perform connection test @2000 psi. lay down cup tester. 2 | 15 | WHITE | 2023-03-04 | TEST BOP | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
881 | 881 | Stack function test-ok. | 14 | WHITE | 2023-03-04 | N/UP BOP | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
882 | 882 | Cont nipple up 13-5/8” Nipple up BOP. Nipple up Inner & outer barrel tight same. | 14 | WHITE | 2023-03-04 | N/UP BOP | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 3.5 | PARAMESHWARA | INDIA
883 | 883 | inatall 13 5/8 bop on riser . m/w install outer barrel installed & connected emergency fill up line. m/while tightening bop to riser bolts & dsa to A'' sec well head & tightening a sec outlet valves & tightining asec well head to b'sec well head ip. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 14 | WHITE | 2023-03-04 | N/UP BOP | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
884 | 884 | Wash down F/ 440 m to 716 m Tag cmt with 10 k. O T | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 3 | PARAMESHWARA | INDIA
885 | 885 | Run Drill-in 9-5/8" casing with casing elevator to 652' MD. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
886 | 886 | Observed casing alignment is not straight and lean to STBD side. Decision made to POOH to verify casing condition. | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
887 | 887 | Pull out of the hole casing to surface. L/D bend joint side way. Note: 2 Observed 3 joints of casing bent. All of 3 joint are above ML. R | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.25 | CHAOPHRAYA | SOUTH EAST ASIA
888 | 888 | RIH with 5'' drill pipe from 2707ft to 5785ft, Fill up string every 20 stands DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 8387 8506 Drill shale 120 15000 2150 6.500 70 6.500 70 794.4 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 8,409 42.47 331100..9988 7,344.4 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 8 | RED | 2023-03-04 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 3.25 | MENTOR | WEST AFRICA
889 | 889 | Held PJSM with crew on tripping in hole with 5 '' drill pipe | 8 | RED | 2023-03-04 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.25 | MENTOR | WEST AFRICA
890 | 890 | Clear rig floor and service TDS. And chief Mechanic carried out 90 days PM on TDS. | 7 | WHITE | 2023-03-04 | LUBRICATE RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1 | MENTOR | WEST AFRICA
891 | 891 | Held PJSM with the crew on slip and cut operation. Hang off block with man riding. Performed slip and cut operation . Cut off 126ft and slip in 126ft from the drum and un hung block | 9 | WHITE | 2023-03-04 | CUT OFF DRILL LINE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 2 | MENTOR | WEST AFRICA
892 | 892 | R/down all the equipment and tools used. Break out TDS and lower string install full open safety valve. | 23 | WHITE | 2023-03-04 | OTHER3 | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.5 | MENTOR | WEST AFRICA
893 | 893 | M/up circulating Swedge on string, circulating @ 300gpm/620psi while cutting off lock wires from Allen key blots on wash pipe. Loosing out stud on wash pipe and removed old wash pipe. Clean out surface, P/up new wash pipe and installed as per OEM fitting 1 instructions. Followed step by step as instructed. Carried out test with 50 RPM with out pumping for one minute. R/down swedge and R m/up TDS on string, pump with 500gpm- 1050psi checked for leakage all ok. Stop pumping and carried out the last checked and U tighten both nuts as instructed. O T | 8 | RED | 2023-03-04 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 4.25 | MENTOR | WEST AFRICA
894 | 894 | Continue POOH 12 1/4'' RSS drilling assy from 3366ft to 2707ft. | 6 | WHITE | 2023-03-04 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.97 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.7211 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 78 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.51 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 119 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 80 DP 5.00 7,695.93 TOTAL HRS 91 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE Lime 30 soltex 20 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 26.17 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 TOTAL 8,506.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 320,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 20 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 3.5 (hrs left 296.5) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 3.5 KPI on slip & cut. NA KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 2 (294.5 hrs left) Changed 04-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 5.5 KPI on slip & cut. = 2hrs KPI on slip to slip connection time: N/A KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 21 Date: 04-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.75 | MENTOR | WEST AFRICA
895 | 895 | Shipyard work scope: Motor man carry out daily checks and equipment maintenance. Continue to chip / buff in water maker room. 1x RN assist motor man 1x AD supervise radio room. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 5 Date: 04-Mar-23 | 23 | WHITE | 2023-03-04 | OTHER3 | SDF | General Maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard workscope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 5 Date: 04-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
896 | 896 | Drill crew; Continue finger board inspection, function and lubricate latches. Assist mechanical department needle gunning in water maker room. 2 Assist deck crew with handrail project. R Derrick man continue with mapping T/T 2 and sand traps U Continue changing out suction valve O'rings. O T | 23 | WHITE | 2023-03-04 | OTHER3 | SDF | General Maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard workscope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 5 Date: 04-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
897 | 897 | Drill crew; Clean threads, dope and apply denso tape on X/O subs on rig floor. Finger board inspection, function and lubricate latches. Assist mechanical department needle gunning in water maker room. Assist deck crew with handrail project. Derrick man continue with mapping T/T 2 and sand traps DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-04 | OTHER3 | SDF | General Maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard workscope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 5 Date: 04-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
898 | 898 | Motorman / Drill crew; Daily rounds and check's. RimDrill readings. 1 Pot water testing and recorded. R Start drain project for pumps in utility room - in progress. U Clean pitroom. O T | 23 | WHITE | 2023-03-04 | OTHER3 | SDF | General Maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard workscope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 5 Date: 04-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
899 | 899 | Ream casing down with Drill-in 9-5/8" casing with 9.2 ppg WBM (split stream) from 347' MD to 741' MD. Note: Observed casing alignment is not straight down at 635' MD. Decision made to continue drill ahead. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 8.25 | CHAOPHRAYA | SOUTH EAST ASIA
900 | 900 | P/U and RIH with casing drill in assembly to 326' MD. M/U 9-5/8" casing spear to TDS and function test. Continue RIH with casing drill U in assembly and wash down to 347' MD. O T | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG, Service all drilling handling 17. Plug Back equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre-tour meeting with the crews for POOH 9 5/8" casing, Riser less drilling with 9-5/8" CSG, Service TOTAL DAYWORK 0.00 0.00 all drilling handling equipment and general housekeeping, KEMS is operational and COM set. NO. OF DAYS 9 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 9 Date: 04-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.25 | CHAOPHRAYA | SOUTH EAST ASIA
901 | 901 | install secondary seal & n/up a sec well head & and tested 2500 psi ok & r/up side outlet valve. | 23 | WHITE | 2023-03-04 | OTHER3 | PSW | Held PJSM For cmt job with Mule shoe. 17. Plug Back Saver sub 5 1/2 ' connection-473. 18. Squeeze Cement Wash pipe hours: 237 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip.1.00 22. Surface Testing DRILLER: 23. Other 3 4.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 BS 6.50 3.02 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 3 DC 6.00 89.21 MANUFACT. VISCOSITY 32 32 32 M 1 XO 7.00 3.48 TYPE PV/YP / / / O F. Other 4 9 HWDP 5.50 276.05 SERIAL NO. GELS / / / C G. Other 5 1 XO 7.00 2.33 JETS FL. LOSS H. Other 6 1 JAR 6.50 29.86 TFA pH TOTALS 12.00 12.00 1 XO 7.00 2.92 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 5.50 92.49 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 7.00 2.66 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 21 STD. D.P. 5.50 1,994.32 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,497.15 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-485. NO. OF DAYS Wash pipe hours: 246 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 24 Date: 04-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
902 | 902 | HPJSM, P/U AND M/U SMITH 8-1/2" USED PDC BIT MSl616B SR#SM2173 ON SLB MTR/MWD/PBL ASSY IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | 6 | WHITE | 2023-03-04 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
903 | 903 | Erecting scaffolding around riser to Nipple up BOP O T | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.5 | MAIN PASS I | MENAM
904 | 904 | M/U SHORT TRIP BOP JETTING ASSY,JET & FLUSH BOP & WELLHEAD,UD JETTING ASSY | 23 | WHITE | 2023-03-04 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
905 | 905 | P/U 9 FT AND S/O 65 K , PICK UP 17 FT TO RETRIEVE UPPER PACK OFF , CONTINUE PICK UP STING TO 60 FT | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
906 | 906 | CONTINUE DISPLACE WITH OBM | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
907 | 907 | F/C, STATIC. POOH WET 12-1/4’’ HLB RSS+MWD ASSY F/1162M TO 1133M. OBSD O/PULL @ 1133M, IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | 8 | RED | 2023-03-04 | REPAIR RIG | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
908 | 908 | CHECKED SURFACE SYSTEM - OK. DECIDED TO POOH. | 8 | RED | 2023-03-04 | REPAIR RIG | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
909 | 909 | SET PARAMETERS AND DRLG 12-1/4" DIR HOLE WITH HLB RSS+MWD ASSY F/ 1142.5 M TO 1162 M. OBSD PRESSURE DROP GRADUALLY F/ 1600 PSI TO 1200 PSI. STOP DRILLING. DRILLING PARAMETERS - 800 GPM, 1630 PSI, 100 RPM, TORQUE 5/6 K. WOB 10KIPS. | 2 | WHITE | 2023-03-04 | DRILL ACTUAL | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
910 | 910 | REVERSE CIRC WITH 5 BPM , 1400 PSI 1 | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.25 | HIGH ISLAND IV | MENAM
911 | 911 | P/UP STRING WITH CIRCULATION & TRY TO PULL STRING ABOVE THE WINDOW, OBSD O/PULL. NO SUCCESS. RIH BACK TO 1142.5M & RESUMED DRILLING. | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
912 | 912 | ATTEMPT TO RIH WITH PUMP. OBSD PRESSURE 1600PSI, GRADUALLY DECREASING TO 1000PSI, C&C MUD OBSD O T NORMAL PRESS GPM-750, PR-1500PSI | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2 | TRIDENT XII | INDIA
913 | 913 | RIH 12-1/4” HLB RSS MWD ASSY ON 5-1/2” DP F/180M TO 1125M.ATTEMPT TO PASS STRING THROUGH WINDOW WITHOUT R PUMPING AS PER HLB DD. OBSD STRING TAKING WEIGHT OF 5 KLBS. U | 6 | WHITE | 2023-03-04 | TRIPS | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
914 | 914 | CONTD M/UP 12-1/4” HLB RSS MWD BHA & RIH UP TO 180M. P/UP 8” D/JAR (JAR BRT-1430HRS). 2 | 6 | WHITE | 2023-03-04 | TRIPS | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
915 | 915 | M/UP PUP JOINT & SHALLOW TEST MWD TOOL –OK(HLB MWD-RSS BRT-1400HRS) CHANGED HANDLING GEAR. | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
916 | 916 | CONTINUE P/UP & M/UP 12-1/4” HLB RSS MWD BHA & RIH UP TO 20M. | 6 | WHITE | 2023-03-04 | TRIPS | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
917 | 917 | P/UP & M/UP RSS TOOL, M/UP 12-1/4'' PDC BIT, PICK UP & RIH MWD TOOLS IN PROGRESS. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 3747 3812 Drill SHALE 100 8000 1630 6.500 81 6.500 81 838.026 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-04 | TRIPS | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
918 | 918 | ATTEMPT TO PASS STRING THROUGH WINDOW WITH CIRCULATION (500 GPM), OBSD STRING TAKING WT 5 KIPS AT 1132.50M. SEVERAL ATTEMPTS WITH PUMPING & PASS-THROUGH WINDOW F/ 1132.5M TO 1142.5M. | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
919 | 919 | M/UP JETTING ASSY. LOWERED SAME, FLUSHED BOP STACK & L/DN JETTING ASSY. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
920 | 920 | RIG DOWN CEMENT HEAD R | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
921 | 921 | DROP FOAM BALL AND CIRC X2 STRING VOLUME O T | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
922 | 922 | RESET KEMS AND CALIBRATE BLOCK HEIGHT. | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
923 | 923 | SERVICE TDS AND TRAVELING BLOCK. O T | 7 | WHITE | 2023-03-04 | LUBRICATE RIG | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
924 | 924 | CUT AND SLIP 100 FT OF DRILL LINE. U | 9 | WHITE | 2023-03-04 | CUT OFF DRILL LINE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1.5 | HIGH ISLAND IV | MENAM
925 | 925 | HELD SAFETY STAND DOWN MEETING. R | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
926 | 926 | HANG OFF BLOCK FOR SLIP AND CUT DRILL LINE. 2 | 9 | WHITE | 2023-03-04 | CUT OFF DRILL LINE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
927 | 927 | CLEAN AND CLEAR RIG FLOOR. | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
928 | 928 | POH WITH 10 STANDS OF 5" DP U | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
929 | 929 | BREAK AND LAY DOWN CEMENT ASSEMBLY. | 6 | WHITE | 2023-03-04 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
930 | 930 | POH WITH WFD RUNNING TOOLS AND LAY OUT SAME | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
931 | 931 | POH WITH 5" HWDP AND RACK BACK IN DERRICK | 6 | WHITE | 2023-03-04 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
932 | 932 | POH AND LAY DOWN 5" DP ( 180 JOINTS ) | 6 | WHITE | 2023-03-04 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 4.75 | HIGH ISLAND IV | MENAM
933 | 933 | HELD PJSM WITH CREW FOR LAY DOWN 5" DP | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
934 | 934 | PUMP 25 BBLS SLUG | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
935 | 935 | PERFORM SAFETY STAND DOWN MEETING | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
936 | 936 | LAY DOWN 6.5" D.C ( 3 JOINTS ) DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-04 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
937 | 937 | B/OFF & L/DN MWD TOOLS, 1X8'' DC & MILL ASSY. | 6 | WHITE | 2023-03-04 | TRIPS | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
938 | 938 | F/C - AT BHA WELL STATIC. CONT POOH BHA F/460 M TO 31 M. CHANGED ELEVATOR AS REQUIRED IN BHA. | 6 | WHITE | 2023-03-04 | TRIPS | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2 | TRIDENT XII | INDIA
939 | 939 | F/C - WELL STATIC. PUMPED SLUG. POOH WITH 12¼” MILLING ASSY ON 5 ½" DP F/1142.5 M TO 460 M. | 6 | WHITE | 2023-03-04 | TRIPS | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
940 | 940 | Continue Wait on 2nd cement plug to set. Meanwhile monitoring well on trip tank. Electrician troubleshoot and change out air leaks hose sensor on Drawworks motor C. Electrician troubleshoot and fixed TDS rotating shaft motor. Carried out 30 days pm on Drawworks. 180 days pm on Top drive wash pipe. 30 and 720 days pms on pipe handler ph 85. 1500 hours pm on top drive. 750 hours pm on top drive. 375 hours pm on top drive. Completed Wiring Terminations of Brine Pump AC Motor. Performed 90-Day P M Checks on Trip-Tank #2 AC Motor. Installed Replacement Air Pressure Switch on Top drive control System. Repaired Faulty Condition on Fire and Gas Detection Panel. Completed Annual PRV inspection and calibration survey. Perform 250 hours pm on engine #3 and #4. Prepared and prime BOP set back area. Clean stair way at the back of rig floor to radiator unit. Cleaning shale shakers still on going. Completed clean and closed buffer chambers on mud #1 . #2 & #3. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | 13 | WHITE | 2023-03-04 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 12 | BALTIC | WEST AFRICA
941 | 941 | Continue Wait on 2nd cement plug to set. Meanwhile monitoring well on trip tank. Electrician troubleshoot and change out air leaks hose sensor on Drawworks motor C. 2 Electrician troubleshoot and fixed TDS rotating shaft motor. R Carried out 30 days pm on Drawworks. U 180 days pm on Top drive wash pipe. O T 30 and 720 days pms on pipe handler ph 85. 1500 hours pm on top drive. 750 hours pm on top drive. 375 hours pm on top drive. Completed Wiring Terminations of Brine Pump AC Motor. Performed 90-Day P M Checks on Trip-Tank #2 AC Motor. Installed Replacement Air Pressure Switch on Top drive control System. Repaired Faulty Condition on Fire and Gas Detection Panel. Completed Annual PRV inspection and calibration survey. Perform 250 hours pm on engine #3 and #4. Prepared and prime BOP set back area. Clean stair way at the back of rig floor to radiator unit. Cleaning shale shakers still on going. Completed clean and closed buffer chambers on mud #1 . #2 & #3. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 13 | WHITE | 2023-03-04 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 12 | BALTIC | WEST AFRICA
942 | 942 | Continue Wait on 2nd cement plug to set .Meanwhile monitoring well on trip tank, Lower TDS close to floor and Mechanic/Electrician R/ U equipment and tools for carry out PMs on TDS. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 13 | WHITE | 2023-03-04 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 5 | BALTIC | WEST AFRICA
943 | 943 | Unhang block from hang offline and secured hang offline in derrick.While continue to monitor well on trip tank. | 23 | WHITE | 2023-03-04 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
944 | 944 | Slip & cut drilling line 26m. Note: Monitor well on trip tank, well static. | 23 | WHITE | 2023-03-04 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.5 | BALTIC | WEST AFRICA
945 | 945 | Pick up landing joints, M/U same to hanger, M/U cable penetrator to hanger cut ESP cable, SPLICE same & connect to penetrator. cut TRSSV & gas vent valve control lines, WRAP 6 FT below HGR neck feed same through HGR, raise pressure in C/L TO 4,500 PSI. | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 4 | RIG 141 | MENAM
946 | 946 | Commence Wait On Cement (WOC) for plug #2. Meanwhile Man-rid to hang off Block with two hang off line | 23 | WHITE | 2023-03-04 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
947 | 947 | Clean & clear rig floor of excess equipment. Un-install hook load sensor prior to slip & cut drilling line. | 23 | WHITE | 2023-03-04 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
948 | 948 | POOH 3 1/2'' cement stinger from 1740 to 1636 mMD/RT. | 17 | WHITE | 2023-03-04 | PLUG BACK | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
949 | 949 | L/U trip tank & perform flow check, well static. O T | 6 | WHITE | 2023-03-04 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
950 | 950 | Drop 7" foam ball & connect TDS. 1 LIU & circulate 2 x bottoms up down string with 1.50 sg RDF at 1835 lpm, 1500 psi while reciprocating string. R Note: Receive ±2 m' of pure spacer at surface. No cement or significant mud contamination/interface found. U | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1.75 | BALTIC | WEST AFRICA
951 | 951 | POOH 31/2'' cement stinger from 1986 to 1740 mMD/RT Note: Observe all 51/2" DP totally dry. | 17 | WHITE | 2023-03-04 | PLUG BACK | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
952 | 952 | Held PJSM and discussed TBRA with all involved prior to slip & cutting drill line. | 23 | WHITE | 2023-03-04 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back 1.25 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 3.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12,049. T C. Treating E IADC CODE GRADIENT 625. L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 51 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 51 Date: 04-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
953 | 953 | 'While preparing THS wing valve to connect hose for annulus pressure test, looked inside both wings for checkup, found steel metal 1 chunks in both sides setting in THS port which is connected to the wing valve. R | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2 | RIG 141 | MENAM
954 | 954 | Land TBG hanger 11” x 3 ½” EUE, 3" BPV (type H) in THS and tighten lock down screws. U | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 0.5 | RIG 141 | MENAM
955 | 955 | 'R/U surface line from CMT unit to W/L pump in SUB, test same against LTV to 500/3,000 PSI FOR 5/10 MIN'S. pressure test wireline O T lubricator against W/L swab valve to 3000 PSI, hold. pressure up TBG side T/ 2,500 PSI IN & SET 9 5/8" X 3 ½" giant ESP PKR, hold pressure for 10 MIN, then bleed pressure slowly. | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1.5 | RIG 141 | MENAM
956 | 956 | PUMP HI-VIS & CIRC OUT HOLE CLEAN. ( GPM-550, PR - 1260 PSI). | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
957 | 957 | DRESSED & REAMED WINDOW SEVERAL TIMES AND CHECK WINDOW WITH PUMPS & ROTATION, WITHOUT PUMPS AND U ROTATION- OK. O T | 3 | WHITE | 2023-03-04 | REAMING | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2.5 | TRIDENT XII | INDIA
958 | 958 | DRILLED NEW FORMATION (RAT HOLE) F/1135.5 M TO 1142.5 M. ( DRILLING PARA:- GPM-550, PR.- 1250 PSI, RPM-80, WOM- 1 40/42 KIPS, TRQ-6/10 KLBS). R | 2 | WHITE | 2023-03-04 | DRILL ACTUAL | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
959 | 959 | CONT MILL WINDOW F/ 1133.4 M T/1135.5 M. (TOW-1130 M, BOW-1135.5 M) PUMP HI-VIS AS REQUIRED ( COLLECT METAL CUTTING 500 KG). MILLING PARA:- GPM-550, PR.- 1220 PSI, RPM-80/100, WOM-40/44 KIPS, TRQ-6/10 KLBS. | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | T12 | HELD PJSM ABOUT MILLING CASING WINDOW. 17. Plug Back SAVER SUB CONNECTION - 1 18. Squeeze Cement TOTAL CONNECTION - 110 19. Fishing WASH PIPE HRS - 05 20. Directional Work 0.50 3.00 TOTAL WASH PIPE HRS: - 315 21. Run/Retrieve Riser Equip. DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, 22. Surface Testing PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RI G DFLROILOLRER A:ND INFORMED ABOUT 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 90 90 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 3 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 64 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,128.22 CUTTING STRUCTURE barite 9 LIME 40 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION CACL2 20 VG 69 16 HOURS STANDBY KELLY DOWN TOTAL 3,717.19 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 3 NO. OF DAYS TOTAL CONNECTION - 113 8 FROM SPUD WASH PIPE HRS - 3 CUMULATIVE TOTAL WASH PIPE HRS: - 318 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 4,800.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT MILLING CASING WINDOW. SAVER SUB CONNECTION - 1 TOTAL CONNECTION - 110 WASH PIPE HRS - 05 TOTAL WASH PIPE HRS: - 315 DEBRIEF:1- PUT MAGNETS PRIOR TO MILLING. FOLLOW INSTRUCTION WHILE MILLING WINDOW, PERSON STAND BY AT FLOW LINE AND COMMUNICATION WITH RIG FLOOR AND INFORMED ABOUT METAL CUTTING. USE PROPER PPE WHILE CLEANING MAGNETS. TASK DONE SAFELY. Operations Activities (Continued...) HELD PJSM ABOUT M/UP 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 3 TOTAL CONNECTION - 113 WASH PIPE HRS - 3 TOTAL WASH PIPE HRS: - 318 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 8 Date: 04-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
960 | 960 | Pull out two handrail from the derrick, taken to welder workshop for repairs. U Removed 6" Choke manifold over board line extension. O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 | 23 | WHITE | 2023-03-04 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
961 | 961 | Pick up remove restriction from traveling path and install elevator support solid body and torque arrestors on TDS. Work with electricians on TDS rotating head function. Pick 10' of 5'' DP from cantilever and secure on rotary table, M/up saver sub, lower/upper IBOP and screw onto TDS main shaft. 2 Continue to carry out house keeping around the Rig floor. R | 23 | WHITE | 2023-03-04 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
962 | 962 | Held PJSM prior to install upper/lower IBOP on TDS. 1 Work with Mechanic to fix leaving hydraulic hose on TDS Rotating head function. R Erect scaffold (plat-form) on rotary table to workable height prior to install torque arrestors and TDS elevator support solid body. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-04 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
963 | 963 | Installed dolly beam TDS stopper. Carry out house keeping on top of driller motor shade. | 23 | WHITE | 2023-03-04 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 42 Date: 04-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
964 | 964 | Nipple up X. mass tree tested same 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 8 | RIG 141 | MENAM
965 | 965 | Nipple down flow line bell nipple choke and kill line 13 5/8" BOP rack back same 13 5/8" riser | 14 | WHITE | 2023-03-04 | N/UP BOP | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 4 | RIG 141 | MENAM
966 | 966 | 'M/U BPV running rods, RIH & install BPV inside THS DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1 | RIG 141 | MENAM
967 | 967 | RIH with pulling tool on S/L, retrieve prong then PX plug, L/D W/L lubricator assembly. POOH with landing joint L/D same, L/D GESCO hdlg. | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2 | RIG 141 | MENAM
968 | 968 | R/U CMT line on THS wing valve, fill back side the test same with 500 PSI against packer for 10 min's, hold. | E | WHITE | 2023-03-04 | TESTING | 141 | Pre job safety meeting with all personal discussed procedures and plan for rig up slick line RIH 17. Plug Back retrieve PX Plug rig down same nipple down 13 5/8" BOP rack back same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 12.00 8.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for rig up X.mass tree TOTAL DAYWORK 0.00 0.00 pressure test same NO. OF DAYS 35 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 35 Date: 04-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1 | RIG 141 | MENAM
969 | 969 | CHANGE TO 4'' HANDLING EQUIPMENT. | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
970 | 970 | PICK UP AND MAKE UP 4'' TEST ASSEMBLY AND RIG UP SURFACE LINES. | 6 | WHITE | 2023-03-04 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
971 | 971 | INSTALL 11" CIW WEAR BUSHING IN TUBING HEAD SPOOL. | 23 | WHITE | 2023-03-04 | OTHER3 | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
972 | 972 | BREAK AND LAY DOWN SURFACE LINES AND 4'' TEST ASSEMBLY. | 6 | WHITE | 2023-03-04 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
973 | 973 | SURFACE PREPARATION FOR PERFORATION RUN#5 W/4.5" 12 SPF TAG -CCL GUN R | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
974 | 974 | RIH WITH HLS 4.5” 5SPF TAG GUN #4, PERFORATED F/ 2486-2480M. POOH & L/DN TAG GUN. 1 | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 6.5 | J T ANGEL | INDIA
975 | 975 | SURFACE PREPARATION FOR PERFORATION RUN#4 | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.63 | J T ANGEL | INDIA
976 | 976 | HELD PJSM POOH & L/DOWN TOOL STRING | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 2.37 | J T ANGEL | INDIA
977 | 977 | Held PJSM, P/U Innovex CMT head, break & L/D pup JT + TIW valve + X-O from CMT head. Monitor well thru trip tank hole static. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 | 1 | WHITE | 2023-03-04 | RIG UP & TEAR DOWN | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
978 | 978 | RADIO SILENCE & GUN ARMING RIH W/4.5" 12 SPF TAG-CCL GUN # 5. FURTHER RIH IS IN PROGRESS. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
979 | 979 | Held PJSM, POOH & L/D 2 X 4'' pup JT + 54 JT 4'' HWDP + Innovex liner running tool. Monitor well thru trip tank hole static. O T | 6 | WHITE | 2023-03-04 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 3.5 | HIGH ISLAND IX | MENAM
980 | 980 | Held PJSM, Drop 2 x Halliburton foam balls, circulate 2 x hole volume @ 10 bpm 2900 psi w/ 100% returns. R | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
981 | 981 | Held PJSM, Rig down Cement lines & cement head assy. 2 | 1 | WHITE | 2023-03-04 | RIG UP & TEAR DOWN | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
982 | 982 | Held PJSM, Continue reverse circulate 2 string volumes @ 3.8 bpm/950 psi & 1 bottom up normal circulation, observe 100 bbls of 95 pcf spacer, 20 bbls contaminate spacer & 8 bbls contaminate cement surface. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
983 | 983 | Held PJSM, Close Bop and reverse circulate 2 string volumes @ 3.8 bpm/950 psi DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
984 | 984 | Held PJSM, P/U running tool 8 feet to expose dog subs. Confirmed dog subs out with 10 kips . S/O 60 kips, Observed positive indication of dog subs shearing. set 4 1/2" HNBR liner top packer. P//U running tool 31 feet. | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
985 | 985 | Held PJSM, Halliburton mix 120 bbl 118 PCF Cement slurry as per Lab recipe in Batch mixer , Haliburton Pump 110 bbl 95 Pcf Hal Tuned Spacer ahead, pump 116 bbl 118 Pcf Cement slurry, Innovex release pump down plug had positive indication of tell- tale flag, Haliburton displace pump down plug with 1 bbl Cmt slurry, 10 bbls 95 Pcf Tuned Spacer, 55 bbls 76 Pcf OBM, 6 bbls 95 Pcf Tuned spacer, displace with 58 bbl 76 pcf OBM . Bump plug with 3200 psi. Held pressure for 5 mins, bleed off pressure. Float function Ok. No losses during cement job. | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
986 | 986 | Held PJSM, POOH with Innovex liner running tool on 4'' DP from 6588 ft to 1898 ft. Monitor well thru trip tank hole static. U | 6 | WHITE | 2023-03-04 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2.5 | HIGH ISLAND IX | MENAM
987 | 987 | Held Pre-job safety meeting prior to commence cement job. | 23 | WHITE | 2023-03-04 | OTHER3 | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
988 | 988 | CONT RIH W/4.5" 12 SPF TAG-CCL GUN # 5. PERFORATED F/ 2480-2486M. POOH & L/DN TAG GUN. | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 4 | J T ANGEL | INDIA
989 | 989 | RADIO SILENCE & GUN ARMING RIH WITH HLS 4.5” 12 SPF TAG GUN #6, PERFORATED F/ 2480-2486M. POOH & L/DN TAG 2 GUN. R | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 5 | J T ANGEL | INDIA
990 | 990 | PRESSURE TEST 13 3/8'' BOP AS PER ARAMCO POLICY AND PROCEDURE. PRESSURE TEST ANNULAR TO 300/3000 PSI AND UPPER PIPE RAM TO 300/2550 PSI FOR 10/10 MINS, GOOD TEST. | 15 | WHITE | 2023-03-04 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
991 | 991 | POH WITH BAKER 8-1/2" MILLING ASSY & RACK BACK 5" DP STDS ON DERRICK. -MONITOR WELL ALL TIME THRU TRIP TANK,WELL STATIC | 6 | WHITE | 2023-03-04 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2.5 | HIGH ISLAND V | MENAM
992 | 992 | SWEEP HOLE TWICE WITH 30 BBLS HI-VIS PILL, CHC AT HIGH PUMP RATE, FLOW CHECK - WELL STATIC. U CHECK WINDOW PASS FREELY WITHOUT PUMP OR ROTAION. O T WEIGHT OF METAL SWARFS RECOVERED = 55 KGS. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
993 | 993 | DRESS WINDOW. PASS UP AND DOWN THROUGH WINDOW WITH AND 2 WITHOUT PUMPS AND ROTARY R | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
994 | 994 | DRILL OUT 8-1/2" RAT-HOLE F/5273' T0/5279' WITH 84 PCF INNOVERT OBM & 100% CIRCULATION | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
995 | 995 | DRILL OUT 8-1/2" RAT-HOLE F/5267' T0/5273' WITH 84 PCF INNOVERT OBM & 100% CIRCULATION DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
996 | 996 | SURFACE PREPARATION FOR PERFORATION RUN#6 W/4.5" 12 SPF TAG -CCL GUN | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
997 | 997 | ESTABLISH MILLING PARAMETERS,MILL WINDOW IN 9-5/8" CASING '. SWEEP HOLE EVERY 1 FT MILLED. TOW 5250' & BOW 5267'. TIE IN NEW LATERAL L-0-1. | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 6 | HIGH ISLAND V | MENAM
998 | 998 | HPJSM, PUMP 30 BBLS SAFRA OIL, 30 BBLS HVP & DISPLACE HOLE WITH 84 PCF INNOVERT OBM, DISPALCE SURFACE LINES CHOKE & KILL LINES WITH OBM. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1.5 | HIGH ISLAND V | MENAM
999 | 999 | ORIENT WHIPSTOCK FACE AT 52 DEGREE LEFT OF HIGH SIDE AS PER SLB DD, SET WHIPSTOCK BY INCREASING FLOW 1 RATE TYO 700 GPM TO CLOSE CIRCULATING VALVE,PRESSURE UP STRING TO 2000 PSI, FOR 5 MIN, SIO 20 KBLS R CONFIRM SET, PIU 15 KLB CONFIRM PACKER NOT MOVING UP, INCREASED PRESS TO 3200 BREAK RUPTUR DISC, SLACK U OFF AND SHEAR BOLT W140 KLBS, PIU 20 FT. O T | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1.5 | HIGH ISLAND V | MENAM
1000 | 1000 | RIH BAKER 9-5/8" WHIPSTOCK ASSY WITH SLB MWD ON 5" HWDP/DP AT CONTROL SPEED TO 5312'. - MONITOR WELL ALL TIME THROUGH TRIP TANK. | 6 | WHITE | 2023-03-04 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
1001 | 1001 | L/DN HLS TOOL STRING, L/DN SHEAVES AND EQUIPMENTS, SHOOTING NIPPLE IN PROGRESS. U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | A | WHITE | 2023-03-04 | PERFORATION |  | HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. 17. Plug Back CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH 18. Squeeze Cement DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 19. Fishing OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 12.00 12.00 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:55 I SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E IADC CODE GRADIENT 0.4463 0.4463 0.4463 L D. Swabbing MANUFACT. VISCOSITY 26 26 26 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE drill water 50 caustic soda 1 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. TOTAL DAYWORK 0.00 0.00 CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH NO. OF DAYS DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR 73 FROM SPUD OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 116 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ Operations Activities (Continued...) HELD PJSM REGARDING RIH HLS 4.5" PERFORATION GUN. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 231 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 918(NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 05+ IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 73 Date: 04-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
1002 | 1002 | ESTABLISH MILLING PARAMETERS. CUT WINDOW THRU 9-5/8" CASING, SWEEP HOLE EVERY 1 FT MILLED | 20 | WHITE | 2023-03-04 | DIRECTIONAL WORK | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
1003 | 1003 | Held PJSM, Halliburton Flush and P/test Cmt lines to 300/3500 psi, | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
1004 | 1004 | L/D BAKER WHIPSTOCK MILLING ASSY & L/O SLB MWD. -GAUGE MILLS:LEAD MILL 1/8" UNDERGAUGE & FOLLOW MILL 3/16" UNDERGAUGE. - L/D 6 JTS 6-1/2" DC | 6 | WHITE | 2023-03-04 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. RIH WITH WHIP STOCK . 19. Fishing PRE JOB SAFETY METING.DRILLING WINDOW 8 1/2 ' 20. Directional Work 9.50 1.50 PRE JOB SAFETY METING. DISPLACE OBM 11.22 PPG 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 11.20 11.20 11.20 T C. Treating E IADC CODE GRADIENT 0.5813 0.5813 0.5813 L D. Swabbing MANUFACT. VISCOSITY 62 62 62 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING. POOH 5"DP. 21 FROM SPUD PRE JOB SAFETY METING L/D BHA. CUMULATIVE 8 PRE JOB SAFETY METING.JETTING BOP. ROTATING HOURS PRE JOB SAFETY METING.P/UP MOTOR. DAILY MUD COST ($) 1,420.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 21 Date: 04-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 3.5 | HIGH ISLAND V | MENAM
1005 | 1005 | Held PJSM, Innovex drop 1 1/2" Phenolic setting Ball, M/up & chase down Ball with 20 bbs hivis @ 1.6 bpm W/ 600 psi to land out on U Ball seat, Pressure up to 1700 psi, set Liner Hgr as per Innovex procedure, Slack off 30Klbs plus Liner Hgr Wt. & confirmed Liner Hgr O T set. Sheared Ball seat @ 2700 psi & confirmed w/ returns, Mechanically released setting tool. Confirm release/ Loss of 55 K Liner Wt. 4 1/2" TOL @ 6554ft , 4 1/2" LC @ 11050ft , 4 1/2" Reamer Shoe @ 11373 ft RKB. | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
1006 | 1006 | Nipple up 13 5/8" BOP | 14 | WHITE | 2023-03-04 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2.75 | MAIN PASS I | MENAM
1007 | 1007 | Held a PJSM to nipple up 13 5/8" BOP | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1008 | 1008 | Nipple up 13-5/8" HP riser with 11" 3M X 10M DSA, and tight the same U | 14 | WHITE | 2023-03-04 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
1009 | 1009 | PJSM prior to nipple up 13 5/8" 10k high pressure riser. R | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1010 | 1010 | Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication 1 | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
1011 | 1011 | Service THS lock down screws, All it free, Isolate SSSV C/L, Clean & check existing hanger neck profile thread (OK), M/U 4 1/2" | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.75 | MAIN PASS I | MENAM
1012 | 1012 | Held a PJSM prior to rigging up scaffolding around BOP. | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1013 | 1013 | PERFORM ACCUMULATOR DRAW DOWN TEST. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 15 | WHITE | 2023-03-04 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1014 | 1014 | PRESSURE TEST BLIND SHEAR RAMS TO 300/2550 PSI FOR 10/10 MINS, GOOD TEST. RIH TEST STRING AND SCREW INTO TEST PLUG. | 15 | WHITE | 2023-03-04 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1015 | 1015 | RIG DOWN SURFACE LINES. UNSCREW TEST ASSEMBLY FROM TEST PLUG AND PULL TO SURFACE. | 15 | WHITE | 2023-03-04 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1016 | 1016 | PRESSURE TEST 13 3/8'' BOP AS PER ARAMCO POLICY AND PROCEDURE. PRESSURE TEST ANNULAR TO 300/3000 PSI AND RAMS TO 300/2550 PSI FOR 10/10 MINS, GOOD TEST. | 15 | WHITE | 2023-03-04 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 3 | HIGH ISLAND IV | MENAM
1017 | 1017 | Held PJSM, Circulate hole clean w/ 76 pcf OBM & 100% returns, . R/up Cement surface lines. | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
1018 | 1018 | CHANGE TO 5'' HANDLING EQUIPMENT. | 23 | WHITE | 2023-03-04 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1019 | 1019 | PERFORM ACCUMULATOR DRAW DOWN TEST. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | 15 | WHITE | 2023-03-04 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1020 | 1020 | Raise scaffolding around riser to Nipple up BOP | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.5 | MAIN PASS I | MENAM
1021 | 1021 | PICK UP AND MAKE UP 5'' TEST ASSEMBLY. RIG UP SURFACE LINES. | 6 | WHITE | 2023-03-04 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 2.75 1.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:59 I SIZE WEIGHT 10.00 10.00 10.00 T C. Treating E IADC CODE GRADIENT 0.519 0.519 0.519 L D. Swabbing MANUFACT. VISCOSITY 45 45 45 P E. Testing M TYPE PV/YP / / / O F. Other 4 SERIAL NO. GELS / / / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 37 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW. CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 37 Date: 04-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1022 | 1022 | Nipple up Kill Manual and HCR valve assy. and Coflex hoses | 14 | WHITE | 2023-03-04 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2 | MAIN PASS I | MENAM
1023 | 1023 | Held PJSM to install BOP Valves and Coflex hoses. | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1024 | 1024 | Held PJSM. Make Up TDS and circulate hole clean with 76 pcf obm 2.75 bpm @ 630 psi and 100 % returns. 1 | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 4 | HIGH ISLAND IX | MENAM
1025 | 1025 | uHeld PJSM, RIH Innovex 41/2'' X 7'' liner hanger assy. on drifted 4'' D/Pipe in open hole @ controlled speed from10717ft to tag @ 11377 ft, Fill up with Hose while Rih. Monitor well thru trip tank well static. | 6 | WHITE | 2023-03-04 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
1026 | 1026 | Held PJSM. Bullhead TBG with 150bbls 76 pcf brine with 3BPM 70/850psi. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | 5 | WHITE | 2023-03-04 | CONDITION MUD & CIRCULATE | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.25 | MAIN PASS I | MENAM
1027 | 1027 | PJSM, Rig up Expro S-LINE LUBRICATOR & BOP WITH 4-1/2" NVAM FOSV, Pressure test SAME TO 300/200 psi/10 MINS, OK. Expro S-LINE PERFORM THE FOLLOWING: - - RIH & RETRIEVE 4-1/2" interwell plug at 200ft POOH. - RIH & RETRIEVE PRONG @ 6136ft.POOH. - RIH & RETRIEVE 3-1/2" PX PLUG @ 6136ft POOH. | E | WHITE | 2023-03-04 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 3 | MAIN PASS I | MENAM
1028 | 1028 | M/U 4-1/2"" LANDING STRING, SCREW IN TBG HANGER. O T | B | WHITE | 2023-03-04 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1 | MAIN PASS I | MENAM
1029 | 1029 | Pressure test BOP Stack Annular and Upper Pipe Rams 3-1/2"VBR & kill lines TO 300/2500psi good test. | 15 | WHITE | 2023-03-04 | TEST BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2.25 | MAIN PASS I | MENAM
1030 | 1030 | PJSM, Rig up BAKER Power tong 4-1/2" handling EQ." 2 | B | WHITE | 2023-03-04 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.75 | MAIN PASS I | MENAM
1031 | 1031 | Retrieve BPV from Tubing Hanger. | E | WHITE | 2023-03-04 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
1032 | 1032 | Connect BOP control hoses and Function test BOP from all panels, ok | 14 | WHITE | 2023-03-04 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.75 | MAIN PASS I | MENAM
1033 | 1033 | Nipple up Bell nipple. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 14 | WHITE | 2023-03-04 | N/UP BOP | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.25 | MAIN PASS I | MENAM
1034 | 1034 | Held PJSM, L/D single and M/up INNOVEX Cement head. R | 12 | WHITE | 2023-03-04 | RUN CASING & CEMENT | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 330.5 Hrs. 21. Run/Retrieve Riser Equip. Run MP#3 with 34 spm, 630 psi for 4.5 hour. 22. Surface Testing Run MP#3 with 44 spm, 63 psi for2 hour. DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 22:00 I SIZE WEIGHT 10.16 T C. Treating E IADC CODE GRADIENT 0.5273 L D. Swabbing MANUFACT. VISCOSITY 60 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 54 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 330.5 Hrs. ROTATING HOURS Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Run MP # 3 SPM 35 PSI 950 = 2 Hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 Tour 2 Remarks (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP#3 with 34 spm, 630 psi for 4.5 hour. Run MP#3 with 44 spm, 63 psi for2 hour. Run MP#3 with 34 spm, 500 psi for 0.5 hours. Operations Activities (Continued...) Function COM and KEMS and Reset, Function TIW and Grey Valve Both left in OPEN position SWL PKG----ROT = 240 Hrs. SWL PKG---CIRC = 330.5 Hrs. Run MP # 1,2 SPM 62 PSI 2900 = 2 Hrs Run MP # 3 SPM 35 PSI 950 = 2 Hrs IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 71 Date: 04-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
1035 | 1035 | Held PJSM to Nipple up Bell nipple and Control hoses. | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1036 | 1036 | Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in desert. Shelf HSE Alert - drop R object. U | 23 | WHITE | 2023-03-04 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 00:45 to 1:15 Held safety stand down. Discussed alerts 26-23 Fire in walk in chiller / freezer container. and HSE 19. Fishing Alert: 27-23 foot injury while rigging down rig equipment. Proper PPE, housekeeping, & communication. . 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 5.50 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 2.75 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 3.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost 0 FROM SPUD in desert. Shelf HSE Alert - drop object. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 3 Date: 04-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
1037 | 1037 | PJSM M/U 8-1/2" BHA. U | 23 | WHITE | 2023-03-05 | OTHER3 | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1038 | 1038 | Drill out cement and shoe. Clean out rat hole. | 3 | WHITE | 2023-03-05 | REAMING | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
1039 | 1039 | RIH and wash down to tag TOC at 548' MD. | 6 | WHITE | 2023-03-05 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.5 | CHAOPHRAYA | SOUTH EAST ASIA
1040 | 1040 | P/U and M/U BHA with Mud motor, LWD T/C and 8-1/2" PDC bit. Install radioactive source. Trip in hole with 5" HWDP. O T | 6 | WHITE | 2023-03-05 | TRIPS | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.5 | CHAOPHRAYA | SOUTH EAST ASIA
1041 | 1041 | Perform accumulator draw down test. R | 15 | WHITE | 2023-03-05 | TEST BOP | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1042 | 1042 | Lay down wellhead landing string. R/U cement pumping sub and test lines to 1,500 psi while mixing cement slurry. T | 12 | WHITE | 2023-03-05 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1043 | 1043 | Perform 9-5/8" casing test against ISR and inner casing valve to 250/800 psi for 5/15 mins. | 15 | WHITE | 2023-03-05 | TEST BOP | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.75 | CHAOPHRAYA | SOUTH EAST ASIA
1044 | 1044 | Continue N/U 13-5/8" BOP operations. | 14 | WHITE | 2023-03-05 | N/UP BOP | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1045 | 1045 | Wait on cement for develop to 500 psi compressive strength. Rig activities: - Install casing valve. - Install wear bushing. - N/D BOP f/ setback area. -N/U wellhead riser adaptor. 0D9E:P4T5H IN1TE2R:0V0AL D2.R2I5LL 14 Continue to niFpOplReM uApT BIOONP, overshot and bReOllT nAiRppYle. WExTt.end CTU pisPtUoMn Pto N 9O0 10 psiP.UMP NO 2 PUMP PUMP TOTAL CORE PUMP FROM TO RCEOARME NO. Note: (SHOW CORE RECOVERY) STAPEBELDE BOINT PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT P/U 5" DP. 0 2500 Drill 2400 6.500 65 368.0859 825 3280 Drill CLYST 85%, SST 15%. 120 6000 2500 6.500 65 6.500 65 736.1718 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 890 0.53 116600..33 889.5 4.1 1,365 20.58 119999..1166 1,354.1 89.4 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 13 | WHITE | 2023-03-05 | WAIT ON CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.5 | CHAOPHRAYA | SOUTH EAST ASIA
1046 | 1046 | Wait on cement for develop to 50 psi compressive strength. Rig activities: - M/U 8-1/2" BHA LWD T/C - Derrick management. - Pick up 5" DP. | 13 | WHITE | 2023-03-05 | WAIT ON CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 3 | CHAOPHRAYA | SOUTH EAST ASIA
1047 | 1047 | Continue to mix and pump 159 bbls of 15.5 ppg cement slurry and displace with 50.28 bbls sea water. Cement in place at 04:15 hrs. H Note: G I - 50 psi compressive strength = 03:01 hrs N - 500 psi compressive strength = 05:31 hrs | 12 | WHITE | 2023-03-05 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1 | CHAOPHRAYA | SOUTH EAST ASIA
1048 | 1048 | Drill 5' of new formation from 825' MD to 830' MD. Circulate bottom's up. Sample is 15% clay, 85% cmt. Perform FIT with cement unit at 822' TVD to 99 psi surface pressure (11.5 ppg EMW). Successful FIT. | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.5 | CHAOPHRAYA | SOUTH EAST ASIA
1049 | 1049 | Circulate bottom up at TD and displace well to 9.2 ppg PHPA WBM. Install CTU landing support and land wellhead with shoe at 822' U O MD / 822' TVD. T | 12 | WHITE | 2023-03-05 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1050 | 1050 | Perform 9-5/8" casing test against ISR and outer casing valve to 250/800 for 5/5 mins. 2 | 15 | WHITE | 2023-03-05 | TEST BOP | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1051 | 1051 | Drill 8-1/2" hole from 830' MD to 3,280' MD/ 3,060' TVD. Note: - Drill hole with 9.2 ppg WBM. - Start pump 30 bbls Hi-vis sweep 10.5 ppg every 3 stand at 2,500' TVD to TD. - Max gas while drilling 66u/ 10u @ 2,350' MD/ 2,234' TVD. - Control ROP 720 fph due to LWD logging record data. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 Night Tour Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 7.25 | CHAOPHRAYA | SOUTH EAST ASIA
1052 | 1052 | RIH WITH 5.5'' LOWER COMPLETION ON 5'' DP CONTROL SPEED AS PER BAKER ENGINEER FROM 3299' TO 9 5/8'' CASING O T SHOE @ 7729' | 6 | WHITE | 2023-03-05 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 3.25 | MAIN PASS IV | MENAM
1053 | 1053 | Continue RIH with 6-1/8" AGS BHA on 4" HWDP stands including jar form 89 m-MD to 232 mMD. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1054 | 1054 | Continue to ream casing down with Drill-in 9-5/8" casing with 9.2 ppg WBM (split stream) from 741' MD to 756' MD. P/U 9 5/8" wellhead and continue ream down to TD at 825' MD / 825' TVD. R | 12 | WHITE | 2023-03-05 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.75 | CHAOPHRAYA | SOUTH EAST ASIA
1055 | 1055 | CONT CIRC WHILE MIXING MICRO WASH. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 2.5 | MAIN PASS IV | MENAM
1056 | 1056 | FLUSH ALL SERVICE EQUIP. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1057 | 1057 | FLOW CHECK WELL STATIC. O T | 6 | WHITE | 2023-03-05 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1058 | 1058 | PUMP 2 X 25 BBLS MICRO SPACER & DISPLACE HOLE F/ 82 PCF OBM T/ 82 PCF BRINE W/ 6 BPM 950 PSI ( DUMP R CONTAMINATED BRINE 160 BBLS. U | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 2.5 | MAIN PASS IV | MENAM
1059 | 1059 | RECORD P/U 230K S/O 150K & CIRC UNTIL MUD IN & OUT SAME W/ 4.6 BPM 940 PSI. 2 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 5 | MAIN PASS IV | MENAM
1060 | 1060 | JPJSM RIH W/ 5 1/2" LOWER ON 5" DP F/ 7729' TO SETTING DEPTH @ 10725', MONITOR WELL ON T-T WELL STATIC. | 6 | WHITE | 2023-03-05 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1 | MAIN PASS IV | MENAM
1061 | 1061 | HPJSM, CONT CIRC @ SHOE W/ 5 BPM 840 PSI. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.5 | MAIN PASS IV | MENAM
1062 | 1062 | AT THE SHOE CIRCULATING 1 X BOTTOM UP WITH 5 BPM - 820 PSI IN PROGRESS ...... DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1 | MAIN PASS IV | MENAM
1063 | 1063 | CONNECT TDS WITH 5'' DP AND CIRCULATING 1.5 STRING VOLUME WITH 5 BPM - 530 PSI , WHILE R/D ITS HANDLING R GEAR AND R/UP 5'' HANDLING GEAR . U | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.75 | MAIN PASS IV | MENAM
1064 | 1064 | P/UP AND M/UP 7'' PACKER LINER HANGER ASSY + X - O TO 3299' . 1 | E | WHITE | 2023-03-05 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.5 | MAIN PASS IV | MENAM
1065 | 1065 | CHANGE OUT ELEVATOR TO 5'' . | 23 | WHITE | 2023-03-05 | OTHER3 | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1066 | 1066 | HPJSM , CONT.P/UP AND RIH 5.5'' TUBING + SCREEN LOWER COMPLETION AS PER TALLY FROM FROM 503' TO 3246' . | E | WHITE | 2023-03-05 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 6.75 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 32 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 35 Date: 05-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 6.25 | MAIN PASS IV | MENAM
1067 | 1067 | Continue to nipple up BOP, overshot and bell nipple. Extend CTU piston to 900 psi. Note: P/U 5" DP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | 14 | WHITE | 2023-03-05 | N/UP BOP | SDC | Pre-tour meeting with the crews for Riser less drilling with 9-5/8" CSG lay down and make up BHA, 17. Plug Back Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I 1 BIT 8.50 0.93 SIZE 8.50 WEIGHT T C. Treating E 1 MMTR 7.00 31.17 IADC CODE GRADIENT PL DE.. TSewsatibnbging 4 MWD 6.75 69.46 MANUFACT. BAKER VISCOSITY M 27 HWDP 5.00 828.08 TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL 2,425 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 24 STD. D.P. 5.00 2,278.72 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.71 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 40.00 1 TOTAL 3,280.07 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 160,000 REMARKS: Pre-tour meeting with the crews for make up BHA and RIH. And drilling making connection, and pick TOTAL DAYWORK 0.00 0.00 up 7" casing offline. Service all drilling handling equipment and general housekeeping, KEMS is operational and NO. OF DAYS COM set 10 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 10 Date: 05-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 2.25 | CHAOPHRAYA | SOUTH EAST ASIA
1068 | 1068 | Continue Allow LCM to soak. Mean while monitor well on trip tank.observe losses 60 to 70 bbl | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 5.5 | ACHEIVER | MENAM
1069 | 1069 | Pick up & make up Rih 9-5/8" scraper assy to 154 m. O T | 6 | WHITE | 2023-03-05 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
1070 | 1070 | POOH F/ 10962 ft to 10349 ft while back ream tight spot 200 Gpm 2200 Psi, 150 Rpm 12 - 18K Trq, Dynamic losses 240 bbls/hr | 6 | WHITE | 2023-03-05 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 3 | ACHEIVER | MENAM
1071 | 1071 | WAITING ON LOGISTIC TO DELIVER SOBM CHEMICALS FROM OSV GS DIPTI SINCE 1800HRS ON 05.03.2023. M/W C&C FOR 40 MIN AT INTERVAL OF EVERY 1 HOUR AS PER REQUIREMENT OF HALLIBURTON RSS+LWD TOOLS. (TOTAL CIR. TIME- 2 HOUR) IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | 23 | WHITE | 2023-03-05 | OTHER3 | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 6 | F G MCCLINTOCK | INDIA
1072 | 1072 | PUMP 20 BBLS HI-VIS CIRCULATE OUT TO HOLE CLEAN(GPM800,1940PSI,RPM80/110,TQ 1-2 KFLBS) POOH 12 1/4" O T DIRECTIONAL ASSY F/1709M TO 1653M INSIDE CASING. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
1073 | 1073 | SET PARAMETER DRILLING 12 1/4" HOLE WITH HLB RSS ASSY F/1674.50M TO 1709M.REAM UP & DN PRIOR TO R CONNECTION.TOOK SURVEY AS PER DIRECTIONAL DRILLER. U | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 3.5 | F G MCCLINTOCK | INDIA
1074 | 1074 | BOTTOM UP INSIDE SHOE PRIOR TO DRLLING (GPM750,1780PSI) 2 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
1075 | 1075 | CONTD RIH 12 1/4" RSS + LWD + MWD ASSY ON 5 1/2" DP F / 1423M TO 1674.5 M.(FILL UP EVERY 15 STANDS). WASH/DN LAST STAND. POOH TO 1667M INSIDE SHOE. | 6 | WHITE | 2023-03-05 | TRIPS | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
1076 | 1076 | CONTD RIH 12 1/4" RSS + LWD + MWD ASSY ON 5 1/2" DP F / 186 M TO 1423 M.FURTHER RIH IP.(FILL UP EVERY 15 STANDS). DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 5494 5607 Drill SAND STONE / SHALE 120 10000 1960 6.500 80 6.500 80 800 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 5,527 2.97 112222..0033 5,524.9 5,576 2.45 112244..77 5,573.6 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-05 | TRIPS | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 2 | F G MCCLINTOCK | INDIA
1077 | 1077 | M/ UP 1 STAND 5 1/2" DP & HLB PERFORM DEPTH CALIBRATION. | 20 | WHITE | 2023-03-05 | DIRECTIONAL WORK | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
1078 | 1078 | CONTD RIH 12 1/4" RSS + LWD + MWD BHA F / 36 M TO 186 M.(P/UP & M/UP HLB 8" DLRG JAR)JAR BRT @ 09:00 HRS. | 6 | WHITE | 2023-03-05 | TRIPS | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
1079 | 1079 | HLB LWD LOAD R/A SOURCE IN TOOLS O T | 20 | WHITE | 2023-03-05 | DIRECTIONAL WORK | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
1080 | 1080 | M/UP PUMPING ASSY & SURFACE PRESSURE TEST HLB LWD TOOLS WITH 620 GPM / 825 PSI.R/DN THE TEST ASSY. U | 22 | WHITE | 2023-03-05 | SURFACE TESTING | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
1081 | 1081 | Shallow test AGS/MWD as per DD/MWD instruction with MW 1.28SG SDF 880 lpm, FG 2734 psi, UG 1633 psi. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
1082 | 1082 | CONTD POOH WITH 12 1/4" SLICK BHA F / 112 M TO SURFACE.BREAK OFF & L/DN 12 1/4" BIT & BIT SUB. 1 | 6 | WHITE | 2023-03-05 | TRIPS | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1 | F G MCCLINTOCK | INDIA
1083 | 1083 | MAKE ARRANGEMENT,P/UP AND M/UP HLB 12 1/4" BHA (RSS + LWD + MWD) M/UP PBL SUB & RIH TO 36 M. R | 6 | WHITE | 2023-03-05 | TRIPS | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 4 | F G MCCLINTOCK | INDIA
1084 | 1084 | Test MWD tools 450 - 600 Gpm, 2700 - 3800 Psi, No good signal observed R | 20 | WHITE | 2023-03-05 | DIRECTIONAL WORK | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
1085 | 1085 | Cont Rih with 9-5/8" scraper aasy on 5-1/2" dp F/154 m to 1110 m. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 | 6 | WHITE | 2023-03-05 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1086 | 1086 | Drop SDD dart and activate PBL. Pump 100 bbls 240 ppb LCM pill #13 and displace in annulus.250 gpm 360 psi.(Dynamic looses U O 160 bbls/hr) T | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
1087 | 1087 | Pump 100 bbls 240 ppb LCM pill #14 and displace in annulus.250 gpm 390 psi.(Dynamic looses 156 bbls/hr) H | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
1088 | 1088 | Cont Pooh 8-1/2”bit F/153 m to surface lay down jar, x/o. U | 6 | WHITE | 2023-03-05 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
1089 | 1089 | Flow check- static. Pooh 8-1/2” bit F/1335 m to 153 m. R | 6 | WHITE | 2023-03-05 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1090 | 1090 | Pumped hi-vis & circulated till hole clean. 2 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
1091 | 1091 | Cont drill cmt plug F/1283 m to 1335 m. (drill para: gpm: 515/380 psi, wob-45 k, rpm-60 & torque: 7-8 kft/lbs) pumped hi-vis after every stand drilled. | 3 | WHITE | 2023-03-05 | REAMING | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 4.5 | PARAMESHWARA | INDIA
1092 | 1092 | set para. cleared cmt f/1200 m to 1283 m. pumped hi-vis in every std. (para: gpm-500, press-400 psi, rpm-60, torq-7-8k, wob- 4-6k). U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 3 | WHITE | 2023-03-05 | REAMING | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 5 | PARAMESHWARA | INDIA
1093 | 1093 | tested casing on cmt @1500 psi ok. R | 15 | WHITE | 2023-03-05 | TEST BOP | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
1094 | 1094 | pump 20 bbls hi-vis & circ bottom up @ 1200m , gpm-400, press-250. 1 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
1095 | 1095 | further rih, obsd cmt patches & w/dn f/780 to 1200m. tagged cmnt plug @1200m. circ prior to cmnt plug testing ip. | 6 | WHITE | 2023-03-05 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 4 | PARAMESHWARA | INDIA
1096 | 1096 | set para. cleared cmt f/761 m to 780 m. pumped hi-vis after every std. (para: gpm-500, press-300 psi, rpm-25/35, torq-5k, wob- 3-4k.) | 3 | WHITE | 2023-03-05 | REAMING | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-500. 18. Squeeze Cement Wash pipe hours: 255 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 12:00 18:00 23:30 I 1 BIT 8.50 0.82 SIZE WEIGHT 8.60 8.60 8.60 T C. Treating E 1 SCRAP 9.63 3.64 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 BS 6.50 3.02 MANUFACT. VISCOSITY 32 32 32 M 3 DC 6.50 89.21 TYPE PV/YP / / / O F. Other 4 1 XO 7.00 3.48 SERIAL NO. GELS / / / C G. Other 5 9 HWDP 5.50 276.05 JETS FL. LOSS H. Other 6 1 XO 7.00 2.33 TFA pH TOTALS 12.00 12.00 1 JAR 6.50 29.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 2.92 DEPTH IN 2 (OFFICE USE ONLY) 3 HWDP 5.50 92.49 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.66 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 33 STD. D.P. 5.50 3,135.27 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 3,641.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-503. NO. OF DAYS Wash pipe hours: 255 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 25 Date: 05-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1097 | 1097 | POOH w/ 8-1/2" DIR BHA F/ 10349ft to 3952, Observed Losses 50 bbls/hr U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | 6 | WHITE | 2023-03-05 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2.5 | ACHEIVER | MENAM
1098 | 1098 | Flow check well on Trip tank Static losses 50 bbls/hr, Install pneumatic slips R | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
1099 | 1099 | Allow LCM to soak. Mean while monitor well on trip tank.observe losses 50bbls to 55 bbls / hour 2 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2 | ACHEIVER | MENAM
1100 | 1100 | Pump 100 bbls 280 ppb LCM pill #15 and displace in annulus.250 gpm 390 psi.(Dynamic looses 120 bbls/hr) | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.75 | ACHEIVER | MENAM
1101 | 1101 | Allow LCM to soak. Mean while monitor well on trip tank. G I N DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
1102 | 1102 | Allow LCM to soak mean while F/C Observe looses 120 bbls/hr drop to 84 bbls/hr.Pump 10 bbls 74 pcf through string every 15 mins, T | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 0.50 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 4.1 TIME 23:03 I 1 BIT 8.50 0.80 SIZE 8.50 WEIGHT 10.00 T C. Treating E 3 AUTOTR 8.38 26.40 IADC CODE M223 GRADIENT 0.519 PL DE.. TSewsatibnbging 4 ONTRAK 8.38 38.90 MANUFACT. BHI VISCOSITY 68 M 1 STAB 8.38 5.98 TYPE U616 PV/YP / O F. Other 4 3 OTHER 6.75 24.31 SERIAL NO. 64146 GELS / C G. Other 5 1 XO 6.75 3.70 JETS 6x14 FL. LOSS H. Other 6 2 HWDP 5.00 60.63 TFA 0.902 pH TOTALS 12.00 12.00 1 XO 6.75 2.40 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 6.75 30.39 DEPTH IN 10,349 2 (OFFICE USE ONLY) 1 XO 6.75 2.40 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 5.00 90.82 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 106 STD. D.P. 5.00 10,001.44 CUTTING STRUCTURE caustic soda 4 xc polymer 10 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 62.81 INNER OUTER DULL CHAR. LOCATION pac l 10 mlntreat 60 HOURS STANDBY KELLY DOWN mc.seal f 40 mc.seal m 180 2 TOTAL 10,350.98 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 47 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 50 Date: 05-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 5.5 | ACHEIVER | MENAM
1103 | 1103 | Con't RIH with 6-1/8" AGS BHA on 4" DP ( Inside 7" CSG shoe ) from 232 mMD to 2546mMD. 1 | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 2 | ENTERPRISE | MENAM
1104 | 1104 | Continue to Drill ahead 12-1/4" hole directional from 8964 ft-MD to 9341 ft-MD, as per DD instruction with 760 gpm, 4094 psi, 120 rpm, 21-22 torque , 15-25kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 340k, s/o wt-220k, Rot-wt 260k 10.8 ppg. ( INC-66.5, AZI-302.54) NOTE; Performed kick drill and flow check ( Well 2 static at 9038 ft ) R | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 22:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 79 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.23 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 6,822 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 92 DP 5.00 8,846.00 TOTAL HRS 111.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE lime 20 soltex 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caco3 20 HOURS STANDBY KELLY DOWN TOTAL 9,629.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 340,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 21 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 KPI on slip & cut. NA KPI on slip to slip connection time: 6/7mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 7 | MENTOR | WEST AFRICA
1105 | 1105 | Con't RIH with 6-1/8" AGS BHA on 4" DP ( Open hole) from 2546 mMD to 3200mMD. U | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.75 | ENTERPRISE | MENAM
1106 | 1106 | CIRCULATE OPEN HOLE VOLUME FLOW CHECK STATIC. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.5 | HIGH ISLAND II | MENAM
1107 | 1107 | RIH TO 5500' @ 25 FPM. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
1108 | 1108 | CONTINUE BKR LOGGING RUN #5: COLLECT SAMPLE @ 5245 FT O T -MONITOR WELL ON TRIP TANK. STATIC. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.5 | HIGH ISLAND II | MENAM
1109 | 1109 | HELD SAFETY STAND DOWN MEETING, DISCUSSED: SWA, PJSM, LIFTING OPERATIONS, SLIP/TRIP HAZARDS, 1 SUPERVISION DURING CREW CHANGE. HAND & FINGERS INJURIES. R -MONITOR WELL ON TRIP TANK. STATIC. U | 23 | WHITE | 2023-03-05 | OTHER3 | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
1110 | 1110 | BKR LOGGING RUN #5: COLLECT SAMPLE @ 5245 FT -MONITOR WELL ON TRIP TANK. STATIC. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
1111 | 1111 | POOH W/ BKR LOGGING RUN # F ON 5" DP TO 4221'. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.25 | HIGH ISLAND II | MENAM
1112 | 1112 | Rig down Lubricator in mouse hole. Break and lay out Greaser head with sheaves. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | E | WHITE | 2023-03-05 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1.5 | TENACIOUS | WEST AFRICA
1113 | 1113 | SLB Slick line RIH with 2.25'' LIB and take impression at HUD at 6082ft. Jar down 10times and POH to surface. O T | E | WHITE | 2023-03-05 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 3.25 | TENACIOUS | WEST AFRICA
1114 | 1114 | SLB Slick line M/u GS tool string. RIH and retrieve isolation sleeve at 5917ft. POH to surface. U | E | WHITE | 2023-03-05 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
1115 | 1115 | SLB Slick line RIH with 2.25'' LIB and take impression at HUD at 6082ft. POH to surface. R | E | WHITE | 2023-03-05 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 2 | TENACIOUS | WEST AFRICA
1116 | 1116 | Fill up PCE and pressure test 250/3500psi 5/5mins. 2 | E | WHITE | 2023-03-05 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
1117 | 1117 | Held PJSM. Rig up SLB Slick line. M/u 2.25'' LIB with 2.68'' Centralizer tool string. | E | WHITE | 2023-03-05 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
1118 | 1118 | Held PJSM with crew. Skid and transverse to A04. | 1 | WHITE | 2023-03-05 | RIG UP & TEAR DOWN | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
1119 | 1119 | Close crown valve. SLB Slick line break tool string and inspect LIB. | E | WHITE | 2023-03-05 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.00 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 34 Date: 05-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
1120 | 1120 | UNLATCH & POOH BKR WIRELINE TO SURFACE. R/D SES | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.75 | HIGH ISLAND II | MENAM
1121 | 1121 | CIRC & CONDITION OBM THRU FULLY OPENED CHOKE. F/C: STATIC | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.75 | HIGH ISLAND II | MENAM
1122 | 1122 | POOH W/ BKR LOG TOOLS ON 5'' DP @ CONTROLLED SPEED. F/C: STATIC FROM 4221' TO 415 | 6 | WHITE | 2023-03-05 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2.75 | HIGH ISLAND II | MENAM
1123 | 1123 | WAITING ON LOGISTICS . MEAN WHILE CONT'D SEA FASTENING & SECURING FOR RIG MOVE. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-05 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. 17. Plug Back TBSM PRIOR TO JETTING ON STBD LEGS. 18. Squeeze Cement U/IBOP ---------3796 FUNCTIONS. 19. Fishing WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 20. Directional Work SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 21. Run/Retrieve Riser Equip. CHECKED COM, DLA, CMF – OK. 22. Surface Testing 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 TBSM PRIOR TO JETTING ON STBD LEG. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 5 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD LEGS. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD LEG. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 5 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 5 Date: 05-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 12 | TRIDENT II | INDIA
1124 | 1124 | WAITING ON LOGISTICS FOR TUG BOATS,M/W,RIG MOVE PREPARATION IIP. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 5 Date: 05-Mar-23 | 1 | WHITE | 2023-03-05 | RIG UP & TEAR DOWN | T02 | HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. 17. Plug Back TBSM PRIOR TO JETTING ON STBD LEGS. 18. Squeeze Cement U/IBOP ---------3796 FUNCTIONS. 19. Fishing WASH PIPE--923HRS (CHANGED ON 07-OCT-22) 20. Directional Work SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) 21. Run/Retrieve Riser Equip. CHECKED COM, DLA, CMF – OK. 22. Surface Testing 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. TOTAL DAYWORK 0.00 0.00 TBSM PRIOR TO JETTING ON STBD LEG. NO. OF DAYS U/IBOP ---------3796 FUNCTIONS. 0 FROM SPUD WASH PIPE--923HRS (CHANGED ON 07-OCT-22) CUMULATIVE SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) ROTATING HOURS CHECKED COM, DLA, CMF – OK. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/J A DRR-1IHLL,4E-R3/:4"D/JAR(2018201811)--180 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 5 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD LEGS. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS Operations Activities (Continued...) HELD PJSM PRIOR TO JACK DOWN HULL TO 17" FT DRAFT TO CHECK WATER INTEGRITY. TBSM PRIOR TO JETTING ON STBD LEG. U/IBOP ---------3796 FUNCTIONS. WASH PIPE--923HRS (CHANGED ON 07-OCT-22) SAVER SUB --613 CONNECTIONS. (CHANGED ON 02-DEC-22) CHECKED COM, DLA, CMF – OK. 8"D /JAR 20288H -- 22 HR,6 1/2"D /JAR 20279 --84 HRS.6-1/2" HYD D/JAR-1H,4-3/4"D/JAR(2018201811)--180 HRS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 5 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T02 Job:T02-23-2 N19-2Z Rpt No: 5 Date: 05-Mar-23 | T02-23-2 N19-2Z | N19-2Z | Mar-23 | 12 | TRIDENT II | INDIA
1125 | 1125 | CONTD M/UP PBL SUB & TEST PBL, ACTIVATE @ 150 PSI,DEACTIVATE @ 2500 PSI.RETRIEVE BALLS, B/OFF & L/DN PBL SUB AND TEST ASSY. | 6 | WHITE | 2023-03-05 | TRIPS | FGM | HELD PJSM ABOUT ACTIVATE PBL SUB .TBSM PRIOR TO P/UP & M/UP 12 1/4" RSS BHA. 17. Plug Back SAVER SUB :- HT-55 - 108 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 108 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 1.50 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing 0.50 DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:50 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 9.90 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.5138 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 112 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 2 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 51 STD. D.P. 5.50 4,811.48 CUTTING STRUCTURE GELTONE 1 BARITE 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 5,423.23 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 218,000 REMARKS: HELD PJSM ABOUT RUNNING IN HOLE 12 1/4" RSS ASSY.TBSM PRIOR TO DRILLING TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 111 CONNECTIONS NO. OF DAYS WASH PIPE :- 113 HRS. 31 FROM SPUD 13 5/8" ANN :- 2 C/O HELD PIT DRILL CUMULATIVE 28 21 1/4'' ANN :- 4 C/O ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 31 Date: 05-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 1.5 | F G MCCLINTOCK | INDIA
1126 | 1126 | P/U & M/U 13-5/8" DELTA BOP TEST PLUG ASSY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | 15 | WHITE | 2023-03-05 | TEST BOP | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
1127 | 1127 | HELD PJSM FOR BOP PRESSURE TEST. | 15 | WHITE | 2023-03-05 | TEST BOP | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
1128 | 1128 | CLEANED & CLEARED RF. | 6 | WHITE | 2023-03-05 | TRIPS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
1129 | 1129 | L/D BKR WL VSP TOOLS & R/D BKR WL EQUIPT'S. *MONITOR WELL ON TRIP TANK. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.25 | HIGH ISLAND II | MENAM
1130 | 1130 | HELD PJSM TO LD BKR W/L TOOLS RUN #6. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
1131 | 1131 | BKR RECORD VSP DATA F/ 7475' UP TO SURFACE. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 4.5 | HIGH ISLAND II | MENAM
1132 | 1132 | RIH BKR WL RUN #6 TOOLS. O T | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1.25 | HIGH ISLAND II | MENAM
1133 | 1133 | HELD SAFETY STAND DOWN MEETING WITH RIG CREWS AND THIRD PARTY. DISCUSSED STOP WORK AUTHORITY, R WORKING AT HEIGHT, DROP OBJECTS, HAND INJURIES AND LIFESAVING RULES. U | 23 | WHITE | 2023-03-05 | OTHER3 | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.5 | HIGH ISLAND II | MENAM
1134 | 1134 | M/U BKR WL RUN #6 VSP.CHECKED LOGGING TOOLS AT SURFACE. 2 | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 1 | HIGH ISLAND II | MENAM
1135 | 1135 | HELD PJSM TO MU BKR W/L TOOLS RUN #6 VSP. | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
1136 | 1136 | SECURE SAMPLES. L/D BKR WL TOOLS (GR/RCX/WGI). | 11 | WHITE | 2023-03-05 | WIRELINE LOGS | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 2 | HIGH ISLAND II | MENAM
1137 | 1137 | HELD PJSM TO LD BKR W/L TOOLS RUN #5 DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-05 | OTHER3 | HI2 | NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, 17. Plug Back CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. 18. Squeeze Cement INSPECT & FUNCTION TEST LINK TILT ALARM. 19. Fishing DAILY CHECK. 20. Directional Work PJSM: WIRE LINE OPS WITH 5'' D/P. 21. Run/Retrieve Riser Equip. PJSM:GENERAL MAINTENANCE . 22. Surface Testing PJSM: SHIPPING AND BUFFING SAND TRAP AREA . DRILLER: 23. Other 3 0.75 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 15:00 I SIZE WEIGHT 11.60 T C. Treating E IADC CODE GRADIENT 0.602 L D. Swabbing MANUFACT. VISCOSITY 85 P E. Testing M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, TOTAL DAYWORK 0.00 0.00 CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. NO. OF DAYS INSPECT & FUNCTION TEST LINK TILT ALARM. 38 FROM SPUD DAILY CHECK. CUMULATIVE 124 PJSM: WIRE LINE RIG UP AND DOWN . ROTATING HOURS PJSM:GENERAL MAINTENANCE . DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 59,036.00 * PREPARE 9-5/8'' PUP JTS WITH MLS. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 Tour 2 Remarks (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE OPS WITH 5'' D/P. PJSM:GENERAL MAINTENANCE . PJSM: SHIPPING AND BUFFING SAND TRAP AREA . PJSM:POOH 5'' DP WITH WIRE LINE . PJSM:R/D WIRE LINE SHEAVE & TOOLS TRIP DRILL: SECURE WELL IN 42 SEC. PIT DRILL:SECURE WELL IN 37 SECS. Operations Activities (Continued...) NSPECT DRAW WORKS AND DRILL LINE. CAD UNIT BOP AND WELL CONTROL EQUIP, CHECKED COM & KEMS, INSPECT STABBING BOARD ALARMS AND LIGHT ENSURE BOTH ARE WORKING. INSPECT & FUNCTION TEST LINK TILT ALARM. DAILY CHECK. PJSM: WIRE LINE RIG UP AND DOWN . PJSM:GENERAL MAINTENANCE . * PREPARE 9-5/8'' PUP JTS WITH MLS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI2 Job:SFNY 1750 Rpt No: 38 Date: 05-Mar-23 | SFNY 1750 | SFNY 1750 | Mar-23 | 0.25 | HIGH ISLAND II | MENAM
1138 | 1138 | Function test MWD tools as per MWD instruction with MW 1.28 SG SDF 753 lpm, 1857-2453 psi. R | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
1139 | 1139 | Make up and rack back 1x stand 5" DP. Break down and lay out as per IAT test. Assist deck crew with cargo management and loading tubulars on deck. Continue seafastening in pumproom pitroom and start in Sackroom. 2 Prep HCR from sackroom to maindeck. R Move 2nd HCR from quayside to maindeck. U Pick up DC's and rack back, break down and lay out as per IAT. O T Assist deck crew with offload tubulars from barge to maindeck. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 93 Date: 05-Mar-23 | 23 | WHITE | 2023-03-05 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 93 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 93 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 93 Date: 05-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
1140 | 1140 | Con't POOH with 6-1/8" AGS BHA from 232 m-MD to surface. O T | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1 | ENTERPRISE | MENAM
1141 | 1141 | Flow check prior to POOH BHA, well static. U | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1142 | 1142 | Continue POOH with AGS BHA F/ 2546 m-MD T/ 232 m-MD. 2 Note : pulling wet R | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 3.5 | ENTERPRISE | MENAM
1143 | 1143 | Flow check, well static. Perform trip drill with crew stab in FOSV and secure well in 26 sec. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1144 | 1144 | Continue POOH 6-1/8" BHA (AGS/MLWD) with 4" DP from 3156 m to 2546 m inside casing shoe. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.25 | ENTERPRISE | MENAM
1145 | 1145 | Continue POOH 6-1/8" BHA (AGS/MLWD) with 4" DP from 3359 m to 3156 m. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1146 | 1146 | Unload RA source | 20 | WHITE | 2023-03-05 | DIRECTIONAL WORK | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1147 | 1147 | Pump slug 30 bbls and follow by with 1.32 SG SDF 10 bbls. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1148 | 1148 | Flow check well. Well static. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1149 | 1149 | Troubleshoot AGS BHA . Observed minimal pressure. Rack back 4" DP 1 stand to derrick and Cycle AGS as per DD instruction. Circulate hole clean with MW 1.32SG SDF, 889 lpm, 3205-3220 psi, 100 rpm, TQ: 10-11 kft-lbs, | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 2 | ENTERPRISE | MENAM
1150 | 1150 | Drilling 6-1/8" hole (AGS/MLWD) from 3561 mMD to 3648 mMD, 2474.86 mTVD with 1.32 SG SDF, 889 lpm, 3220-3260 psi, 190 rpm, tq 10-13 kft-lbs, WOB 10-14 klbs as per DD/MWD instruction. P/U 396 klbs, S/O 163 klbs, R/T 225 klbs. | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 3.25 | ENTERPRISE | MENAM
1151 | 1151 | Make up TDS fill up string. Ream down 6-1/8" BHA (AGS/MWD) MWD log down to bottom with speed 110 m/hr. from 3532 m to 3561m with 740 lpm, 2470 psi, 100 rpm, TQ: 8 - 10 klbs-ft. | 3 | WHITE | 2023-03-05 | REAMING | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.75 | ENTERPRISE | MENAM
1152 | 1152 | Con't RIH with 6-1/8" AGS BHA on 4" DP ( Open hole) from 3200 mMD to 3532mMD. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1153 | 1153 | Function test MWD tools as per MWD instruction with MW 1.28 SG SDF 741lpm, 2320 psi. O T | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1154 | 1154 | POOH 6-1/8" BHA (AGS/MLWD) with 4" DP from 3648 m to 3359 m. Hole take correct displacement. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.75 | ENTERPRISE | MENAM
1155 | 1155 | Break out drill bit, Plug in MWD cable, break out AGS assy and L/D, Rack back M/LWD BHA | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
1156 | 1156 | P/U new AGS, bit. Make up AGS and bit. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1 | ENTERPRISE | MENAM
1157 | 1157 | C/O LWD ADL tool. Download program and test tool. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 2.25 | ENTERPRISE | MENAM
1158 | 1158 | Continue Drilling 12-1/4" hole directional from 9341 ft-MD to 9629 ft-MD, as per DD instruction with 760 gpm, 4094 psi, 120 rpm, 21- U 22 torque , 15-27kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. O T Up-wt 340k, s/o wt-210k, Rot-wt 260k 10.8 ppg. ( INC-72.51, AZI-302.54) IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 22:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 79 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.23 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 6,822 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 92 DP 5.00 8,846.00 TOTAL HRS 111.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE lime 20 soltex 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caco3 20 HOURS STANDBY KELLY DOWN TOTAL 9,629.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 340,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 21 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 KPI on slip & cut. NA KPI on slip to slip connection time: 6/7mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 5 | MENTOR | WEST AFRICA
1159 | 1159 | Continue to Drill ahead 12-1/4" hole directional from 8743 ft-MD to 8964 ft-MD, as per DD instruction with 800 gpm, 4357 psi, 120 rpm, 21-22 torque , 15-25kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 340k, s/o wt-220k, Rot-wt 260k 10.8 ppg. ( INC-55.34, AZI-302.74) DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 2 PUMP NO 3 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 8964 9629 Drill shale 170 20000 6.500 68 6.500 68 771.7 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 9,273 66.5 330088..5588 7,848.3 9,369 69.76 330088..5588 7,884.1 9,438 72.51 330077..5588 7,906.4 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 22:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 79 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.23 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 6,822 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 92 DP 5.00 8,846.00 TOTAL HRS 111.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE lime 20 soltex 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caco3 20 HOURS STANDBY KELLY DOWN TOTAL 9,629.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 340,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 21 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 KPI on slip & cut. NA KPI on slip to slip connection time: 6/7mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 5 | MENTOR | WEST AFRICA
1160 | 1160 | Drill ahead 12-1/4" hole directionally from 8506 ft-md to 8743 ft-md, as per DD instruction with 800 gpm, 4353 psi, 120 rpm, 18-20 O T torque , 15-20kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up- wt 340k, s/o wt-220k, Rot-wt 260k. | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 22:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 79 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.23 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 6,822 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 92 DP 5.00 8,846.00 TOTAL HRS 111.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE lime 20 soltex 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caco3 20 HOURS STANDBY KELLY DOWN TOTAL 9,629.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 340,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 21 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 KPI on slip & cut. NA KPI on slip to slip connection time: 6/7mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 4 | MENTOR | WEST AFRICA
1161 | 1161 | Run back to bottom from 8282 ft-md to 8506 ft-md U | 8 | RED | 2023-03-05 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 22:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 79 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.23 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 6,822 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 92 DP 5.00 8,846.00 TOTAL HRS 111.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE lime 20 soltex 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caco3 20 HOURS STANDBY KELLY DOWN TOTAL 9,629.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 340,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 21 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 KPI on slip & cut. NA KPI on slip to slip connection time: 6/7mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.5 | MENTOR | WEST AFRICA
1162 | 1162 | R/D pump-in assembly and carry out tests on installed TDS wash pipe as per OEM work instructions, OK. Carry out physical checks 1 with man rider, OK. R | 8 | RED | 2023-03-05 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 22:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 79 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.23 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 6,822 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 92 DP 5.00 8,846.00 TOTAL HRS 111.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE lime 20 soltex 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caco3 20 HOURS STANDBY KELLY DOWN TOTAL 9,629.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 340,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 21 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 KPI on slip & cut. NA KPI on slip to slip connection time: 6/7mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1 | MENTOR | WEST AFRICA
1163 | 1163 | Rack back additional 2 stds in derrick, M/U circulating sub and continue circulating well with 300 gpm, 815 psi while changing out TDS wash pipe. | 8 | RED | 2023-03-05 | REPAIR RIG | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 22:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY 79 M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.23 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 6,822 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 92 DP 5.00 8,846.00 TOTAL HRS 111.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE lime 20 soltex 20 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caco3 20 HOURS STANDBY KELLY DOWN TOTAL 9,629.90 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 340,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 21 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 8 (hrs left 292) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 8 KPI on slip & cut. NA KPI on slip to slip connection time: 6/7mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 10hrs (282 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 18 KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: N/A KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 22 Date: 05-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.5 | MENTOR | WEST AFRICA
1164 | 1164 | Daily rounds and checks. R NDOR readings. U Pot water tested & recorded. O T Completed drain project for pumps in utility room. Housekeeping In Engineroom. Reserve Pit Rooms & Pump room has been cleaned. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 6 Date: 05-Mar-23 | 23 | WHITE | 2023-03-05 | OTHER3 | SDF | Continue with shipyard work scope. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 6 Date: 05-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1165 | 1165 | Continue cleaning and servicing slips, dog collars and tongs. Continue mapping in T/T and sand traps. Start disassembling ST 160. 2 | 23 | WHITE | 2023-03-05 | OTHER3 | SDF | Continue with shipyard work scope. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 6 Date: 05-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1166 | 1166 | Clean and check handling equipment slips / dog collars etc. O T Assist technical department with needle gunning in water maker room. House keeping and cleaning all areas. Make preparations to start disassembling ST160. PM's. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-05 | OTHER3 | SDF | Continue with shipyard work scope. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 6 Date: 05-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1167 | 1167 | Continue with slip and cut tool box inventory. Clean, grease and apply denso tape on X/O's on cantilever. Continue with suction valves O'ring change out. 1 Continue with mapping T/T and sand traps. R Look on catalogue for 4" handling equipment. U | 23 | WHITE | 2023-03-05 | OTHER3 | SDF | Continue with shipyard work scope. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Continue with shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 6 Date: 05-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1168 | 1168 | Con't RIH with 6-1/8" AGS BHA on 4" DP ( Inside 7" CSG shoe ) from 232 mMD to 492mMD. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1169 | 1169 | Shallow test AGS/MWD as per DD/MWD instruction with MW 1.32SG SDF 700 lpm, FG 1810 psi, UG 1180 psi. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
1170 | 1170 | Pick up and make up 6-1/8” BHA (AGS + M/LWD/PWD). Make up bit and load radioactive source. RIH with 6-1/8" AGS BHA on 4" HWDP stands including jar to 232 m-MD. | 6 | WHITE | 2023-03-05 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 0.25 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.5 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 6.13 WEIGHT 11.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.5709 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV NOV VISCOSITY 68 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 TKC46-F1 PV/YP 23/14 O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. A272719 S287640 GELS 10/15 C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 4x12 FL. LOSS H. Other 6 TFA 0.442 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 11,969 SOLIDS 13.7 DAYWORK TIME SUMMARY DEPTH IN 11,683 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 285 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 761.35 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 7 FROM SPUD Stop the job if unsafe CUMULATIVE 56 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 9 Date: 05-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1 | ENTERPRISE | MENAM
1171 | 1171 | Torque up the BOP double to 3292ft-lbs. Carry out integrated acceptance test on the mud mixing, transfer and storage systems. Carry out running equipment daily checks.Troubleshoot for koomey unit triplex pump No.1 and No.2 due to loss suction. Continue transfer R engine oil M 154 to storage tank in engine room. Change lube oil filter for engine #4. Clean air line supply to diverter panel’s air tank. U O Flushing R/O unit. Continue check spare part for engine#1. Troubleshoot for hytorc unit. Trouble for purifier #1 House keeping in air T compressor room. Plan jobs for Tomorrow/ Tomorrow Night. 1000 hrs.PM for engine#1. Pressure test for sea water and drill water line. T 90 days PM for all jacking gear boxes. Assist for install fixation rack. 180 days PM for fuel purifier#1 H G I N DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-05 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 93 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 93 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 93 Date: 05-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
1172 | 1172 | PUMP HIVIS C & C MUD WITH 500GPM/1512 PSI. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1 | RON TAPPMEYER | INDIA
1173 | 1173 | CONTD M/UP 12-1/4” HLB RSS MWD BHA & RIH UP TO 180M. P/UP 8” D/JAR ( RSS, MWD BRT- 1800HRS & JAR BRT- 18:30HRS). | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
1174 | 1174 | SHALLOW TEST AT GPM-750, PR-1150PSI , | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
1175 | 1175 | M/UP 12 ¼” PDC BIT WITH HLB RSS-MWD ASSY.PLUG-IN & TOOL PROGRAMMING. O T | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
1176 | 1176 | FLUSH LINES & TEST BOTH MUD PUMP GATE VALVES SEPARATELY AT 2000 PSI. FOUND OK. U | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
1177 | 1177 | CONTINUE CHECK VALVES OF MP#1. OBSD BLEED OFF GATE VALVE BODY WASHED OUT.REPLACED SAME. OBSD DISCHARGE GATE VALVE SEAT OF M/P#1 WASHED OUT.REMOVED BROKEN PIECES & REPLACED SEAT & GATE.CHECK RIG FLOOR STANDPIPE VALVE-OK.M/W P/UP & M/UP HLB TM COLLAR, F/SUB, B/OFF 12 ¼” PDC BIT AND RACK BACK ON 2 DERRICK. R | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 4 | TRIDENT XII | INDIA
1178 | 1178 | B/OFF & L/DN 1X5-1/2'' DP, X/OVER, FLOAT SUB & TM COLLAR UP TO 15 M. CHECK VALVES OF MP#1. OBSD BLEED OFF GATE VALVE BODY WASHED OUT.REPLACING SAME I.P. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 3812 3934 Drill SHALE 140 8000 2100 6.500 83 6.500 83 858.718 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2 | TRIDENT XII | INDIA
1179 | 1179 | RIH 12-1/4” HLB RSS MWD ASSY ON 5-1/2” DP F/180M TO 1125M. FILL STRING EVERY 15 STDS. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
1180 | 1180 | M/UP 12¼” BIT AND CHECKED THE PRESS AGAINST THE HYDRAULIC FLOW CHART ONE PUMP AT A TIME (GPM-500, PR- 250 PSI). START BOTH M/P GPM-750, PR-600 PSI. NOT MATCHING WITH HYDRAULICS. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
1181 | 1181 | HLB PLUG-IN & DOWNLOADED DATA. OPEN BOTH MUD PUMP FLUID ENDS, SUCTION & DISCHARGE STRAINER FOUND OK. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
1182 | 1182 | B/OFF AND CHECKED FLOAT SUB & MWD TOOL FOUND OK. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
1183 | 1183 | SHALLOW TESTED MWD TOOLS AT GPM-750, PR-600 PSI. (BELOW HYDRAULIC FLOW CHART). | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
1184 | 1184 | F/C, STATIC. POOH WITH HLB RSS/MWD BHA WET F/102M TO SURFACE. OBSD GATE VALVE HOUSING ELEMENT (APPROX.- O T 4INCH) INSIDE THE FLOAT SUB. RECOVERED SAME. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
1185 | 1185 | F/C WELL STATIC. POOH WITH BHA WET F/179 M TO 102 M. L/DN D/JAR (JAR ART 0600HRS). U | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
1186 | 1186 | CONTD POOH WET 12-1/4’’ HLB RSS+MWD ASSY F/1130 M TO 179 M WITH VISUALLY CHECK STRING & PUMP DN & CIRC IN 1 STRING AFTER POOH EVERY 5 STANDS.OBSD NO VISUAL LEAKAGE. R | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 3.5 | TRIDENT XII | INDIA
1187 | 1187 | B/OFF 12 ¼” PDC BIT, M/UP TDS AND FLUSHED MWD TOOLS. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 0.5 | TRIDENT XII | INDIA
1188 | 1188 | GEL BREAK FOR 15 MIN AT 900 GPM. ORIENT TOOLS FACE TO 22 DEG LEFT. PASS THRU WINDOW WITH 500 GPM & 10 KIPS WOB. CONT W/DN UPTO 1162 M (BOTTOM). | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
1189 | 1189 | SET PARAMETERS AND DRLG 12-1/4" DIR HOLE WITH HLB RSS+MWD ASSY F/ 1162 TO 1199 M. REAM ONCE, PUMP 20 BBL HI-WT PILL EVERY STAND DRILLED & TAKE SURVEY AS REQUIRED. DRILLING PARAMETERS - 850 GPM, 2100 PSI, 140 RPM, TORQUE 5/6 K. WOB 10/12 KIPS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 2.5 | TRIDENT XII | INDIA
1190 | 1190 | HELD SAFETY STAND DOWN MEETING. R | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1191 | 1191 | CONTINUE TO PICK UP 4'' DRILL PIPE AND RIH FROM 6823 FT TO 7100 FT. 2 | 6 | WHITE | 2023-03-05 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1192 | 1192 | WASH DOWN 6 JOINTS FROM 6823 FT TO 7011 FT WITH 200 GPM AND 700 PSI. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1193 | 1193 | CONTINUE TO PICK UP 4'' DRILL PIPE AND RIH FROM 6444 FT TO 6823 FT. | 6 | WHITE | 2023-03-05 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1194 | 1194 | PICK UP AND RIH WITH 4" DP ON 6 1/8" CLEAN OUT ASSY FROM 591 FT TO 6444 FT DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-05 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 6 | HIGH ISLAND IV | MENAM
1195 | 1195 | PICK UP AND RIH WITH 4" HWDP FROM 192 FT TO 591 FT , PICK UP DRILLING JAR | 6 | WHITE | 2023-03-05 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1196 | 1196 | PICK UP AND MAKE UP 6 1/8" BIT WITH 4 3/4" D.C TO 192 FT | 6 | WHITE | 2023-03-05 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1197 | 1197 | HELD PJSM WITH CREW FOR PICK UP 6 1/8" BHA | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1198 | 1198 | CHANGE OUT HANDLING EQUIPMENT TO 4" | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1199 | 1199 | CLEAN AND CLEAR RIG FLOOR O T | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1200 | 1200 | POH WITH CUP TESTER ASSY AND LAY DOWN SAME U | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1201 | 1201 | PRESSURE TEST X2 CASING VALVES TO 300 PSI LOW AND 2400 PSI HIGH R | 15 | WHITE | 2023-03-05 | TEST BOP | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1202 | 1202 | PERFORM SAFETY STAND DOWN MEETING 1 | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1203 | 1203 | PICK UP AND MAKE UP CUP TESTER ASSY | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1204 | 1204 | POH WITH TEST PLUG ASST AND LAY DOWN SAME | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
1205 | 1205 | CONTINUE TO PICK UP 4'' DRILL PIPE AND RIH FROM 7100 FT TO 10036 FT. PICK UP 300 JOINTS OF 4'' DRILL PIPE. U | 6 | WHITE | 2023-03-05 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.75 | HIGH ISLAND IV | MENAM
1206 | 1206 | Connect all the hoses on pipe handler. O T Change out spacer on pipe handler and install drilling spacer. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 | 23 | WHITE | 2023-03-05 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
1207 | 1207 | Work with mechanic on installation of TDS blower. 1 Rig up rig tongs & intensifier and make up TDS main shaft, upper, lower IBOP and saver sub to required torque. R Carry out house keeping around the Rig floor. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-05 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
1208 | 1208 | POOH 3 1/2'' stinger from 1430m to 304m. L/D 2 x cross over. 2 | 6 | WHITE | 2023-03-05 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.75 | BALTIC | WEST AFRICA
1209 | 1209 | Line up and pumped 6m3 of 1.80sg slug. with 597 lpm, 161 psi. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1210 | 1210 | Continue toPerformed Derrick management. | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2 | BALTIC | WEST AFRICA
1211 | 1211 | Continue to POOH 3 1/2'' stinger assy from 1575m to 1430m. Lay down ( Note; Slug didnt hold) 1D1E:P3T0H IN1TE1R:4V5AL D0.R2I5LL 22 Changed out 5F O1R/2M'' AdTpI OeNlevator to 5''dp eleRvOaTtoArR.Y WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP 1F1R:O45M 12:T0O0 R0C.EO2AR5ME N2O3. Perform(SeHd ODWe rCriOckR Em RaEnCagOeVmEReYn)t. STAPEBELDE BOINT PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-05 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1212 | 1212 | Slug pipe with 2m3 of 1.80 sg heavy pill and displace surface line with 2m3 og 1.50 RDF. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1213 | 1213 | POOH 3 1/2'' stinger assy wet on elevator from 1750m to 1575m. | 6 | WHITE | 2023-03-05 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1214 | 1214 | POOH 3 1/2'' tbg stinger from 304m to surface.Break out and lay down in singles. ( Install dog collar clamp on every joint pulled) R | B | WHITE | 2023-03-05 | TUBING TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 3.75 | BALTIC | WEST AFRICA
1215 | 1215 | Break out and lay out SES assy. | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
1216 | 1216 | Pressure test line against Low-Torque 300/3000 psi, 5/10 min. Good test. Bleed off pressure to 0psi. Line up cement unit to test to LKL and cementer flush line had returns. Spaced out and closed MPR. | 22 | WHITE | 2023-03-05 | SURFACE TESTING | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
1217 | 1217 | P/U, M/U pumping assembly and connect Low-Torque at SES. Flush cement line with base oil from cementer to rig floor, connect hose. | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
1218 | 1218 | M/U TDS to string, break circulation with 300 lpm, confirm returns on the flow line, increase flow rate to 500 lpm, pressure 240 psi. PUW/SOW=152k/152k with pump on. Continue washing down on each stand with 500 lpm at 3 - 5 min/std from 1636m to 1777.2m and tag cement with 8 kibs, observed pressure increase 270 psi. P/U off bottom, increase flow to 1800 lpm, pressure1500 psi, RIH and re-tag TOC at 1777.2m with pressure increase to 1640 psi. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.5 | BALTIC | WEST AFRICA
1219 | 1219 | Continue Wait on 2nd cement plug to set. Meanwhile monitoring well on trip tank. Attempted to function TDS rotating shaft after PM, no rotation. 1 Troubleshoot and fixed rotating device. R Prepared and prime 13 5/8" BOP set back area. U Clean and closed buffer chambers on mud pump #1,#2 & #3. O T | 13 | WHITE | 2023-03-05 | WAIT ON CEMENT | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 4 | BALTIC | WEST AFRICA
1220 | 1220 | M/UP TEST ASSY AND SURFACE LINE. FLUSH AND TEST LINE @2500 PSI. C/OUT FIT @ 1973 PSI, EMW 18PPG IN STAGES.OK. PUMPED 3.3 BBLS RETURN 3.3 BBLS. FUNCTIONED TESTED BOP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | 23 | WHITE | 2023-03-05 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1 | RON TAPPMEYER | INDIA
1221 | 1221 | Cement unit pump at pump at 0.25 -0.3bbl/min base oil and pressure to 1600psi and held for 10mins. Bleed off pressure to 0psi . Volume pumped/Recovered 4.5/4.5bbls. | 22 | WHITE | 2023-03-05 | SURFACE TESTING | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
1222 | 1222 | R/D 3 1/2'' stinger elevator from TDS bail and R/U 5'' DP elevator. U | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
1223 | 1223 | P/U one stand of 5'' DP from derrick, RIH slowly accross BOP and well head, B/O & L/D same on the V-door in preparation for BOP O T test. | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1224 | 1224 | Clean and clear rig floor from all redundant item. | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1225 | 1225 | Install 4" 1002 hammer union extension connection on TDS S-Pipe. Hook up rotary hose on TDS. | 23 | WHITE | 2023-03-05 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
1226 | 1226 | Wattling on day light for divers operation U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 1 Date: 05-Mar-23 | 23 | WHITE | 2023-03-05 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid 17. Plug Back out over well GNN-8 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 9.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid TOTAL DAYWORK 0.00 0.00 out over well GNN-3 NO. OF DAYS 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 1 Date: 05-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 7 | RIG 141 | MENAM
1227 | 1227 | Changed casing handling equipment 2 Rig up GESCO equipment R | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | 141 | Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid 17. Plug Back out over well GNN-8 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 9.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid TOTAL DAYWORK 0.00 0.00 out over well GNN-3 NO. OF DAYS 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 1 Date: 05-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 1 | RIG 141 | MENAM
1228 | 1228 | Skid in over well GNN-3 Rig up surface line | 1 | WHITE | 2023-03-05 | RIG UP & TEAR DOWN | 141 | Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid 17. Plug Back out over well GNN-8 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 0.00 9.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid TOTAL DAYWORK 0.00 0.00 out over well GNN-3 NO. OF DAYS 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 1 Date: 05-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 1 | RIG 141 | MENAM
1229 | 1229 | Pooh while lay down 26" BIT Bit Sub And XO 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 36 Date: 05-Mar-23 | 6 | WHITE | 2023-03-05 | TRIPS | 141 | Pre job safety meeting with all personal discussed procedures and plan for nipple up X mass tree 17. Plug Back pressure test same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 3.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid TOTAL DAYWORK 0.00 0.00 out over well GNN-8 NO. OF DAYS 36 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 36 Date: 05-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 2 | RIG 141 | MENAM
1230 | 1230 | Continue Skidding cantilever over well GNN-8 | 1 | WHITE | 2023-03-05 | RIG UP & TEAR DOWN | 141 | Pre job safety meeting with all personal discussed procedures and plan for nipple up X mass tree 17. Plug Back pressure test same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 3.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid TOTAL DAYWORK 0.00 0.00 out over well GNN-8 NO. OF DAYS 36 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 36 Date: 05-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 1 | RIG 141 | MENAM
1231 | 1231 | Center derrick R Skid out over well GNN-8 check alignment U make up 6 1/2" DC and 26" Bit RIH same to mud line 240 feet O T divers jump to the water check center well Pooh with 1X 6 1/2" DC rack back same DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 1 | WHITE | 2023-03-05 | RIG UP & TEAR DOWN | 141 | Pre job safety meeting with all personal discussed procedures and plan for nipple up X mass tree 17. Plug Back pressure test same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 3.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid TOTAL DAYWORK 0.00 0.00 out over well GNN-8 NO. OF DAYS 36 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 36 Date: 05-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 6 | RIG 141 | MENAM
1232 | 1232 | Continue work on plat form with production crew Prepare Rig for skid out over well GNN-8 Cut and Slip 108 feet drilling line 1 | 23 | WHITE | 2023-03-05 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for nipple up X mass tree 17. Plug Back pressure test same 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 6.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 3.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for skid and skid TOTAL DAYWORK 0.00 0.00 out over well GNN-8 NO. OF DAYS 36 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-2 GNN-6ST Rpt No: 36 Date: 05-Mar-23 | 141-23-2 | GNN-6ST | Mar-23 | 6 | RIG 141 | MENAM
1233 | 1233 | Performed Derrick management. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
1234 | 1234 | Changed out 5 1/2'' dp elevator to 5''dp elevator. | 22 | WHITE | 2023-03-05 | SURFACE TESTING | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
1235 | 1235 | P/U two stand of 5'' HWDP from derrick, RIH and secured in rotary with slips . M/U 4 1/2 IF P X 4 1/2IF P and test plug assembly 4 1/2 IF box X 41/2 IF box to 2 stands of 5"HWDP in rotary. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 1 | BALTIC | WEST AFRICA
1236 | 1236 | P/U one stand 5'' HWDP from derrick, M/U to wear bushing RT. RIH slowly to well head and engage wear bushing at 13.2m/RTwith 1/4 right turn. PIcked wear bushing from well head and POOH slowly to surface. B/O & L/O running tool. | 23 | WHITE | 2023-03-05 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 2.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 2.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.75 NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 52 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 52 Date: 05-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
1237 | 1237 | Work with Mechanic to fix TDS Rotating head function. Break and lay down 15ft pup joint used for IBOP installation. Install pipe handler on TDS. 2 Wire lock all bolts on TDS. R Carry out house keeping around the Rig floor. U | 23 | WHITE | 2023-03-05 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 43 Date: 05-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
1238 | 1238 | CHANGE TO 5'' HANDLING EQUIPMENT. O T | 23 | WHITE | 2023-03-05 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1239 | 1239 | OBSD O/PULL @ 1133 M, ATTEMPT SEVERAL TIMES WITH PUMP & RECIPROCATION. P/UP STRING WITH 20 KIPS O/PULL & PULL STRING ABOVE THE WINDOW & POOH UPTO 1130 M. | 8 | RED | 2023-03-05 | REPAIR RIG | T12 | HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. 17. Plug Back SAVER SUB CONNECTION - 2 18. Squeeze Cement TOTAL CONNECTION - 115 19. Fishing WASH PIPE HRS - 0 20. Directional Work TOTAL WASH PIPE HRS: - 318 21. Run/Retrieve Riser Equip. DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN 22. Surface Testing JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RE S P DORNILSLIBEIRL:ITIES.INSPECTED 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 9 MWD 8.25 64.76 SIZE 12.25 WEIGHT 10.20 10.20 10.20 T C. Treating E 1 XO 8.00 3.68 IADC CODE 1 GRADIENT 0.5294 0.5294 0.5294 PL DE.. TSewsatibnbging 9 HWDP 6.75 272.74 MANUFACT. HALLIBTN VISCOSITY 67 65 65 M 1 JAR 8.00 31.10 TYPE 519 PV/YP / / / O F. Other 4 4 HWDP 6.75 120.90 SERIAL NO. 13768668 GELS / / / C G. Other 5 1 XO 8.00 3.64 JETS 7x14 FL. LOSS H. Other 6 3 HWDP 5.50 92.16 TFA 1.052 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 185 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 35 STD. D.P. 5.50 3,289.63 CUTTING STRUCTURE MEGA MUL 55 NOVATEC 35 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION VG 69 10 HOURS STANDBY KELLY DOWN 55.12 TOTAL 3,933.73 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 180,000 REMARKS: HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 4 NO. OF DAYS TOTAL CONNECTION - 119 9 FROM SPUD WASH PIPE HRS - 2.5 CUMULATIVE TOTAL WASH PIPE HRS: - 320.5 ROTATING HOURS DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 4,800.00 DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPON S DIBRILILITLIEERS:.INSPECTED EQUIPMENTS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT POOH 12-1/4" HLB DIRECTIONAL BHA. SAVER SUB CONNECTION - 2 TOTAL CONNECTION - 115 WASH PIPE HRS - 0 TOTAL WASH PIPE HRS: - 318 DEBRIEF:1- POOH WITH 12-1/4'' DIRCTIONAL BHA ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT RIH 12-1/4" HLB DIRECTIONAL ASSY. SAVER SUB CONNECTION - 4 TOTAL CONNECTION - 119 WASH PIPE HRS - 2.5 TOTAL WASH PIPE HRS: - 320.5 DEBRIEF:2- RIH WITH 12-1/4'' DIRCTIONAL ASSY. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE . IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 9 Date: 05-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1.5 | TRIDENT XII | INDIA
1240 | 1240 | DRILL OUT SOFT CEMENT FROM 10217 FT WITH 300 GPM, 2250 PSI, 50 RPM, 5K TORQUE, 5 - 10K WOB AND TAG LANDING COLLAR AT 10665 FT. | 3 | WHITE | 2023-03-05 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 4 | HIGH ISLAND IV | MENAM
1241 | 1241 | CONT POOH 6" SLICK ASSY F/2176M TO 1492M. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | 6 | WHITE | 2023-03-05 | TRIPS |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
1242 | 1242 | RECIPROCATE AT HANGER TOP WITH AND WITHOUT ROTATION SEVERAL TIMES. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
1243 | 1243 | POOH 6" ASSY F/2492M TO 2176M. HANGER TOP. | 6 | WHITE | 2023-03-05 | TRIPS |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
1244 | 1244 | PUMPED HI-VIS AND CIRC OUT.@ 340 GPM/1050PSI. 40 RPM/TQ 7-8. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
1245 | 1245 | HONED PERFORATED INTERVAL F/2492-2480M. @ 340 GPM/1050PSI. MEANWHILE MAKING BRINE & HI-VIS | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 4 | J T ANGEL | INDIA
1246 | 1246 | POOH 6” ASSY ASSY F/2568-2492M O T | 6 | WHITE | 2023-03-05 | TRIPS |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
1247 | 1247 | RIH F/2492M TO 2568M LANDING COLLAR. RECORDED INJECTIVITY 01 BPM@ 850 PSI, 1.5 BPM@ 1500 PSI, 2.5 BPM@ 2000 R PSI & 3.9 BPM@2500 PSI. U | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
1248 | 1248 | CONT REAM & CLR PACKER SETTING DEPTH 2450M. RIH F/2450M TO 2480M. HONED PERFORATED INTERVALS F/2480- 2492M. | 3 | WHITE | 2023-03-05 | REAMING |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 2.5 | J T ANGEL | INDIA
1249 | 1249 | RIH F/2182M TO 2450M, REAM & CLR PACKER SET AREA IS IN PROGRESS. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 3 | WHITE | 2023-03-05 | REAMING |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
1250 | 1250 | PUMP HI-VIS 20 BBLS & CIRC OUT, CONT REAM & CHECK H/TOP & DBOP AREA SEVERAL TIMES CLEAR THE SAME. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 2 | J T ANGEL | INDIA
1251 | 1251 | OBSD H/UP RECIPROCATE @2178M TO 2188M CLEAR DBOP AREA W/ RPM-40, TRQ 6-8 GPM 350, PRESS 1000 PSI | 3 | WHITE | 2023-03-05 | REAMING |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 2.5 | J T ANGEL | INDIA
1252 | 1252 | CONT RIH F/1440M TO 2176M H/TOP CONTROL SPEED | 6 | WHITE | 2023-03-05 | TRIPS |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.75 | J T ANGEL | INDIA
1253 | 1253 | FILL UP STRING | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.25 | J T ANGEL | INDIA
1254 | 1254 | PUMPED HI-VIS PILL & CIRC OUT. 2 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
1255 | 1255 | HPJSM, P/U AND M/U SMITH 8-1/2" USED PDC BIT MSl616B SR#SM2173 ON SLB MTR/MWD/PBL ASSY | 6 | WHITE | 2023-03-05 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. P/UP MOTOR 19. Fishing PRE JOB SAFETY METING RIH 5" HWDP AND DP 20. Directional Work PRE JOB SAFETY METING.DRILLING . 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MOTOR 8.13 26.72 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 DCM 6.72 6.40 MANUFACT. SMITH VISCOSITY 62 68 66 M 1 XO 6.95 1.12 TYPE MS6168 PV/YP / / 26/21 O F. Other 4 1 MWD 6.88 65.46 SERIAL NO. SM2173 GELS / / 10/14 C G. Other 5 1 PBL 6.50 20.89 JETS 6x13 FL. LOSS 0 H. Other 6 25 HWDP 6.63 770.15 TFA 0.778 pH 0 TOTALS 5.50 0.00 1 JAR 6.19 33.49 DEPTH OUT 5,630 SOLIDS 25 DAYWORK TIME SUMMARY 13 HWDP 6.63 400.39 DEPTH IN 5,319 2 (OFFICE USE ONLY) TOTAL DRILL 311 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 49 STD. D.P. 5.00 4,642.04 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 26.21 1 1 NO A TOTAL 5,993.65 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 185,000 X 1 NO BHA REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING . 22 FROM SPUD PRE JOB SAFETY METING.POOH W/81/2" MOTOR ASSEMBLY CUMULATIVE 20 PRE JOB SAFETY METING.L/D BHA ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 22 Date: 05-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
1256 | 1256 | RIH SLB 8-1/2" MTR/MWD ASSY ON 5" DP TO 1500' | 6 | WHITE | 2023-03-05 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. P/UP MOTOR 19. Fishing PRE JOB SAFETY METING RIH 5" HWDP AND DP 20. Directional Work PRE JOB SAFETY METING.DRILLING . 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MOTOR 8.13 26.72 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 DCM 6.72 6.40 MANUFACT. SMITH VISCOSITY 62 68 66 M 1 XO 6.95 1.12 TYPE MS6168 PV/YP / / 26/21 O F. Other 4 1 MWD 6.88 65.46 SERIAL NO. SM2173 GELS / / 10/14 C G. Other 5 1 PBL 6.50 20.89 JETS 6x13 FL. LOSS 0 H. Other 6 25 HWDP 6.63 770.15 TFA 0.778 pH 0 TOTALS 5.50 0.00 1 JAR 6.19 33.49 DEPTH OUT 5,630 SOLIDS 25 DAYWORK TIME SUMMARY 13 HWDP 6.63 400.39 DEPTH IN 5,319 2 (OFFICE USE ONLY) TOTAL DRILL 311 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 49 STD. D.P. 5.00 4,642.04 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 26.21 1 1 NO A TOTAL 5,993.65 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 185,000 X 1 NO BHA REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING . 22 FROM SPUD PRE JOB SAFETY METING.POOH W/81/2" MOTOR ASSEMBLY CUMULATIVE 20 PRE JOB SAFETY METING.L/D BHA ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 22 Date: 05-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
1257 | 1257 | WASH DOWN FROM 10036 FT AND TAG SOFT CEMENT AT 10217 FT. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1258 | 1258 | M/UP TEST ASSY AND SURFACE LINE. FLUSH AND TEST LINE @2000 PSI. C/OUT SIT @ 1700 PSI IN STAGES.OK. RIG DOWN U TEST ASSY AND SURFACE LINE. O T | 23 | WHITE | 2023-03-05 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1.5 | RON TAPPMEYER | INDIA
1259 | 1259 | PUMP HIVIS . C & C PRIOR TO SIT WITH 500 GPM/1450 PSI. R | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1 | RON TAPPMEYER | INDIA
1260 | 1260 | CLEARED/DRILLED CMT F/2304M TO 2328.5M (0.5M BELOW SHOE). 2 | 3 | WHITE | 2023-03-05 | REAMING | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 3 | RON TAPPMEYER | INDIA
1261 | 1261 | CONT CHANGE OVER WELL FLUID TO 13 PPG KCL POLYMER MUD. C & C MUD TO HOMOGENEOUS WITH 500 GPM/1450 PSI. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 3 | RON TAPPMEYER | INDIA
1262 | 1262 | RIH 8 1/2" SLICK ASSY UP TO 2307M ( F/C). WASH DOWN LAST STAND. C/OVER WELL FLUID F/ SEA WATER TO 13 PPG KCL 1 POLYMER MUD IP. R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 0.5 | RON TAPPMEYER | INDIA
1263 | 1263 | MIXED CHEMICALS IN PIT#1, 2, 3 &4. LOADED BARITE IN PIT#1 ,#2 & #3. MUD PREPARED FOR C/OVER PRIOR TO CEMENT DRILLING | 23 | WHITE | 2023-03-05 | OTHER3 | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 11.5 | RON TAPPMEYER | INDIA
1264 | 1264 | Drill 8 1/2 hole section as per D/D instruction from 1810m to 1880m, 1609TVD1800 lit/min , 2600 psi , 80 RPM ( 8 - 12 K ) TRQ 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 20 Date: 05-Mar-23 | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 27/12.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/7 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL 230 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS 13 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.00 5,304.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.27 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 9.84 1 TOTAL 6,169.59 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 20 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 162 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 20 Date: 05-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 10 | KEY MANHATTAN | MENAM
1265 | 1265 | Drill out 9 5/8 Shoe track from 1804m to 1808m (9 5/8 shoe) and rat hole to 1810 m. Flow rate 1600 lit/min - 2250 psi , RPM 60 , TRQ 6000. | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 27/12.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/7 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL 230 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS 13 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.00 5,304.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.27 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 9.84 1 TOTAL 6,169.59 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 20 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 162 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 20 Date: 05-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 2 | KEY MANHATTAN | MENAM
1266 | 1266 | Preparing for drilling. Adjusting parameters with DD to monitoring drilling on DD and Geolog screen. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 3 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 5938 6168 Drill 10 % Sand - 90 % Clay 90 10 2500 6.000 55 6.000 55 460.845 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 5,988 37.1201 116622..7733 5,137.5 6,082 37.19 116622..9999 5,212.6 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 8 | RED | 2023-03-05 | REPAIR RIG | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 27/12.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/7 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL 230 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS 13 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.00 5,304.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.27 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 9.84 1 TOTAL 6,169.59 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 20 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 162 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 20 Date: 05-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 1 | KEY MANHATTAN | MENAM
1267 | 1267 | Repair drilling instrumentation ( Spectrum 1000 and Rigsense ) Continue with circulation and mixing ant treating mud. | 8 | RED | 2023-03-05 | REPAIR RIG | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 55 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 27/12.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 4/7 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 1 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.4 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL 230 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS 13 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.00 5,304.53 CUTTING STRUCTURE T HOURS WITHOUT D.P. 1 SNG. D.P. 5.00 31.27 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 9.84 1 TOTAL 6,169.59 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 20 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 162 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 20 Date: 05-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 11 | KEY MANHATTAN | MENAM
1268 | 1268 | RIH SLB 8-1/2" MTR/MWD ASSY ON 5" DP TO TOW @l 5250' R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 5630 5967 Drill Shale 40 10000 3000 6.000 70 6.000 70 579.866 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 5,582 49.61 331188..2266 4,565.5 2,179.7 5,675 49.72 331188..2222 5,025.7 327.2 5,770 51.87 331177..4488 5,085.7 326.9 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 22 Date: 05-Mar-23 | 6 | WHITE | 2023-03-05 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. P/UP MOTOR 19. Fishing PRE JOB SAFETY METING RIH 5" HWDP AND DP 20. Directional Work PRE JOB SAFETY METING.DRILLING . 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MOTOR 8.13 26.72 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 DCM 6.72 6.40 MANUFACT. SMITH VISCOSITY 62 68 66 M 1 XO 6.95 1.12 TYPE MS6168 PV/YP / / 26/21 O F. Other 4 1 MWD 6.88 65.46 SERIAL NO. SM2173 GELS / / 10/14 C G. Other 5 1 PBL 6.50 20.89 JETS 6x13 FL. LOSS 0 H. Other 6 25 HWDP 6.63 770.15 TFA 0.778 pH 0 TOTALS 5.50 0.00 1 JAR 6.19 33.49 DEPTH OUT 5,630 SOLIDS 25 DAYWORK TIME SUMMARY 13 HWDP 6.63 400.39 DEPTH IN 5,319 2 (OFFICE USE ONLY) TOTAL DRILL 311 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 49 STD. D.P. 5.00 4,642.04 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 26.21 1 1 NO A TOTAL 5,993.65 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 185,000 X 1 NO BHA REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING . 22 FROM SPUD PRE JOB SAFETY METING.POOH W/81/2" MOTOR ASSEMBLY CUMULATIVE 20 PRE JOB SAFETY METING.L/D BHA ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 22 Date: 05-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
1269 | 1269 | FILL STRING AND SHALLOW TEST MWD 1 | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. P/UP MOTOR 19. Fishing PRE JOB SAFETY METING RIH 5" HWDP AND DP 20. Directional Work PRE JOB SAFETY METING.DRILLING . 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MOTOR 8.13 26.72 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 DCM 6.72 6.40 MANUFACT. SMITH VISCOSITY 62 68 66 M 1 XO 6.95 1.12 TYPE MS6168 PV/YP / / 26/21 O F. Other 4 1 MWD 6.88 65.46 SERIAL NO. SM2173 GELS / / 10/14 C G. Other 5 1 PBL 6.50 20.89 JETS 6x13 FL. LOSS 0 H. Other 6 25 HWDP 6.63 770.15 TFA 0.778 pH 0 TOTALS 5.50 0.00 1 JAR 6.19 33.49 DEPTH OUT 5,630 SOLIDS 25 DAYWORK TIME SUMMARY 13 HWDP 6.63 400.39 DEPTH IN 5,319 2 (OFFICE USE ONLY) TOTAL DRILL 311 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 49 STD. D.P. 5.00 4,642.04 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 26.21 1 1 NO A TOTAL 5,993.65 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 185,000 X 1 NO BHA REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING . 22 FROM SPUD PRE JOB SAFETY METING.POOH W/81/2" MOTOR ASSEMBLY CUMULATIVE 20 PRE JOB SAFETY METING.L/D BHA ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 22 Date: 05-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
1270 | 1270 | CONT RIH F/635M TO 1440M O T | 6 | WHITE | 2023-03-05 | TRIPS |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
1271 | 1271 | FILL UP STRING U | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.25 | J T ANGEL | INDIA
1272 | 1272 | SET PARAMETER COMMENCE DRILLING FRESH FORMATION F/2328.5 M TO 2334 M. RPM-80,GPM-500, PRESS-1550 PSI. TQ- 2/4 KFTLBS. | 2 | WHITE | 2023-03-05 | DRILL ACTUAL | RTP | WASH PIPE HRS: 0 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 761 HRS. 18. Squeeze Cement SAVER SUB :-1 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 177 CONNECTIONS. 20. Directional Work INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 11.50 2.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 8.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.82 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.25 2.69 IADC CODE 117 GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 2 DC 6.50 61.19 MANUFACT. SMITH VISCOSITY 53 53 53 M 3 STAB 6.39 11.09 TYPE XR+CPS PV/YP / / / O F. Other 4 5 DC 6.50 147.77 SERIAL NO. RP 2625 GELS / / / C G. Other 5 10 HWDP 5.00 268.01 JETS 3x20,18 FL. LOSS H. Other 6 1 JAR 6.50 29.92 TFA 1.169 pH TOTALS 12.00 12.00 6 HWDP 5.00 176.97 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 60 DP 5.00 1,887.86 DEPTH IN 7,644 2 (OFFICE USE ONLY) 1 XO 7.00 2.76 TOTAL DRILL 89 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 1.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 53 STD. D.P. 5.50 5,019.26 CUTTING STRUCTURE BARITE 9 PAC RG 12 T HOURS WITHOUT D.P. 1 SNG. D.P. 5.50 31.53 INNER OUTER DULL CHAR. LOCATION zan 4 DRISTEMP 10 HOURS STANDBY KELLY DOWN 18.24 1 TOTAL 7,658.10 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 225,000 REMARKS: WASH PIPE HRS: 6 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 767 HRS. NO. OF DAYS SAVER SUB :-1 CONNECTION. 49 FROM SPUD TOTAL CONNECTIONS :- 178 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 49 Date: 05-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1.5 | RON TAPPMEYER | INDIA
1273 | 1273 | CHANGE ELEVATOR 3-1/2" TO 5-1/2" 1 | 23 | WHITE | 2023-03-05 | OTHER3 |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.25 | J T ANGEL | INDIA
1274 | 1274 | Held PJSM prior to L/Down 3 1/2" Completion. O T | 23 | WHITE | 2023-03-05 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1275 | 1275 | POOH and L/Down 5 jts x 4 1/2" N.Vam TBG, 4 1/2" N.Vam P/jt & 4 1/2" TRSSSV. R Continuously monitoring and filling well from trip tank. U | B | WHITE | 2023-03-05 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.75 | MAIN PASS I | MENAM
1276 | 1276 | L/Down CIW TBG hanger and P/jt. 2 | B | WHITE | 2023-03-05 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1 | MAIN PASS I | MENAM
1277 | 1277 | Held PJSM prior to L/Down 4 1/2" Completion. | 23 | WHITE | 2023-03-05 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1278 | 1278 | R/Up 4 1/2"Handling equipment. | B | WHITE | 2023-03-05 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1279 | 1279 | R/Up 4 1/2"Handling equipment. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | B | WHITE | 2023-03-05 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1280 | 1280 | Slick Line RIH and set Interwell pump THRU plug above punch POOH & R/Down Slick line. | E | WHITE | 2023-03-05 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 3 | MAIN PASS I | MENAM
1281 | 1281 | R/UP Slick sine BOP and Lubricator. Pressure test to 2000psi | E | WHITE | 2023-03-05 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1.5 | MAIN PASS I | MENAM
1282 | 1282 | Held PJSM to R/UP Slick line | 6 | WHITE | 2023-03-05 | TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1283 | 1283 | Bull head TCA 76 pcf brine 2 bpm, 950psi. Flow check static losses 20 bbls/hr O T | 23 | WHITE | 2023-03-05 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 3.5 | MAIN PASS I | MENAM
1284 | 1284 | M/U TDS to 4-1/2" landing joint Released TBG HGR Lock Down Screws. Work seal assy and able to un-sting seal assy POOH to tbg R hanger at at surface. Flow check static losses 26 bbls/hr. U | E | WHITE | 2023-03-05 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 2 | MAIN PASS I | MENAM
1285 | 1285 | Held safety stand down and Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in desert. Shelf HSE Alert - drop object. 1 | 23 | WHITE | 2023-03-05 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
1286 | 1286 | R/Down expro slick line lubricator, BOP, SES, X-O, 4-1/2" N.Vam TIW and surface lines. | E | WHITE | 2023-03-05 | TESTING | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 1 | MAIN PASS I | MENAM
1287 | 1287 | CONT RIH F/437M TO 635M R | 6 | WHITE | 2023-03-05 | TRIPS |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
1288 | 1288 | R/Up 3 1/2"Handling equipment. | B | WHITE | 2023-03-05 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
1289 | 1289 | Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & Life saving equipment. | 23 | WHITE | 2023-03-05 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.5 | MAIN PASS I | MENAM
1290 | 1290 | DRILL OUT LANDING COLLAR FROM 10665 FT TO 10666 FT WITH 150 - 300 GPM, 1100 - 2250 PSI, 30 - 70 RPM, AND 10 - 20K WOB. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | 3 | WHITE | 2023-03-05 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 0.75 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 TIME 12:00 18:00 23:59 I 1 BIT 6.13 0.61 SIZE 6.13 WEIGHT 10.00 10.00 10.00 T C. Treating E 1 BS 5.31 4.00 IADC CODE GRADIENT 0.519 0.519 0.519 PL DE.. TSewsatibnbging 3 DC 4.75 184.90 MANUFACT. VISCOSITY 59 59 59 M 1 XO 5.00 2.74 TYPE PV/YP / / / O F. Other 4 3 HWDP 4.00 92.37 SERIAL NO. 838186 GELS / / / C G. Other 5 1 JAR 6.50 29.50 JETS FL. LOSS H. Other 6 9 HWDP 5.00 276.67 TFA 0.000 pH TOTALS 12.00 12.00 300 DP 4.00 9,445.24 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.00 547.58 CUTTING STRUCTURE Mul xt 8 lime 60 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION ecotrol 24 HOURS STANDBY KELLY DOWN TOTAL 10,583.61 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 38 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA LAY DOWN DP CUMULATIVE 70 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 38 Date: 05-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.5 | HIGH ISLAND IV | MENAM
1291 | 1291 | P/UP & M/UP BIT ,JUNG SUB,STRING STAB RIH CLEAR OUT ASSY BHA UP TO 437M. | 6 | WHITE | 2023-03-05 | TRIPS |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
1292 | 1292 | HELD PJSM P/UP & SHOOTING NIPPLE | A | WHITE | 2023-03-05 | PERFORATION |  | HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating 0.50 O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.2 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 6x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.663 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,425 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 38 STD. D.P. 5.50 3,462.43 CUTTING STRUCTURE drill water 50 xcpolymer 3 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION pacrg 1 caustic soda 1 HOURS STANDBY KELLY DOWN TOTAL 4,895.41 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 152,000 REMARKS: HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 74 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 130 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT ASSY. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 233 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 923 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING HONING PERFORATE DEPTH. TOOK TOFS @ 14:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 74 Date: 05-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
1293 | 1293 | Held PJSM, M/U BOP's test assy (test pug with 2 7/8'' D/pipe), P/test annular and top rams to 300/2500 psi , Good tests. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 | 15 | WHITE | 2023-03-05 | TEST BOP | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
1294 | 1294 | POOH and L/Down 3 1/2" EUE completion TBG from 5999ft to 1998ft.Continuously monitoring and filling well from trip tank. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | B | WHITE | 2023-03-05 | TUBING TRIPS | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement AT 1:00 to 1:30 Held safety stand down. Discussed HSE alert 24-23, Search and rescue Stuck vehicle and lost in 19. Fishing desert. Shelf HSE Alert - drop object. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 4.00 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 0.25 11.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I SIZE WEIGHT 10.15 T C. Treating E IADC CODE GRADIENT 0.5268 L D. Swabbing MANUFACT. VISCOSITY P E. Testing 7.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE calcium chloride 32 T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS AT 16:00 to 16:30 Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & 0 FROM SPUD Life saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 4 Date: 05-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 7.5 | MAIN PASS I | MENAM
1295 | 1295 | Held PJSM, Retrieve 11'' FMC wear bushing from wellhead. Monitor well on Trip tank, Well static. O T | E | WHITE | 2023-03-05 | TESTING | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
1296 | 1296 | Held PJSM, Service top drive and check for DROPS, Clean and clear rig floor U | 7 | WHITE | 2023-03-05 | LUBRICATE RIG | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1 | HIGH ISLAND IX | MENAM
1297 | 1297 | Held PJSM, Change out top pipe rams to 2 7/8''. | 14 | WHITE | 2023-03-05 | N/UP BOP | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 2 | HIGH ISLAND IX | MENAM
1298 | 1298 | Held PJSM, Pooh and L/D in singles with 7" Scraper clean out assy on 4" D/pipe F/ 4149 ft to 324 ft, (total 117 joints). Monitor well on Trip tank, Well static. | 6 | WHITE | 2023-03-05 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 5.25 | HIGH ISLAND IX | MENAM
1299 | 1299 | Held PJSM, Pooh and L/D in singles with 7" Scraper clean out assy on 4" D/pipe F/ 6563 ft to 4149 ft,(total 96 joints). Monitor well on Trip tank, Well static. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-05 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 4 | HIGH ISLAND IX | MENAM
1300 | 1300 | Held PJSM, circulate hole clean w/ 76pcf OBM. Flow check well, well static, Pump Slug. O T | 5 | WHITE | 2023-03-05 | CONDITION MUD & CIRCULATE | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
1301 | 1301 | Held PJSM, Rih with Scraper assy 4" D/pipe @ control speed F/ 334 ft to 4 ½”” TOL @ 6563 ft work Scraper across Pkr interval R (6000-6544) Fill & break circ every 20 stds. Monitor well on Trip tank, Well static. U | 6 | WHITE | 2023-03-05 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 4.5 | HIGH ISLAND IX | MENAM
1302 | 1302 | Held PJSM, Make up 6 1/8" CP mill, Bit sub w/Float, 6 1/8" String Mill, 1 jt of 4 ¾” dc , x/over, 7" Csg Scraper, x/over 2 joints of 4 ¾” DC , X/over and 3 joints of 4” HWDP , jar and 3 joints of 4 “ HWDP to 324 ft. Monitor well on Trip tank, Well static. 1 | 6 | WHITE | 2023-03-05 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.5 | HIGH ISLAND IX | MENAM
1303 | 1303 | Held PJSM. Clean and clear r/floor. | 6 | WHITE | 2023-03-05 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 0.5 | HIGH ISLAND IX | MENAM
1304 | 1304 | Held PJSM, Pooh with 7" Scraper clean out assy 2 stands 4" HWDP & L/D 3 JT 4 3/4'' DC + 4 3/4'' Drilling jar + crossover + 7'' 2 scraper + crossover + 6 1/8'' string mill + bit sub + 6 1/8'' CP mill F/ 324 ft to surface. Monitor well on Trip tank, Well static. R | 6 | WHITE | 2023-03-05 | TRIPS | HI9 | Function COM and KEMS and Reset, 17. Plug Back Function TIW and Grey Valve Both left in OPEN position 18. Squeeze Cement 19. Fishing SWL PKG----ROT = 240 Hrs. 20. Directional Work SWL PKG---CIRC = 332 Hrs. 21. Run/Retrieve Riser Equip. 22. Surface Testing Run MP#2 and # 3 SPM 47 PSI 1650 = 1.5 Hrs DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 MILL 6.13 2.45 SIZE WEIGHT 10.16 T C. Treating E 1 BS 4.56 3.01 IADC CODE GRADIENT 0.5273 PL DE.. TSewsatibnbging 1.00 1 MILL 6.13 4.74 MANUFACT. VISCOSITY 60 M 1 DC 4.75 30.70 TYPE PV/YP / O F. Other 4 1 XO 4.75 2.27 SERIAL NO. GELS / C G. Other 5 1 SCRAP 7.00 3.30 JETS FL. LOSS H. Other 6 1 XO 4.75 3.02 TFA pH TOTALS 12.00 12.00 2 DC 4.75 61.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 3 HWDP 4.00 92.05 DEPTH IN 2 (OFFICE USE ONLY) 1 4.75 26.85 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 3 HWDP 4.00 92.16 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 321.92 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Function COM and KEMS and Reset, TOTAL DAYWORK 0.00 0.00 Function TIW and Grey Valve Both left in OPEN position NO. OF DAYS 55 FROM SPUD SWL PKG----ROT = 240 Hrs. CUMULATIVE 225 SWL PKG---CIRC = 332 Hrs. ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI9 Job:BRRI-40 Rpt No: 72 Date: 05-Mar-23 WIRE LINE | BRRI-40 | BRRI-40 | Mar-23 | 1.75 | HIGH ISLAND IX | MENAM
1305 | 1305 | PJSM for running 7" CSG and Rig up casing equipment. U | 23 | WHITE | 2023-03-06 | OTHER3 | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1306 | 1306 | Pull wear bushing. R | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1307 | 1307 | Continue POOH BHA. Retrieve radioactive source. Break out of bit and rack back BHA. Note: Download MWD data offline. 2 | 6 | WHITE | 2023-03-06 | TRIPS | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.5 | CHAOPHRAYA | SOUTH EAST ASIA
1308 | 1308 | Flow check - well static. Note: Trip drill well secure in 21 sec. 1D0E:P4T5H IN1TE1R:0V0AL D0.R2I5LL 6 Drop gyro. ChFaOseR MgAyrToIO dNown 200 strokes aRtO 1T0A0R sYpm.W STh.ut down pumpP tUoM tPake surveyP.U CMoPntinue POPOUMHP to BHA. PUMP TOTAL CORE PUMP 1F1R:O00M 12:T0O0 R1C.EO0AR0ME N6O. Continu(eS HpOuWll o CuOt RthEe R hEoCleO VaEndR Yre)trieve gyroST.APEBELDE BOINT PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-06 | TRIPS | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1309 | 1309 | Pump slug and trip out of hole to 1,213' MD. | 6 | WHITE | 2023-03-06 | TRIPS | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.25 | CHAOPHRAYA | SOUTH EAST ASIA
1310 | 1310 | Flow check - well static. | 6 | WHITE | 2023-03-06 | TRIPS | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1311 | 1311 | Flow check- static. pooh 8 ½’’nbs assy F/1335 m to155 m. R | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1312 | 1312 | Drill 8-1/2" hole from 3,280' MD to section TD at 4,331' MD/ 3,993' TVD. Note: R - Drill hole with 9.2 ppg WBM to TD. U O - Top of MMU at 4,000' MD/ 4,713' TVD. T - Start pump 30 bbls Hi-vis sweep 10.5 ppg every 3 stand at 2,500' TVD to TD. T - Start pump 50 bbls SW sweep every 3 stand on Tangent section. H - Displace well on the fly with 9.8 ppg PHPA WBM on last connection before TD. G I - Max gas while drilling 57u/ 20u @ 3,584' MD/ 3,338' TVD. N - Control ROP 720 fph due to LWD logging record data. - Shallow top sand 2,648’ MD/ 2,499’ TVD base on LWD data. | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 7.5 | CHAOPHRAYA | SOUTH EAST ASIA
1313 | 1313 | Make up & Rih with wire line. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 | 11 | WHITE | 2023-03-06 | WIRELINE LOGS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
1314 | 1314 | Pressure test Packer seal @ 1000 psi ok. | 11 | WHITE | 2023-03-06 | WIRELINE LOGS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1315 | 1315 | Chang elevator, install shooting nipple rig up HLS wire line equips.Mean while surface preparation HLS tools. O T | 11 | WHITE | 2023-03-06 | WIRELINE LOGS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1316 | 1316 | Flow check ok cont Pooh F/ 155 m to surface.Lay down x/o, jar & bit. U | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
1317 | 1317 | POOH WITH BAKER RUNNING TOOLS ASSY FROM 7434' | 6 | WHITE | 2023-03-06 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1 | MAIN PASS IV | MENAM
1318 | 1318 | Circulate and displace well with 9.8 ppg PHPA mud. - Pump 1st 80 bbls of 11 ppg sweep and continue to circulate with 9.8 ppg PHPA mud. - Pump 2nd 80 bbls of 11 ppg sweep and continue to circulate with 9.8 ppg PHPA mud. - Pump 3rd 80 bbls of 11 ppg sweep and continue to circulate with 9.8 ppg PHPA mud. - Continue to circulate with 9.8 ppg PHPA. Total of circulate 5.13 bottoms up - Shakers clean. GPM: 780 RPM:120. - Calculated average hole size: 10.6". | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
1319 | 1319 | Run in the hole with 7" casing TPCQ to 4,225' MD. O T | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.75 | CHAOPHRAYA | SOUTH EAST ASIA
1320 | 1320 | Continue pull out the hole and retrieve gyro. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-06 | TRIPS | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1 | CHAOPHRAYA | SOUTH EAST ASIA
1321 | 1321 | Make up 7" casing hanger. Land hanger with casing shoe at 4,321' MD/ 3,985' TVD. Test seals to 6,500 psi. Energize snap ring. Pull test 10K over slack-off weight - Good test. | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.5 | CHAOPHRAYA | SOUTH EAST ASIA
1322 | 1322 | Pump hi-vis & circ out. displaced well vol with 8.6ppg filtered brine.With 450 gpm, 250 psi, 90spm. Flushed all surface lines & equpmnts. 2 | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1323 | 1323 | FLOW CHECK . WELL STATIC PUMP SLUG . | 6 | WHITE | 2023-03-06 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1 | MAIN PASS IV | MENAM
1324 | 1324 | SET LINER HANGER/ TOP PACKER AS PER BAKER ENGINEER , LINER HANGER SET @ 1800 PSI , RELEASE RUNNING U TOOLS , TOL @ 7433' . O T | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1.5 | MAIN PASS IV | MENAM
1325 | 1325 | CONT. PUMP MICRO - WASH AS PER PLAN WITH 3 BPM 450 PSI . R | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.75 | MAIN PASS IV | MENAM
1326 | 1326 | BAKER ENGINEER DROP 1.5'' BALL . 1 | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1327 | 1327 | PUMP AND SPOT MICRO - WASH AS PER PLAN + 20 BBLS HI - VIS WITH 5.5 BPM - 950 PSI . | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.75 | MAIN PASS IV | MENAM
1328 | 1328 | M/U X/O with 5" DP. Circulate hole and Reciprocate pipe with 9.8ppg PHPA at 300 gpm, 180 psi. Note: Max gas 41 unit. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1 | CHAOPHRAYA | SOUTH EAST ASIA
1329 | 1329 | HPJSM , CONT. CIRCULATING HOLE WITH 3.5 BPM - 280 PSI HILE MIXING MICRO - WASH . | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.75 | MAIN PASS IV | MENAM
1330 | 1330 | Wait on cement for develop to 50 psi compressive strength. Rig activities: - M/U 6-1/8" BHA. - P/U 4" HWDP and 4" DP. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | 13 | WHITE | 2023-03-06 | WAIT ON CEMENT | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 5.25 | CHAOPHRAYA | SOUTH EAST ASIA
1331 | 1331 | Drop gyro. Chase gyro down 200 strokes at 100 spm. Shut down pump to take survey. Continue POOH to BHA. | 6 | WHITE | 2023-03-06 | TRIPS | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1332 | 1332 | Wait on cement for develop to 50 psi compressive strength. Rig activities: - M/U 6-1/8" BHA. IADCDAILY DRILL- PIN/UG 4" RHWEDPPO anRdT 4" FDOP.RM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 Night Tour Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 13 | WHITE | 2023-03-06 | WAIT ON CEMENT | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 5.25 | CHAOPHRAYA | SOUTH EAST ASIA
1333 | 1333 | Mix and pump 162 bbls of 15.0 ppg cement slurry and displace with 163.8 bbls sea water. Cement in place at 18:45 hr. Remark: - 50 psi compressive strength = 5 hr 28 mins. - 500 psi compressive strength = 7 hr 56 mins | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 1.5 | CHAOPHRAYA | SOUTH EAST ASIA
1334 | 1334 | Rig up cement head on rig floor. | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.75 | CHAOPHRAYA | SOUTH EAST ASIA
1335 | 1335 | PJSM for R/U Cement head perform cement job. | 23 | WHITE | 2023-03-06 | OTHER3 | SDC | Pre-tour meeting with the crews for drilling making connection, and pick up 7" casing offline. Service 17. Plug Back all drilling handling equipment and general housekeeping, KEMS is operational and COM set 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. BAKER VISCOSITY P E. Testing M TYPE DD604M- PV/YP O F. Other 4 SERIAL NO. 5336250 GELS C G. Other 5 JETS 6x13 FL. LOSS H. Other 6 TFA 0.778 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 825 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING X 1 NO TD REMARKS: Pre-tour meeting with the crews for POOH with 8.1/2' BHA , run 7' casing., cement job.on line and TOTAL DAYWORK 0.00 0.00 P/u 4' DP. Service all drilling handling equipment and general housekeeping, KEMS is operational and COM set NO. OF DAYS 11 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDC Job:PA51 Exploration Rpt No: 11 Date: 06-Mar-23 | PA51 Exploration | PA51 | Mar-23 | 0.25 | CHAOPHRAYA | SOUTH EAST ASIA
1336 | 1336 | Cont rih 8-1/2” fg nbs F/791m to 1335 m. Wash down last std. tag @ 1335 m with 10k. | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1337 | 1337 | Continue RIH 2 7/8" cmt stinger on 5" DP F/ 10349 ft T/ 11100 ft.wash down last 2 stand observe 50 bbl losses | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
1338 | 1338 | Cut and Slip 110 ft. O T | 9 | WHITE | 2023-03-06 | CUT OFF DRILL LINE | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1339 | 1339 | M/U Safety valve with X/O,P/U and RIH 2-7/8" tbg cmt stinger from surface to 1006 ft. I | B | WHITE | 2023-03-06 | TUBING TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 3 | ACHEIVER | MENAM
1340 | 1340 | R/U 2-7/8" Tbg handling equipment, change BX elevator to 2-7/8" Manual elevator, remove rotating arm, R/U manual tubing tongs. H G | 23 | WHITE | 2023-03-06 | OTHER3 | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
1341 | 1341 | clean clear rig floor. HPJSM with the crew for RIH 2-7/8" Tubing T | 23 | WHITE | 2023-03-06 | OTHER3 | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
1342 | 1342 | POOH and lay down 8 1/2" BHA from 100 ft to surface and L/D same. T | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
1343 | 1343 | Cont. POOH on 5' HWDP f 286 ft' to 100 ft' U O | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
1344 | 1344 | Flow Check prior to BHA, Observed 48 Bbls /hr losses R | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
1345 | 1345 | R/D 2-7/8" Tbg handling equipment, change 2-7/8" Manual elevator to BX elevator with rotating arm, N | 23 | WHITE | 2023-03-06 | OTHER3 | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
1346 | 1346 | HPJSM, POOH w/ 8-1/2" DIR BHA F/ 3952 To 286ft , Observed Losses 48 bbls/hr | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
1347 | 1347 | SET PARAMETERS & RESUME DRILLING 12 1/4" SECTION F/1709M TO 1820M. REAM UP & DN ONCE PRIOR TO CONNECTION. PUMP 20 BBLS HI-VIS EVERY ALTERNATIVE STAND DRILLED. TOOK SURVEY AS PER HLB DD.( WOB 10-15 K LBS/RPM 150/TQ 8-12 KFT-LBS/GPM 800/2040PSI) FURTHER DRILLING IN PROGRESS IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 32 Date: 06-Mar-23 | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | FGM | HELD PJSM ABOUT PRIOR TO CIRCULATION WHILE WAITING ON . 17. Plug Back SAVER SUB :- HT-55 - 111 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 113 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:55 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 10.00 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.519 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 476 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.50 5,284.45 CUTTING STRUCTURE Le supermul 2 INVERMUL 2 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.50 62.73 INNER OUTER DULL CHAR. LOCATION LIME 40 StEELSEAL 40 HOURS STANDBY KELLY DOWN 12.21 BARACarB25 80 LIQUATONE 1 2 TOTAL 5,971.13 BEARINGS GAUGE OTHER REASON fracseal 10 SUSPENTONE 3 SEALS DULL PULLED WT. OF STRING 234,000 BARITE 9 REMARKS: HELD PJSM ABOUT PRIOR TO DRILLING 12 1/4'' HOLE. TBSM PRIOR TO CONNECTION. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 115 CONNECTIONS NO. OF DAYS WASH PIPE :- 120 HRS. 32 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 35 21 1/4'' ANN :- 4 C/O HELD PIT DRILL ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 32 Date: 06-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 6.5 | F G MCCLINTOCK | INDIA
1348 | 1348 | RIH F/1653M TO 1709M. WASH DOWN LAST STAND & BREAK CIRCULATION. O T | 6 | WHITE | 2023-03-06 | TRIPS | FGM | HELD PJSM ABOUT PRIOR TO CIRCULATION WHILE WAITING ON . 17. Plug Back SAVER SUB :- HT-55 - 111 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 113 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:55 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 10.00 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.519 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 476 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.50 5,284.45 CUTTING STRUCTURE Le supermul 2 INVERMUL 2 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.50 62.73 INNER OUTER DULL CHAR. LOCATION LIME 40 StEELSEAL 40 HOURS STANDBY KELLY DOWN 12.21 BARACarB25 80 LIQUATONE 1 2 TOTAL 5,971.13 BEARINGS GAUGE OTHER REASON fracseal 10 SUSPENTONE 3 SEALS DULL PULLED WT. OF STRING 234,000 BARITE 9 REMARKS: HELD PJSM ABOUT PRIOR TO DRILLING 12 1/4'' HOLE. TBSM PRIOR TO CONNECTION. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 115 CONNECTIONS NO. OF DAYS WASH PIPE :- 120 HRS. 32 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 35 21 1/4'' ANN :- 4 C/O HELD PIT DRILL ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 32 Date: 06-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 0.5 | F G MCCLINTOCK | INDIA
1349 | 1349 | CONTINUE WAITING ON LOGISTIC TO DELIVER SOBM CHEMICALS FROM OSV GS DIPTI SINCE 1800HRS ON 05.03.2023. M/W C&C FOR 40 MIN AT INTERVAL OF EVERY 1 HOUR AS PER REQUIREMENT OF HALLIBURTON RSS+LWD TOOLS. (TOTAL 2.0 HRS IN SHIFT & TOTAL CIR. TIME- 8.5 HOUR) (BOAT OSV DIPTI ALONG SIDE @1500HRS ONLY DELIVER 01 2 PALLET CHEMICALS DUE TO BAD WEATHER CONDITIONS BOAT DIPTI PULL OUT. AGAIN BOAT ALONG SIDE @1550 HRS R AND DELIVER CHEMICALS. CHEMICAL MIXING AND PREPARE MUD.) U | 23 | WHITE | 2023-03-06 | OTHER3 | FGM | HELD PJSM ABOUT PRIOR TO CIRCULATION WHILE WAITING ON . 17. Plug Back SAVER SUB :- HT-55 - 111 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 113 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:55 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 10.00 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.519 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 476 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.50 5,284.45 CUTTING STRUCTURE Le supermul 2 INVERMUL 2 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.50 62.73 INNER OUTER DULL CHAR. LOCATION LIME 40 StEELSEAL 40 HOURS STANDBY KELLY DOWN 12.21 BARACarB25 80 LIQUATONE 1 2 TOTAL 5,971.13 BEARINGS GAUGE OTHER REASON fracseal 10 SUSPENTONE 3 SEALS DULL PULLED WT. OF STRING 234,000 BARITE 9 REMARKS: HELD PJSM ABOUT PRIOR TO DRILLING 12 1/4'' HOLE. TBSM PRIOR TO CONNECTION. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 115 CONNECTIONS NO. OF DAYS WASH PIPE :- 120 HRS. 32 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 35 21 1/4'' ANN :- 4 C/O HELD PIT DRILL ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 32 Date: 06-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 5 | F G MCCLINTOCK | INDIA
1350 | 1350 | WAITING ON LOGISTIC TO DELIVER SOBM CHEMICALS FROM OSV GS DIPTI SINCE 1800HRS ON 05.03.2023. M/W C&C FOR 40 MIN AT INTERVAL OF EVERY 1 HOUR AS PER REQUIREMENT OF HALLIBURTON RSS+LWD TOOLS. (TOTAL 4.5 HRS IN SHIFT & TOTAL CIR. TIME- 6.5 HOUR) 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 5607 5971 Drill SAND STONE 150 10000 2000 6.500 80 6.500 80 800 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 5,674 1.93 112255..33 5,671.4 5,767 1.15 111199..3388 5,764.4 5,862 0.9 111100..77 5,859.2 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-06 | OTHER3 | FGM | HELD PJSM ABOUT PRIOR TO CIRCULATION WHILE WAITING ON . 17. Plug Back SAVER SUB :- HT-55 - 111 CONNECTIONS 18. Squeeze Cement WASH PIPE :- 113 HRS. 19. Fishing 13 5/8" ANN :- 2 C/O 20. Directional Work 21 1/4'' ANN :- 4 C/O 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 5.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 5.1 TIME 12:10 18:00 23:55 I 1 BIT 12.25 1.12 SIZE 12.25 WEIGHT 9.90 9.90 10.00 T C. Treating E 11 OTHER 12.00 109.58 IADC CODE GRADIENT 0.5138 0.5138 0.519 PL DE.. TSewsatibnbging 1 PPL 8.00 9.15 MANUFACT. SMITH VISCOSITY 70 70 70 M 1 XO 8.06 2.79 TYPE MDI 519 PV/YP / / / O F. Other 4 9 HWDP 6.63 271.36 SERIAL NO. 1558 GELS / / / C G. Other 5 1 XO 8.00 1.94 JETS 8x14 FL. LOSS H. Other 6 1 JAR 8.00 32.42 TFA 1.203 pH TOTALS 12.00 12.00 1 XO 8.00 1.61 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 6.63 178.81 DEPTH IN 5,495 2 (OFFICE USE ONLY) 1 XO 8.00 2.99 TOTAL DRILL 476 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 7 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 56 STD. D.P. 5.50 5,284.45 CUTTING STRUCTURE Le supermul 2 INVERMUL 2 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.50 62.73 INNER OUTER DULL CHAR. LOCATION LIME 40 StEELSEAL 40 HOURS STANDBY KELLY DOWN 12.21 BARACarB25 80 LIQUATONE 1 2 TOTAL 5,971.13 BEARINGS GAUGE OTHER REASON fracseal 10 SUSPENTONE 3 SEALS DULL PULLED WT. OF STRING 234,000 BARITE 9 REMARKS: HELD PJSM ABOUT PRIOR TO DRILLING 12 1/4'' HOLE. TBSM PRIOR TO CONNECTION. TOTAL DAYWORK 0.00 0.00 SAVER SUB :- HT-55 - 115 CONNECTIONS NO. OF DAYS WASH PIPE :- 120 HRS. 32 FROM SPUD 13 5/8" ANN :- 2 C/O CUMULATIVE 35 21 1/4'' ANN :- 4 C/O HELD PIT DRILL ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: FGM Job:MBS181HCA-A Rpt No: 32 Date: 06-Mar-23 | MBS181HCA-A | MBS181HCA#A | Mar-23 | 12 | F G MCCLINTOCK | INDIA
1351 | 1351 | RECEIVED REVISED PLAN. PUMP SLUG, POOH LWD ASSY BHA F/2290M TO 947 M.FPIP. R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | 6 | WHITE | 2023-03-06 | TRIPS | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 2 | RON TAPPMEYER | INDIA
1352 | 1352 | SERVICE TDS . | 23 | WHITE | 2023-03-06 | OTHER3 | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.5 | MAIN PASS IV | MENAM
1353 | 1353 | M/U cement assy 10 ft 5" pup joint , Safety valve and side entry sub. torque same and L/D. | 23 | WHITE | 2023-03-06 | OTHER3 | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
1354 | 1354 | RIH 2 7/8" cmt stinger on 5" DP F/ 1006 ft T/ 8350 ft. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 4 | ACHEIVER | MENAM
1355 | 1355 | Continue RIH 2 7/8" cmt stinger on 5" DP F/ 8350 ft T/ 10349 ft.observe 50 bbl losses | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 2 | ACHEIVER | MENAM
1356 | 1356 | p/up, m/up and rih 8 ½” bit with fg nbs assy & rih upto 170 m. U | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 2 | PARAMESHWARA | INDIA
1357 | 1357 | l/dn bit, scraper, bit sub & jar ip. R | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 0.5 | PARAMESHWARA | INDIA
1358 | 1358 | pooh 9-5/8” scraper f/ 1292 m to surface. l/dn bit, scraper, bit sub & jar ip. 1 | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 3.5 | PARAMESHWARA | INDIA
1359 | 1359 | pump 30 bbls hivis & circ out. @ 450 gpm, press- 350. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1 | PARAMESHWARA | INDIA
1360 | 1360 | m/up 9-5/8” scraper assy & rih f /1110m to 1292 m. scraped 1240 to 1275 m. | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
1361 | 1361 | RIH w/ 5" DP to Tag TOC, F/ 10100 ft to 10252 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.25 | ACHEIVER | MENAM
1362 | 1362 | Waiting on Cement, monitor well on trip tank. Observed 90 bbls to 110 Bbls Losses/ hr. | 13 | WHITE | 2023-03-06 | WAIT ON CEMENT | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 3.5 | ACHEIVER | MENAM
1363 | 1363 | Disconnect top drive and drop foam Ball, CIRC 3 string volume with 500 gpm 980 psi, Observed 100 bbls to 120 Bbls Losses | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.75 | ACHEIVER | MENAM
1364 | 1364 | CIRC 2 BTM UP with 500 gpm 980 psi, Observed 50bbls to 70 Bbls Losses | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.5 | ACHEIVER | MENAM
1365 | 1365 | Lay down cement head and POOH from 11100 ft to 10100 ft 15 ft/min no over pull | 6 | WHITE | 2023-03-06 | TRIPS | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1.25 | ACHEIVER | MENAM
1366 | 1366 | cementer pump 60 bbl of 80 pcf spacer and pump 53 bbl of 118 pcf cement slurry and pump 11 bbl of 80 pcf spacer and displacement O T with 160 bbl of 74 pcf mud, | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 1 | ACHEIVER | MENAM
1367 | 1367 | Line up to cement manifold flash the line and test same 500/3000 psi 10/10 min U | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
1368 | 1368 | CIRC hole clean thru service hose with 250 gpm 358 psi R | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
1369 | 1369 | pick up and make up cement head and service hose meanwhile HPJSM with crew for cement job 2 | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | SDA | Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + 17. Plug Back ZMS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 3.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:30 I 32 OTHER 2.78 1,006.12 SIZE WEIGHT 10.00 T C. Treating E 1 XO 6.75 1.63 IADC CODE GRADIENT 0.519 PL DE.. TSewsatibnbging 1 XO 6.75 4.00 MANUFACT. VISCOSITY 68 M DP TYPE PV/YP / O F. Other 4 SERIAL NO. GELS / C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 78 STD. D.P. 5.00 7,338.61 CUTTING STRUCTURE x c polymer 30 pac l 15 T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION caustic soda 6 HOURS STANDBY KELLY DOWN TOTAL 8,350.36 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Visually inspect drawworks, TDS and handling equipment. Function test alarms, crown/floor savers + TOTAL DAYWORK 0.00 0.00 ZMS. NO. OF DAYS 48 FROM SPUD CUMULATIVE 50 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 8,764.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDA Job:MRJN-656 Rpt No: 51 Date: 06-Mar-23 | MRJN-656 | MRJN-656 | Mar-23 | 0.5 | ACHEIVER | MENAM
1370 | 1370 | cont rih 8-1/2” fg nbs f/170m to 791m. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-06 | TRIPS | PSW | Held PJSM For RIH with 8-1/2" bit . 17. Plug Back Saver sub 5 1/2 ' connection-505. 18. Squeeze Cement Wash pipe hours: 256 hrs. 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME I SIZE 8.50 WEIGHT T C. Treating E IADC CODE 517 GRADIENT L D. Swabbing MANUFACT. SMITH VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. 77111 GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT 0 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,377 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 0 0 NO A TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 0.152 NO BHA REMARKS: Held PJSM For RIH with 8-1/2" bit . TOTAL DAYWORK 0.00 0.00 Saver sub 5 1/2 ' connection-507. NO. OF DAYS Wash pipe hours: 257 hrs. 1 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: PSW Job:N_1#4 Rpt No: 26 Date: 06-Mar-23 WIRE LINE | PSW-23-3 | N_1#4 | Mar-23 | 1.5 | PARAMESHWARA | INDIA
1371 | 1371 | CONT. POOH WITH BAKER RUNNING TOOLS FROM 4735' TO SURFACE . | 6 | WHITE | 2023-03-06 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 2 | MAIN PASS IV | MENAM
1372 | 1372 | WAITING FOR 150MT BARITE & 150MT D/WATER FOR DRILLING 8-1/2” PHASE. 2 | 23 | WHITE | 2023-03-06 | OTHER3 | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 5.5 | RON TAPPMEYER | INDIA
1373 | 1373 | CLEAR AND CLEAN RIG FLOOR . | 23 | WHITE | 2023-03-06 | OTHER3 | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1374 | 1374 | Continue Pooh 12 1/4'' RSS drilling assy BHA from 783ft to 299ft. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | 6 | WHITE | 2023-03-06 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.25 | MENTOR | WEST AFRICA
1375 | 1375 | Continue Pooh 12 1/4'' RSS drilling assy on 5'' DP from 2707 ft-MD to 783 ft | 6 | WHITE | 2023-03-06 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.25 | MENTOR | WEST AFRICA
1376 | 1376 | Lined up mud pump and pump 25bbls of 12.0 ppg slug. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.5 | MENTOR | WEST AFRICA
1377 | 1377 | Flow checked @ casing shoe, well static. O T | 6 | WHITE | 2023-03-06 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.25 | MENTOR | WEST AFRICA
1378 | 1378 | Continue Pooh 12 1/4'' RSS drilling assy on 5'' DP from 4440 ft-MD to casing shoe 2707 ft-MD. U | 6 | WHITE | 2023-03-06 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 1.5 | MENTOR | WEST AFRICA
1379 | 1379 | Prepare and skid in the cantilever 30ft forward. Secure all opening, Relocate BOP HCR valves, manual valves and other accessories to the BOP setback. Prepare and skid out the cantilever 63ft Aft and secure all openings. Dress and install 5" - 2 7/8" VBR to the LPR. R Continue to assist in R/D the cementing Unit. Carry out running equipment daily checks. Troubleshoot for port FWD crane air starting U O valve. Assist for test fixation system port leg. 1,000 hrs.PM for engine #1 Emergency engine run tested. Shut donw rig air system for T welding job. Remove divertor overboard valve (STBD) for check valve position. 90 days PM for jacking gearbox. House keeping in air T compressor room. General lift on deck support 3rd party team and cargo on quay side H Support Rig skidding G I Assist Demobilization on the equipment N Preload tank inspection Offload drill pipe from barge and lay out Install Air compressor on LER top Roof DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-06 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 94 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 94 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 94 Date: 06-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
1380 | 1380 | Held PJSM with the crew on shift change. R | 23 | WHITE | 2023-03-06 | OTHER3 | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.25 | MENTOR | WEST AFRICA
1381 | 1381 | POOH with 5 '' drill pipe wet from 10015 ft to 4440ft. Hole sleek. | 6 | WHITE | 2023-03-06 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 6.5 | MENTOR | WEST AFRICA
1382 | 1382 | Held pre job safety meeting with crew members on tripping pipe | 23 | WHITE | 2023-03-06 | OTHER3 | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.25 | MENTOR | WEST AFRICA
1383 | 1383 | Flow check at BTM prior to POOH, ( Well static ) DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-06 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.25 | MENTOR | WEST AFRICA
1384 | 1384 | Continue to circulate hole clean with 760 gpm, 4254 psi, 100 rpm, 18-20 torque, Pumped 30 bbls of hi vis sweep and circulate clean. O T | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 4.75 | MENTOR | WEST AFRICA
1385 | 1385 | Took SCR at TD 10,015ft with (Pump #1 20spm=190 psi, 30spm=320 psi, 40spm=470 psi and Pump #2- 20spm= 200psi, R 30spm=320psi, 40spm=470psi.) U | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.5 | MENTOR | WEST AFRICA
1386 | 1386 | Continue Drilling 12-1/4" hole directional from 9629 ft-MD to section TD @ 10015 ft-MD, 7994 ft TVD as per DD instruction with 760 gpm, 4236 psi, 120 rpm, 19-26 torque , 15-27kWOB, Pump sweep every 2 stand drilled, Halliburton MWD took survey on every stand drilled before connection. Up-wt 325k, s/o wt-205k, Rot-wt 255k 10.9 ppg. ( INC-72.51, AZI-302.54) 1 | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 6.5 | MENTOR | WEST AFRICA
1387 | 1387 | Performed trip drill with crew members.20 seconds 2 | 6 | WHITE | 2023-03-06 | TRIPS | SDM | Driller: Akugbor,Isaac 17. Plug Back No accidents no pollution reported. 18. Squeeze Cement Functioned TIW and Gray valves ok. 19. Fishing Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. 20. Directional Work Diverter closer = 5times total. 21. Run/Retrieve Riser Equip. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 22. Surface Testing Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 DRILLER: 23. Other 3 0.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.1 TIME 23:00 I 1 BIT 12.25 1.23 SIZE 12.25 WEIGHT 90.13 T C. Treating E 1 AUTOTR 12.25 21.70 IADC CODE GRADIENT 4.6778 PL DE.. TSewsatibnbging 1 STAB 12.25 6.56 MANUFACT. BAKER VISCOSITY M 12 OTHER 8.00 94.50 TYPE TD506K PV/YP 35/28 O F. Other 4 1 MWD 8.00 23.75 SERIAL NO. 5329430 GELS 13/17 C G. Other 5 5 DC 8.00 156.30 JETS 18,4x16,15 FL. LOSS 3.8 H. Other 6 1 JAR 8.00 32.96 TFA 1.206 pH TOTALS 12.00 12.00 3 DC 8.00 87.56 DEPTH OUT SOLIDS 15.19 DAYWORK TIME SUMMARY 1 XO 8.00 3.24 DEPTH IN 2,807 2 (OFFICE USE ONLY) 12 HWDP 5.00 356.10 TOTAL DRILL 7,208 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 38 DP 5.00 3,656.31 TOTAL HRS 117.5 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. 5.00 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 4,440.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 325,000 REMARKS: Driller: Christopher Odogwu TOTAL DAYWORK 0.00 0.00 No accidents no pollution reported. NO. OF DAYS Functioned TIW and Gray valves ok. 22 FROM SPUD Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. CUMULATIVE 397 Diverter closer = 5times total. ROTATING HOURS Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Driller: Akugbor,Isaac No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs) hrs this shift = 10 (hrs left 272) 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 KPI on slip & cut. NA KPI on slip to slip connection time: KPI-on Tripping in: N/A KPI on Tripping out hole: 857.7ft per hour on open hole. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pip Operations Activities (Continued...) Driller: Christopher Odogwu No accidents no pollution reported. Functioned TIW and Gray valves ok. Diverter insert parker 28'' OD X 17 3/4" ID insert packer date. put in use 2nd October 2022. Diverter closer = 5times total. Wash pipe (300hrs)Total hrs = 0 hrs (272 hrs left) Changed 05-03-2023 Wash pipe inspected. OK. Cumulative wash pipe hrs = 28 hrs KPI on slip & cut. = NA KPI on slip to slip connection time: 5/6mins KPI-on Tripping in: N/A KPI on Tripping out hole: 1539ft per hour. KPI on N/U Bop. KPI on Running Casing. N/A. KPI on BOP Test.N/A KPI on N/D BOP. N/A KPI on L/D Drill pipe. N/A KPI on P/U Drill Pipe. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDM Job:SDM-22-9 Rpt No: 23 Date: 06-Mar-23 | MA84-B | Madu 84 B | Mar-23 | 0.25 | MENTOR | WEST AFRICA
1388 | 1388 | Make up, rack back and lay out 1stand 3.5" DP as per IAT. Work on BOP side outlet installation Dress Ram blocks for installation. 2 Assist deck crew with cargo management. R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 94 Date: 06-Mar-23 | 23 | WHITE | 2023-03-06 | OTHER3 | SDS | Annular BOP changed out on 01/03/2023 17. Plug Back No. Functioned this Tour = 0 Total function = 0 18. Squeeze Cement Upper IBOP changed out on 19. Fishing Due date for change out 20. Directional Work Lower IBOP changed out on 21. Run/Retrieve Riser Equip. Due date for change out 22. Surface Testing Saver Sub changed out on DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Annular BOP changed out on 01/03/2023 TOTAL DAYWORK 0.00 0.00 No. Functioned this Tour = 0 Total function = 0 NO. OF DAYS Upper IBOP changed out on 0 FROM SPUD Due date for change out CUMULATIVE Lower IBOP changed out on ROTATING HOURS Due date for change out DAILY MUD COST ($) TOTAL MUD COST ($) Saver Sub changed out on DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 94 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Elliott Jason Leigh Operations Activities (Continued...) Annular BOP changed out on 01/03/2023 No. Functioned this Tour = 0 Total function = 0 Upper IBOP changed out on Due date for change out Lower IBOP changed out on Due date for change out Saver Sub changed out on No. of connection this tour = Total No. of connections = Wash pipe our this tour = Total wash pipe hours = Driller: Findlay Alexander IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 94 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDS Job:SDS-22-30 Rpt No: 94 Date: 06-Mar-23 WIRE LINE | Warm Stack Crystal SY Singapore | SDS-22-30 | Mar-23 | 12 | SCEPTOR | SOUTH EAST ASIA
1389 | 1389 | Schlumberger redressed grease head and dress up new cable head. | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 2.25 | TENACIOUS | WEST AFRICA
1390 | 1390 | Perform deck management. Meanwhile conduct Bull head operations on LIU - A03. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | 23 | WHITE | 2023-03-06 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 3.25 | TENACIOUS | WEST AFRICA
1391 | 1391 | Install 4-1/2'' handling equipment. P/u and rack 4-1/2'' Riser tubing into derrick. O T | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 0.75 | TENACIOUS | WEST AFRICA
1392 | 1392 | Close crown valve. Break and lay down welltec tool string. Rig down SLB Slick line and E-line. U | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 3 | TENACIOUS | WEST AFRICA
1393 | 1393 | SLB e-line POH with Stoker to surface. R | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1.75 | TENACIOUS | WEST AFRICA
1394 | 1394 | Allow push arms to retract, Attempt to POOH from 6,082' and observed overpull. Bled off 500psi tubing pressure. SLB E-line work string free with 4000lbs max over pull. 2 | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 2.25 | TENACIOUS | WEST AFRICA
1395 | 1395 | Schlumberger / welltec attempt to open FS2 valve with welltec Stroker shifting tool. Lost communication to tool. | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
1396 | 1396 | Schlumberger / welltec attempt to open FS2 valve with welltec Stroker shifting tool - No success. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 2.5 | TENACIOUS | WEST AFRICA
1397 | 1397 | Welltec check and function CCL /Welltec Stroker shifting tool at 5983 ft. schlumberger continue to run in hole - tagged FS2 valve at 6082 ft. | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
1398 | 1398 | Line up cement line and pressure up tubing 500 psi with cement unit . | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
1399 | 1399 | Run in hole with CCL / Welltec Stroker shifting tool from surface to 5983 ft. Stop and take cable tension every 1000 ft. Schlumberger E-line correlate depth. | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 2.25 | TENACIOUS | WEST AFRICA
1400 | 1400 | Make up lubricator. N Line up cement unit flush and fill up riser with 9.5 ppg brine and pressure test lubricator 250/3500 psi 5/5 min. Open crown valve, and confirm TRSV open - locked with 9000 psi. | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 0.75 | TENACIOUS | WEST AFRICA
1401 | 1401 | Pick up Welltec Stroker shifting tool lower in mouse hole and connect together. T Transfer Welltec Stroker shifting tools from mousehole and secure inside slickline BOP. Connect tool string to Schlumberger E-line H and check connectivity. G I | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1.25 | TENACIOUS | WEST AFRICA
1402 | 1402 | Rig up E-line sheaves and pass line through same. Pick up E-Line grease head, make up to lubricator and connect control lines. T | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 1 | TENACIOUS | WEST AFRICA
1403 | 1403 | PJSM for rig up E- line. U O | 23 | WHITE | 2023-03-06 | OTHER3 | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 0.25 | TENACIOUS | WEST AFRICA
1404 | 1404 | Connect cable head to Welltec tool string on cantilever deck and function test Welltec tools. R | E | WHITE | 2023-03-06 | TESTING | SDT | All job tasks accompanied with relevant PTW, TBRA or prompt cards 17. Plug Back Saver sub connections: 0 18. Squeeze Cement TDS rotating hours:0 19. Fishing Drilling rotating hours: 0 20. Directional Work Circulation hrs : 0 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 3.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing 11.75 8.75 M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: All job tasks accompanied with relevant PTW, TBRA or prompt cards TOTAL DAYWORK 0.00 0.00 Saver sub connections: 0 NO. OF DAYS TDS rotating hours:0 19 FROM SPUD Drilling rotating hours: 0 CUMULATIVE 675 Circulation hrs : 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDT Job:SDT-22-17 Rpt No: 35 Date: 06-Mar-23 | Lifua A-04 | SDT-22-17 | Mar-23 | 0.5 | TENACIOUS | WEST AFRICA
1405 | 1405 | L/D RUNNING TOOLS ASSY . | 6 | WHITE | 2023-03-06 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.5 | MAIN PASS IV | MENAM
1406 | 1406 | Daily rounds and checks. O T Pot water tested & recorded. Weekly Equipment running hours. Full set of engine soot filters made up. Weekly/Monthly PMR’s IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 7 Date: 06-Mar-23 | 23 | WHITE | 2023-03-06 | OTHER3 | SDF | Disassemble ST 160 for maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 7 Date: 06-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1407 | 1407 | Wall thickness checks in T/T2 and sand traps. Continue needle gunning and painting in water maker room. Disassemble ST 160 clean and send parts to mechanical work shop. Continue servicing tongs, slips and dog collars. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-06 | OTHER3 | SDF | Disassemble ST 160 for maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 7 Date: 06-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1408 | 1408 | DROP BALL & BALL LAND APPLY 1600 PSI SET 9 5/8" QTM PKR, BLEED TO 0 PSI & CLOSE BACK PT TCA & PKR 1000 PSI , BLEED TO 0 PSI , 20K PULL & PUSH TEST, APPLY 2400 PSI TO RELEASE SERVICE TOOLS , STING OUT CLOSE MFIV , FILL UP TCA HOLE STATIC , STING IN OPEN MFIV OBSERVE HOLE IN LOSS , STING OUT CLOSE MFIV, CLOSE BACK APPLE 1000 PSI TO TCA & TEST MFIV. - TOP OF MIDDLE COMPLETION @ 4563'. | 5 | YELLOW | 2023-03-06 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1.75 | MAIN PASS IV | MENAM
1409 | 1409 | RECORD P/U 170K S/O 165K & CIRC 1.5 STRING VOLUME W/ 3 BPM 40 PSI. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1.25 | MAIN PASS IV | MENAM
1410 | 1410 | CONT RIH W/ 4 1/2" MIDDLE COMPLETION ON 5" DP F/ 2987' TO SETTING DEPTH @ 7440', 3 MIN PER STD AS PER SLB. | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 3 | MAIN PASS IV | MENAM
1411 | 1411 | M/U 2 EACH X-O'S ON 5" DP & M/U T.D.S. BREAK CIRC W/ 3 BPM 20 PSI & RECORD P/U 94K S/O 94K @ 2987'. O T | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.5 | MAIN PASS IV | MENAM
1412 | 1412 | R/D ITS POWER TONG & C/O HANDLING TOOLS TO 5" DP. U | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1413 | 1413 | CONT P/U & RIH X-O , 1 X JT 5 1/2" ,INNER STRING , 9 5/8" QTM PKR, F/ 2785' T/ 2892'. R | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1 | MAIN PASS IV | MENAM
1414 | 1414 | HPJSM, POH W/ 9 5/8" RUNNING TOOLS ON 5" DP F/ 4563' T/ 4150' CONTROL SPEED 1.5 MIN PER STD. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | 6 | WHITE | 2023-03-06 | TRIPS | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1415 | 1415 | CHANGE OUT HANDLING EQUIP TO 5 1/2". 2 | 23 | WHITE | 2023-03-06 | OTHER3 | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1416 | 1416 | HPJSM, P/U & RIH 4 1/2" #11.6 MIDDLE COMPLETION AS PER TALLY TO 2790'. MONITOR WELL ON T-T WELL STATIC. | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 2.75 | MAIN PASS IV | MENAM
1417 | 1417 | HPJSM , P/UP M/UP 4.5'' MULL SHOE . DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.25 | MAIN PASS IV | MENAM
1418 | 1418 | R/UP 4.5'' ITS HANDLING GEAR . | 23 | WHITE | 2023-03-06 | OTHER3 | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.75 | MAIN PASS IV | MENAM
1419 | 1419 | L/D TEST PLUG ASSY AND LANDING JOINT . | 15 | WHITE | 2023-03-06 | TEST BOP | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.5 | MAIN PASS IV | MENAM
1420 | 1420 | PRESSURE TEST TOP RAMS AND ANNULAR 300/3000 PSI AS PER ARAMCO . | 15 | WHITE | 2023-03-06 | TEST BOP | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.75 | MAIN PASS IV | MENAM
1421 | 1421 | P/UP M/UP 4.5'' LANDING JOINT AND M/UP TEST PLUG ASSY . | 15 | WHITE | 2023-03-06 | TEST BOP | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 0.5 | MAIN PASS IV | MENAM
1422 | 1422 | HPJSM, R/U EX-PRO SLICK LINE & DRIFT TO 2785' W/ 3.875" & R/D S/L. | E | WHITE | 2023-03-06 | TESTING | MP4 | NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I 17. Plug Back BOP, GOOD COMM, PLAN TOFS. 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 1.50 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 3.1 TIME 23:45 I SIZE 16.00 WEIGHT 82.00 T C. Treating E IADC CODE GRADIENT 4.2558 L D. Swabbing MANUFACT. NOV VISCOSITY 40 P E. Testing 2.00 8.50 M TYPE PV/YP / O F. Other 4 SERIAL NO. 58323 GELS / C G. Other 5 JETS 12x10 FL. LOSS H. Other 6 TFA 0.920 pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 4,917 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: NO ACC ,NO POLL REPORTED, CHECKED C.O.M. / KEMS. FUNCTION TEST FOSV , UPPER I TOTAL DAYWORK 0.00 0.00 BOP, GOOD COMM, PLAN TOFS. NO. OF DAYS 33 FROM SPUD CUMULATIVE 2,675 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 2,896.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP4 Job:RBYN 65 Rpt No: 36 Date: 06-Mar-23 | RBYN 65 | RBYN 65 | Mar-23 | 1 | MAIN PASS IV | MENAM
1423 | 1423 | Con't RIH with 6-1/8" AGS BHA on 4" DP ( Inside 7" CSG shoe ) from 492 mMD to 2546mMD. | 6 | WHITE | 2023-03-06 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 2 | ENTERPRISE | MENAM
1424 | 1424 | M/U TDS and function test MWD tools as per MWD instruction with MW 1.32 SG SDF, 763 lpm, 1965-2531 psi. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
1425 | 1425 | Daily rounds and checks. NDOR readings recorded. Pot water tested & recorded. 1 Weekly Equipment running hours. R Full set of engine soot filters made up. U Weekly/Monthly PMR’s O T Iron Roughneck has been powerwashed. | 23 | WHITE | 2023-03-06 | OTHER3 | SDF | Disassemble ST 160 for maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 7 Date: 06-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1426 | 1426 | Continue drilling 6-1/8" hole (AGS/PWD/MWD/LWD-TC) from 3745 mMD to 3763mMD, 2565 mTVD with 1.32 SG SDF, 750 lpm, 2400- 2650 psi, 180 rpm, TQ: 10-13 kft-lbs, WOB 10-12 klbs as per DD/MWD instruction. P/U Wt to 420 Klbs not break over, S/O 167 k, ROT 229 k. Back ream TQ:11 -13 kft. Note: P/U Wt, not break over, back ream 1 single every stand and wait for take survey after connection. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.5 | ENTERPRISE | MENAM
1427 | 1427 | Continue circulate and weight up mud to 1.44 SG, with 520LPM, 1480 psi, 80 RPM, 9-10K ft-lbs. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.5 | ENTERPRISE | MENAM
1428 | 1428 | Drop carbide and perform 10 min, static test. | 23 | WHITE | 2023-03-06 | OTHER3 | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1429 | 1429 | Circulate and weight up MW to 1.42 SG, with 120 RPM, 10-12k ft-lbs, 633 LPM, 2400-2500 psi O T | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.5 | ENTERPRISE | MENAM
1430 | 1430 | Continue drilling 6-1/8" hole (AGS/PWD/MWD/LWD-TC) from 3763 mMD to 3879 mMD/ 2645.42m-MD TVD with 1.39 SG SDF, 750- 633 lpm, 2500-2800psi, 180-220 rpm, TQ: 11-13 kft-lbs, WOB 10-12 klbs as per DD/MWD instruction. P/U Wt not break over, S/O 174 k, ROT 230 k. Back ream TQ:11 -13 kft. 2 Note: P/U Wt, not break over, back ream 1 single every stand and wait for take survey after connection. Cycle pump for FG/UG as R per DD. U | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 8.75 | ENTERPRISE | MENAM
1431 | 1431 | Continue drilling 6-1/8" hole (AGS/PWD/MWD/LWD-TC) from 3745 mMD to 3763mMD, 2565 mTVD with 1.32 SG SDF, 750 lpm, 2400-2650 psi, 180 rpm, TQ: 10-13 kft-lbs, WOB 10-12 klbs as per DD/MWD instruction. P/U Wt to 420 Klbs not break over, S/O 167 DEPTH INTERVAL DRILL k, ROT 229 k.F BOaRcMkA rTeIaOmN TQ:11 -13 kft. ROTARY WT. PUMP NO 3 PUMP PUMP PUMP TOTAL CORE PUMP FROM TO RCEOARME NO. Note: P(/SUH WOWt, nCoOtR bEr eRaEkC oOvVeErR, bYa)ck ream 1ST sAPiEBnEgLlDEe eveBOrINyT staPnRdE aSnSd wLSIaNIiZtE EfRor tSaPkMe suLrSIvNIeZEyER aftSerP MconLnSIeNIcZEtEiRon.SPM LSINIZEER SPM OPUUTMPUPT 12346 12726 Drill 80% CLAY, 20% SAND 220 10 6.500 32 4.3 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 12,726 39.64 228855..4444 8,708.7 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 1.5 | ENTERPRISE | MENAM
1432 | 1432 | Continue drilling 6-1/8" hole (AGS/PWD/MWD/LWD-TC) from 3651 mMD to 3745mMD, 2550 mTVD with 1.32 SG SDF, 880 lpm 2400-2650 psi, 180 rpm, TQ: 10-13 kft-lbs, WOB 10-12 klbs as per DD/MWD instruction. With 880 lpm Observed seepage loss with loss rate 6 BPH. Correction after kelly down stand. With 800 lpm – no loss. Reduce flow rate to 750 lpm – no loss. P/U Wt not break over, S/O 167 k, ROT 229 k. Back ream TQ:11 -13 kft. Note: P/U Wt to 420 Klbs, not break over, back ream 1 single every stand and wait for take survey after connection. | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 5 | ENTERPRISE | MENAM
1433 | 1433 | Circulate bottom up. Gas reduce to 0.11% . with MW 1.32Sg SDF, 879 lpm, 120 rpm, 3210- 3225 psi TQ; 8-10 kft-lbs. Note: - Max gas: 32.54 %/BG 0.10% - Bottom up gas 0.10%/BG 0.10%. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.75 | ENTERPRISE | MENAM
1434 | 1434 | Drilling 6-1/8" hole (AGS/PWD/MWD/LWD-TC) from 3648 mMD to 3651 mMD, 2477.48mTVD with 1.32 SG SDF, 879 lpm, 3010- 3070 psi, 190 rpm, tq 10-13 kft-lbs, WOB 10-14 klbs as per DD/MWD instruction. P/U 354 klbs, S/O 160 klbs, R/T 221 klbs. Observed gas increase to 20%. Stop drilling and P/U off bottom. | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1435 | 1435 | Make up TDS fill up string. Ream down 6-1/8" BHA (AGS/MWD) MWD log down to bottom with speed 110 m/hr. from 3619 m to O T 3648m with 740 lpm, 2180 psi, 80 rpm, TQ: 8 - 10 klbs-ft. | 3 | WHITE | 2023-03-06 | REAMING | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
1436 | 1436 | Con't RIH with 6-1/8" AGS BHA on 4" DP ( Open hole ) from 3254 mMD to 3619mMD. U | 6 | WHITE | 2023-03-06 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.5 | ENTERPRISE | MENAM
1437 | 1437 | M/D TDS and check MWD tool static temperature. with 765 lpm, 2571 psi. R | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.25 | ENTERPRISE | MENAM
1438 | 1438 | Con't RIH with 6-1/8" AGS BHA on 4" DP ( open hole ) from 2546 mMD to 3254mMD. 1 | 6 | WHITE | 2023-03-06 | TRIPS | 8768309 | TBRA before do the job. 17. Plug Back Use PBED process. 18. Squeeze Cement Hand free operation. 19. Fishing Stop the job if unsafe 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.6 TIME 23:59 I 1 BIT 6.13 0.66 SIZE 6.13 WEIGHT 12.00 T C. Treating E 1 OTHER 6.13 13.78 IADC CODE GRADIENT 0.6228 PL DE.. TSewsatibnbging 1 MWD 5.75 94.95 MANUFACT. NOV VISCOSITY 71 M 5 HWDP 4.00 156.79 TYPE TKC46-F1 PV/YP / O F. Other 4 1 JAR 5.00 24.48 SERIAL NO. S287640 GELS / C G. Other 5 15 HWDP 4.00 470.70 JETS 4x12 FL. LOSS H. Other 6 TFA 0.442 pH TOTALS 12.00 12.00 DEPTH OUT 12,726 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 11,969 2 (OFFICE USE ONLY) TOTAL DRILL 758 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 15.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 125 STD. D.P. 5.00 11,874.54 CUTTING STRUCTURE T HOURS WITHOUT D.P. 2 SNG. D.P. 5.00 63.35 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.13 0 0 WT A 2 TOTAL 12,726.38 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 230,000 X 1 NO TD REMARKS: TBRA before do the job. TOTAL DAYWORK 0.00 0.00 Use PBED process. NO. OF DAYS Hand free operation. 8 FROM SPUD Stop the job if unsafe CUMULATIVE 69 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 8768309Job:SDE-23-6 Rpt No: 10 Date: 06-Mar-23 WIRE LINE | SDE-23-6 | PLWE-18 | Mar-23 | 0.75 | ENTERPRISE | MENAM
1439 | 1439 | Wall thickness checks in T/T2 and sandtraps. Continue needle gunning and painting in water maker room. Disassemble ST 160 clean and send parts to mechanical work shop. 2 Continue servicing tongs, slips and dogcollars. R Review TBRA's. U | 23 | WHITE | 2023-03-06 | OTHER3 | SDF | Disassemble ST 160 for maintenance. 17. Plug Back 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Shipyard work scope. TOTAL DAYWORK 0.00 0.00 NO. OF DAYS 0 FROM SPUD CUMULATIVE 0 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: SDF Job:SDF-23-2 Rpt No: 7 Date: 06-Mar-23 | SDF-23-2 | SDF-23-2 | Mar-23 | 6 | FORTRESS | NORTH SEA
1440 | 1440 | CONTINUE RIH BAKER 8 1/2" LWD ASSY ON BHA & DP F/ 1380 M. FILL UP EVERY 10 STAND & CIRCULATE AS PER BAKER INSTRUCTION. RELOG F/2270 M TO 2290 M. | 6 | WHITE | 2023-03-06 | TRIPS | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 4.5 | RON TAPPMEYER | INDIA
1441 | 1441 | CONTINUE RIH BAKER 8 1/2" ASSY ON BHA F/ 25 M TO 226 M. (P/UP D/JAR F/DECK) JAR BRT @ 1000 HRS. | 6 | WHITE | 2023-03-06 | TRIPS | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1 | RON TAPPMEYER | INDIA
1442 | 1442 | CIRC HOLE CLEAN AND REDUCE MUD WEIGHT GRADUALLY TO 67+ PCF DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 4.75 | HIGH ISLAND IV | MENAM
1443 | 1443 | DRILL OUT NEW FORMATION FROM 10831 FT TO 10847 FT WITH 300 GPM 80 RPM , 2150 PSI , 18 K WOB | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1444 | 1444 | FLOW CHECK MONITOR WELL ON TRIP TANK WELL STATIC | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1445 | 1445 | DRILL OUT 7" SHOE FROM 10827 FT TO 10831 FT | 3 | WHITE | 2023-03-06 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1446 | 1446 | DRILL OUT HARD CEMENT FROM 10807 FT TO 10827 FT | 3 | WHITE | 2023-03-06 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
1447 | 1447 | PRESSURE TEST LINER TO 1000 PSI , GOOD TEST O T | 23 | WHITE | 2023-03-06 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1448 | 1448 | CIRCULATE WITH 300 GPM, 1720 PSI, 20 RPM. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1449 | 1449 | PUMP 25 BBLS SWEEP AND CIRC HOLE CLEAN WITH 300 GPM , 2100 PSI U | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1450 | 1450 | DRILL OUT F.C FROM 10704 FT TO 10706 FT 1 | 3 | WHITE | 2023-03-06 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1451 | 1451 | DRILL OUT HARD CEMENT FROM 10660 FT TO 10704 FT | 3 | WHITE | 2023-03-06 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1452 | 1452 | CONTINUE DRILL OUT LANDING COLLAR @ 10660 FT | 3 | WHITE | 2023-03-06 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2.5 | HIGH ISLAND IV | MENAM
1453 | 1453 | CONTD DRLG 12-1/4" DIR HOLE WITH HLB RSS+MWD ASSY F/1354M TO 1642M. REAM TWICE EACH CONNECTION, PUMP 20 BBL HI-WT PILL EVERY STAND DRILLED & RECORD SURVEY AFTER CONECTION. DRILLING PARA:- WOB-10-15KIPS, GPM-975, PR-2650-2700 PSI, RPM-160, TQ- 6-9 KLBS-FT. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | T12 | HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. 17. Plug Back SAVER SUB CONNECTION - 5 18. Squeeze Cement TOTAL CONNECTION - 124 19. Fishing WASH PIPE HRS - 11 20. Directional Work TOTAL WASH PIPE HRS: - 331.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY.. HELD PJSM WITH 22. Surface Testing PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PRO C DERDIULLREER ,: ROLES AND 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 0.98 SIZE 12.25 WEIGHT 10.50 10.60 10.60 T C. Treating E 9 MWD 8.25 64.76 IADC CODE 1 GRADIENT 0.545 0.5501 0.5501 PL DE.. TSewsatibnbging 1 XO 8.00 3.68 MANUFACT. HALLIBTN VISCOSITY 65 67 71 M 9 HWDP 6.63 272.74 TYPE 519 PV/YP 29/26 / / O F. Other 4 1 JAR 8.00 31.10 SERIAL NO. 13768668 GELS 10/30 / / C G. Other 5 4 HWDP 8.00 120.01 JETS 7x14 FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA 1.052 pH TOTALS 12.00 12.00 3 HWDP 5.50 92.16 DEPTH OUT SOLIDS 14 DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 1,639 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 13 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 5.50 4,709.58 CUTTING STRUCTURE NOVATEC 50 MEGA MUL 110 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.50 63.32 INNER OUTER DULL CHAR. LOCATION CACL2 40 LIME 40 HOURS STANDBY KELLY DOWN 25.16 G SEAL PLUS 10 Vin seal plus 30 2 TOTAL 5,387.14 BEARINGS GAUGE OTHER REASON CACo3 blend 40 barite 12 SEALS DULL PULLED WT. OF STRING 190,000 REMARKS: HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 10 NO. OF DAYS TOTAL CONNECTION - 134 10 FROM SPUD WASH PIPE HRS - 11.5 CUMULATIVE TOTAL WASH PIPE HRS: - 343 ROTATING HOURS DEBRIEF:2- MAKING CONNECTIONS USING MANUAL TONGS. INSPECTION OF TOOLS AND EQUIPMENTS DAILY MUD COST ($) 8,160.00 TOTAL MUD COST ($) 12,960.00 BEFORE COMMENCING THE JOB, STAB PIPE WITH GRAB TOOL. ST A YD RCILLELEARR: TONGS FROM TONG IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. SAVER SUB CONNECTION - 5 TOTAL CONNECTION - 124 WASH PIPE HRS - 11 TOTAL WASH PIPE HRS: - 331.5 DEBRIEF:1- DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY.. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTIONS. CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. SAVER SUB CONNECTION - 10 TOTAL CONNECTION - 134 WASH PIPE HRS - 11.5 TOTAL WASH PIPE HRS: - 343 DEBRIEF:2- MAKING CONNECTIONS USING MANUAL TONGS. INSPECTION OF TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, STAB PIPE WITH GRAB TOOL. STAY CLEAR TONGS FROM TONG RADIUS (ARC) . CLEARED ESCAPE ROUTES, STAYING CLEAR FROM LINE OF FIRE, PROPER HAND PLACEMENT. JOB DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 12 | TRIDENT XII | INDIA
1454 | 1454 | OBSD LINER SEAL OF MP# 1 LEAKING. REPLACED SAME. R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 4442 5387 Drill SHALE AND LIME STONE 160 10000 2700 6.500 94 6.500 94 972.524 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 4,510 25.88 110011..0022 4,358.6 1,001.5 4,604 27 9999..5522 4,442.4 1,043.1 4,699 26.94 9988..4455 4,527.0 1,086.1 4,794 27.75 110000..22 4,611.2 1,129.6 4,894 30.15 110044..3399 4,699.0 1,178.2 4,988 32.97 110066..2255 4,778.7 1,227.0 TIME LOG 5,E0L7A9PSE3D5.4C8ODE 110066..55 4,854.3 1,278.2 5,174 37.63 110077..7733 4,930.4 1,334.3 5,269 40.12 110077..8833 5,004.6 1,393.8 DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 8 | RED | 2023-03-06 | REPAIR RIG | T12 | HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. 17. Plug Back SAVER SUB CONNECTION - 5 18. Squeeze Cement TOTAL CONNECTION - 124 19. Fishing WASH PIPE HRS - 11 20. Directional Work TOTAL WASH PIPE HRS: - 331.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY.. HELD PJSM WITH 22. Surface Testing PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PRO C DERDIULLREER ,: ROLES AND 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 0.98 SIZE 12.25 WEIGHT 10.50 10.60 10.60 T C. Treating E 9 MWD 8.25 64.76 IADC CODE 1 GRADIENT 0.545 0.5501 0.5501 PL DE.. TSewsatibnbging 1 XO 8.00 3.68 MANUFACT. HALLIBTN VISCOSITY 65 67 71 M 9 HWDP 6.63 272.74 TYPE 519 PV/YP 29/26 / / O F. Other 4 1 JAR 8.00 31.10 SERIAL NO. 13768668 GELS 10/30 / / C G. Other 5 4 HWDP 8.00 120.01 JETS 7x14 FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA 1.052 pH TOTALS 12.00 12.00 3 HWDP 5.50 92.16 DEPTH OUT SOLIDS 14 DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 1,639 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 13 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 5.50 4,709.58 CUTTING STRUCTURE NOVATEC 50 MEGA MUL 110 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.50 63.32 INNER OUTER DULL CHAR. LOCATION CACL2 40 LIME 40 HOURS STANDBY KELLY DOWN 25.16 G SEAL PLUS 10 Vin seal plus 30 2 TOTAL 5,387.14 BEARINGS GAUGE OTHER REASON CACo3 blend 40 barite 12 SEALS DULL PULLED WT. OF STRING 190,000 REMARKS: HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 10 NO. OF DAYS TOTAL CONNECTION - 134 10 FROM SPUD WASH PIPE HRS - 11.5 CUMULATIVE TOTAL WASH PIPE HRS: - 343 ROTATING HOURS DEBRIEF:2- MAKING CONNECTIONS USING MANUAL TONGS. INSPECTION OF TOOLS AND EQUIPMENTS DAILY MUD COST ($) 8,160.00 TOTAL MUD COST ($) 12,960.00 BEFORE COMMENCING THE JOB, STAB PIPE WITH GRAB TOOL. ST A YD RCILLELEARR: TONGS FROM TONG IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. SAVER SUB CONNECTION - 5 TOTAL CONNECTION - 124 WASH PIPE HRS - 11 TOTAL WASH PIPE HRS: - 331.5 DEBRIEF:1- DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY.. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTIONS. CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. SAVER SUB CONNECTION - 10 TOTAL CONNECTION - 134 WASH PIPE HRS - 11.5 TOTAL WASH PIPE HRS: - 343 DEBRIEF:2- MAKING CONNECTIONS USING MANUAL TONGS. INSPECTION OF TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, STAB PIPE WITH GRAB TOOL. STAY CLEAR TONGS FROM TONG RADIUS (ARC) . CLEARED ESCAPE ROUTES, STAYING CLEAR FROM LINE OF FIRE, PROPER HAND PLACEMENT. JOB DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 1 | TRIDENT XII | INDIA
1455 | 1455 | DRILL OUT HARD CEMENT FROM 10706 FT TO 10807 FT WITH 300 GPM , 2100 PSI, 80 RPM R | 3 | WHITE | 2023-03-06 | REAMING | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1456 | 1456 | FLOW CHECK. WELL STATIC. | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1 | HIGH ISLAND IV | MENAM
1457 | 1457 | PUMP SLUG. 2 | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1458 | 1458 | POOH WITH WITH CLEAN OUT ASSEMBLY ON 5'' DRILL PIPE FROM 10847 FT TO 10039 FT. R | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1459 | 1459 | RIH 6 1/8'' RSS ASSEMBLY ON 4'' DRILL PIPE FROM 393 FT TO 1800 FT. | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1460 | 1460 | CONTINUE TO MAKE UP 6 1/8'' RSS ASSEMBLY FROM 80 FT TO 393 FT. | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1461 | 1461 | LOAD RADIO ACTIVE SOURCE. | 20 | WHITE | 2023-03-06 | DIRECTIONAL WORK | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1462 | 1462 | HELD PJSM FOR HANDLING RADIO ACTIVE SOURCE. | 20 | WHITE | 2023-03-06 | DIRECTIONAL WORK | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1463 | 1463 | PICK AND MAKE UP 6 1/8'' SLB RSS BHA TO 80 FT. | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
1464 | 1464 | CHANGE TO 4'' HANDLING EQUIPMENT. | 23 | WHITE | 2023-03-06 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1465 | 1465 | INSTALL WEAR BUSHING. | 23 | WHITE | 2023-03-06 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
1466 | 1466 | MAKE UP JETTING SUB AND JETTED ACROSS WELL HEAD CAVITY WITH 450 GPM, 50 PSI, 15 RPM. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1467 | 1467 | CHANGE TO 5'' HANDLING EQUIPMENT. | 23 | WHITE | 2023-03-06 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1468 | 1468 | POOH FROM 591 TO SURFACE. BREAK AND LAY DOWN BIT AND BIT SUB. | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.75 | HIGH ISLAND IV | MENAM
1469 | 1469 | FLOW CHECK. WELL STATIC. | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1470 | 1470 | POOH CLEAN OUT ASSEMBLY ON 4'' DRILL PIPE FROM 6739 FT TO 591 FT. | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 2 | HIGH ISLAND IV | MENAM
1471 | 1471 | HELD SAFETY STAND DOWN MEETING. | 23 | WHITE | 2023-03-06 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.5 | HIGH ISLAND IV | MENAM
1472 | 1472 | POOH CLEAN OUT ASSEMBLY ON 4'' DRILL PIPE FROM 10039 FT TO 6739 FT. O T | 6 | WHITE | 2023-03-06 | TRIPS | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 1.25 | HIGH ISLAND IV | MENAM
1473 | 1473 | CHANGE TO 4'' HANDLING EQUIPMENT. U | 23 | WHITE | 2023-03-06 | OTHER3 | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1474 | 1474 | CONT DRLG 12-1/4" DIR HOLE WITH HLB RSS+MWD ASSY F/ 1199 TO 1354 M. REAM TWICE EACH STAND, PUMP 20 BBL HI- WT PILL EVERY STAND DRILLED & TAKE SURVEY EVERY SINGLE DRILLED. DRILLING PARA:- WOB – 10-15 KIPS, GPM-940, PR-2380 PSI, RPM-155, TORQUE 5/6 K.LBS. 1 | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | T12 | HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. 17. Plug Back SAVER SUB CONNECTION - 5 18. Squeeze Cement TOTAL CONNECTION - 124 19. Fishing WASH PIPE HRS - 11 20. Directional Work TOTAL WASH PIPE HRS: - 331.5 21. Run/Retrieve Riser Equip. DEBRIEF:1- DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY.. HELD PJSM WITH 22. Surface Testing PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PRO C DERDIULLREER ,: ROLES AND 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.1 TIME 12:00 18:00 23:45 I 1 BIT 12.25 0.98 SIZE 12.25 WEIGHT 10.50 10.60 10.60 T C. Treating E 9 MWD 8.25 64.76 IADC CODE 1 GRADIENT 0.545 0.5501 0.5501 PL DE.. TSewsatibnbging 1 XO 8.00 3.68 MANUFACT. HALLIBTN VISCOSITY 65 67 71 M 9 HWDP 6.63 272.74 TYPE 519 PV/YP 29/26 / / O F. Other 4 1 JAR 8.00 31.10 SERIAL NO. 13768668 GELS 10/30 / / C G. Other 5 4 HWDP 8.00 120.01 JETS 7x14 FL. LOSS H. Other 6 1 XO 8.00 3.64 TFA 1.052 pH TOTALS 12.00 12.00 3 HWDP 5.50 92.16 DEPTH OUT SOLIDS 14 DAYWORK TIME SUMMARY DEPTH IN 3,748 2 (OFFICE USE ONLY) TOTAL DRILL 1,639 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 13 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 50 STD. D.P. 5.50 4,709.58 CUTTING STRUCTURE NOVATEC 50 MEGA MUL 110 T HOURS WITHOUT D.P. 2 SNG. D.P. 5.50 63.32 INNER OUTER DULL CHAR. LOCATION CACL2 40 LIME 40 HOURS STANDBY KELLY DOWN 25.16 G SEAL PLUS 10 Vin seal plus 30 2 TOTAL 5,387.14 BEARINGS GAUGE OTHER REASON CACo3 blend 40 barite 12 SEALS DULL PULLED WT. OF STRING 190,000 REMARKS: HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. TOTAL DAYWORK 0.00 0.00 SAVER SUB CONNECTION - 10 NO. OF DAYS TOTAL CONNECTION - 134 10 FROM SPUD WASH PIPE HRS - 11.5 CUMULATIVE TOTAL WASH PIPE HRS: - 343 ROTATING HOURS DEBRIEF:2- MAKING CONNECTIONS USING MANUAL TONGS. INSPECTION OF TOOLS AND EQUIPMENTS DAILY MUD COST ($) 8,160.00 TOTAL MUD COST ($) 12,960.00 BEFORE COMMENCING THE JOB, STAB PIPE WITH GRAB TOOL. ST A YD RCILLELEARR: TONGS FROM TONG IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. SAVER SUB CONNECTION - 5 TOTAL CONNECTION - 124 WASH PIPE HRS - 11 TOTAL WASH PIPE HRS: - 331.5 DEBRIEF:1- DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY.. HELD PJSM WITH PERSONNEL INVOLVED IN JOB. DISCUSSED ABOUT THE TASK PROCEDURE , ROLES AND RESPONSIBILITIES.INSPECTED EQUIPMENTS TO BE USED. ARRANGED WORK AREA TO AVOID SLIP AND TRIP HAZARDS. STAYING CLEAR FROM LINE OF FIRE WHILE TORQUING CONNECTIONS. CORRECT MANUAL HANDLING. SAFE HAND/BODY PLACEMENTS. EFFECTIVE COMMUNICATION. Operations Activities (Continued...) HELD PJSM ABOUT DRILLING 12-1/4" DIRECTIONAL HOLE WITH HLB RSS+MWD ASSY. SAVER SUB CONNECTION - 10 TOTAL CONNECTION - 134 WASH PIPE HRS - 11.5 TOTAL WASH PIPE HRS: - 343 DEBRIEF:2- MAKING CONNECTIONS USING MANUAL TONGS. INSPECTION OF TOOLS AND EQUIPMENTS BEFORE COMMENCING THE JOB, STAB PIPE WITH GRAB TOOL. STAY CLEAR TONGS FROM TONG RADIUS (ARC) . CLEARED ESCAPE ROUTES, STAYING CLEAR FROM LINE OF FIRE, PROPER HAND PLACEMENT. JOB DONE SAFELY. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: T12 Job:BE#7XH Rpt No: 10 Date: 06-Mar-23 | BE#7XH | BE#7XH | Mar-23 | 11 | TRIDENT XII | INDIA
1475 | 1475 | PERFORM SHALLOW TEST WITH 200 GPM AND 850 PSI. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 Tour 2 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 20 | WHITE | 2023-03-06 | DIRECTIONAL WORK | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1476 | 1476 | Work with electrician in taking Armature and field insulation reading on TDS. Work with Mechanic on installation of Top Drive blower vent. Work with Mechanic in replacing hydraulic hose on TDS. 2 Carry out inspection on crown, grease and secure cable guards on crown sheaves. R | 23 | WHITE | 2023-03-06 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
1477 | 1477 | R/D 5'' DP elevator from TDS bail and R/U 5 1/2'' DP elevator. | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
1478 | 1478 | Clean, clear rig floor and remove all redundant item with crane out of rig floor. | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1479 | 1479 | P/U MWD tool ( ADR+PM collar) from cantilever deck, break put and laid down same. O T P/U MWD tool from derrick, MWD tool (AFR+Dummy PCDC+ADR+CTN+ALD), break and laid down same. | 6 | WHITE | 2023-03-06 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 3.25 | BALTIC | WEST AFRICA
1480 | 1480 | MU wear bushing to running tool + X-over to 5'' dp. Lower tool/wear bushing assy through BOP stack and land on the load shoulder 2 in compact spool at 14.10m. Disengage running tool from WB by rotating 5'' dp counter clockwise 1/4 turn. POOH and lay down R running tool. Rack back stand on derrick. U | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.75 | BALTIC | WEST AFRICA
1481 | 1481 | Changed out 5 1/2'' dp to 5'' dp elevator. POOH and lay down test plug assy | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 3.25 | BALTIC | WEST AFRICA
1482 | 1482 | Continue to break out and lay down test assy. plug | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.25 | BALTIC | WEST AFRICA
1483 | 1483 | Held PJSM and discussed with all involved and AOS personnel. | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1484 | 1484 | Disconnect HP hose. R/D SES assy. L/D 1 x 5.5'' dp and cross over. PU 1 X 5'''dp and RIH, screw on test plug. Close lower pipe ram. Pressure test 2 7/8'' x 5 1/2'' variable ram. 300/5000 psi. Bleed of pressure to 0psi. Pressure test Annular on 5'' dp 300/3500psi DEPTH INTERVAL DRILL for 5/5mins okF.BOlReMedA ToIfOf Npressure 0 psi, ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP 1F1R:O30M 12:T0O0 R0C.EO5AR0ME N2O3. Break o(uStH aOnWd ClaOyR dEo RwEnC SOEVSE RaYs)sy. STAPEBELDE BOINT PRESS LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM LSINIZEER SPM OPUUTMPUPT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.25 | BALTIC | WEST AFRICA
1485 | 1485 | R/down Hose. Unscrew Test assy from Test Plug + Pooh to surface. Pressure test Blind Shear Ram against Choke and lower Kill coflex hoses against valves # 7 & # 9 on Choke and Kill Manifold. 300/3500 psi, 5/5mins. Good test. bled off pressure to 0 psi. | 15 | WHITE | 2023-03-06 | TEST BOP | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1486 | 1486 | Test # 2. Line up and Pressure test Lower Pipe Ram - 2 7/8" x 5 1/2" against Lower Kill HCR + First FOSV. 300/5000 psi, 5/5min. R Good test. Good test. bled off pressure to 0 psi. U Test # 3. Line up and Pressure test 5 1/2'' Fixed pipe Rams against Lower Kill Manual valve + Choke HCR, + First FOSV O T to.300/5000 psi, 5/5min. Good test. Good test. bled off pressure to 0 psi. Test # 4. Line up and Line up and Pressure test 5 1/2'' Fixed pipe ram against Choke Manual valve + Lower IBOP, 300/5000 psi, 5/5min. Good test. Good test. bled off pressure to 0 psi. Test # 5. Line up and Pressure test 5 1/2'' Fixed pipe ram against Upper Kill HCR + Upper IBOP. 300/5000 psi, 5/5min. Good test. bled off pressure to 0 psi. Test # 6. Line up and Pressure test 5 1/2'' Fixed pipe ram against Upper Kill Manual valve + Mud Hose. 300/5000 psi, 5/5min. Good test. bled off pressure to 0 psi. | 15 | WHITE | 2023-03-06 | TEST BOP | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 4 | BALTIC | WEST AFRICA
1487 | 1487 | Cementer flushed line with base oil, connect hose to Lo-Torque at SES. Pressure test line against lo-Torque valve 300 / 5000 psi, 5/5min. good test. 1 | 22 | WHITE | 2023-03-06 | SURFACE TESTING | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1488 | 1488 | Completed P/U & M/U BOP test assemblies (5 1/2'' PJ + SES + HT 55 FOSV + 10 ft PJ. Connect SES. | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2 | BALTIC | WEST AFRICA
1489 | 1489 | MU SES assy. Flush lines had with cement unit had returns. Connect HP hose to lo- torq valve on SES connection. Test # 7. Pressure test 13 5/8'' Annular BOP 5.5'' DP. 300/3500 psi, 5/5min. Good test. bled off pressure to 0 psi. | 15 | WHITE | 2023-03-06 | TEST BOP | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.25 | BALTIC | WEST AFRICA
1490 | 1490 | P/U,joint of 8 1/4" drill collar on TDS, M/U 12 1/4"x 2.16m string mill + bit sub + 13 3/8" casing scraper and 12 1/4" window mill. RIH Scraper Assy on 8 1/4" drill collar to 13.23m.( top of wear bushing) Continue P/U & M/U 8 1/4" drill collar to scraper Assy and cautiously RIH scraper and mill through well head from 13.23.m to 32m.. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-06 | TRIPS | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 3.25 | BALTIC | WEST AFRICA
1491 | 1491 | Disconnect HP hose. R/D SES assy. L/D 1 x 5.5'' dp and cross over. PU 1 X 5'''dp and RIH, screw on test plug. Close lower pipe ram. Pressure test 2 7/8'' x 5 1/2'' variable ram. 300/5000 psi. Bleed of pressure to 0psi. Pressure test Annular on 5'' dp 300/3500psi for 5/5mins ok.Bleed off pressure 0 psi, | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 2.25 | BALTIC | WEST AFRICA
1492 | 1492 | Break out and lay down SES assy. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | 23 | WHITE | 2023-03-06 | OTHER3 | BAL | Installed Lower IBOPs on 22/06/2022 Upper IBOP 17. Plug Back Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date 18. Squeeze Cement changed 04/02/2022.) 19. Fishing Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 20. Directional Work Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 21. Run/Retrieve Riser Equip. 22/01/23,Closure =2 (Total = 14 22. Surface Testing 0.50 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: 23. Other 3 4.75 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME 19:30 I SIZE WEIGHT 12.49 T C. Treating E IADC CODE GRADIENT 0.6482 L D. Swabbing MANUFACT. VISCOSITY 82 P E. Testing M TYPE PV/YP 41/15 O F. Other 4 SERIAL NO. GELS 10/16 C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS 31 DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Installed Lower IBOPs on 22/06/2022 Upper IBOP TOTAL DAYWORK 0.00 0.00 Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date NO. OF DAYS changed 04/02/2022.) 53 FROM SPUD Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 CUMULATIVE 1,279 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head ROTATING HOURS 22/01/23,Closure =2 (Total = 14 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 Operations Activities (Continued...) Installed Lower IBOPs on 22/06/2022 Upper IBOP Changed out Derrick escape line 13mm x 300 ft x 2.0 T, Sling ID #1100, Date of production 21/01/22, Date changed 04/02/2022.) Changed out Test line on shaker roof 3'' ID x 9.2M x 3''FIG 1502 both ends S/N: 2019092676818. Date: 06/06/20 Functions new diverter and ball valves on 14th June 2022 working good.Functioned diverter on well head 22/01/23,Closure =2 (Total = 14 Changed out wash pipe on the 25th July 2022 S/N 10375863-001. Wash pipe hours= 127 Change out Annular element on 08 /01/ 2023. Item #794243. s/no 80NERX DGD 0322-0168. 13-5/8" Annular Bop daily closure 2=Total =2. Changed out 29 1/2'' Diverter piston seals on 10th January 2023 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: BAL Job:1 Rpt No: 53 Date: 06-Mar-23 | NTOKON -1 | 1 | Mar-23 | 0.5 | BALTIC | WEST AFRICA
1493 | 1493 | Work with mechanic on installation of TDS blower. 1 Working on Rig Move check list. R Work with mechanic to change oil and filter on TDS gear box. U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-06 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
1494 | 1494 | Working on Rig Move check list. Carry out preventive maintenance on rig drilling equipment. | 23 | WHITE | 2023-03-06 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 7 | ADIARTIC-I | WEST AFRICA
1495 | 1495 | prepare for welding pad eyes & torch cutting operations on Texas deck, R/U weld tent on Texas deck. GNN-6ST1 projects activities on platform: - HI press hose exists from rig standpipe manifold to GNN-6ST1 X-mass wing flow line. - flush hose with rig pump with 7 BBL diesel, soak same, cont. pumping 5 BBL diesel. - soak diesel, then pump 20 BBL sea water to flush hose. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 23 | WHITE | 2023-03-06 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 0.5 | RIG 141 | MENAM
1496 | 1496 | Lay down GESCO handling equipment side door & SLIPS, change DP HDLG to 5" elevator. cut off length 9.20 FT IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 Tour 1 Operations Activities (Continued...) TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 0.5 | RIG 141 | MENAM
1497 | 1497 | Hang 20" guide CSG W/ BOP crane wire with 2 pad eyes, rough cut 20" CSG above pad eyes, retrieve 1 JT+ cut off on rig floor, L/D same with GESCO power tongue. cut off length 9.20 FT | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 1 | RIG 141 | MENAM
1498 | 1498 | Weld 4 pad eyes on 20" guide CSG joints above Texas deck for securing 20" CSG after rough cut. - wait on welding to cool 1 HR before rough cut. - position pad eyes to allow P/U 22 FT OF 20" CSG. - expected 20" CSG elevation above 30" conductor after P/U 22 FT: 15 FT. | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 3.5 | RIG 141 | MENAM
1499 | 1499 | Waiting On Platform Operation . O T GNN-6ST1 projects activities on platform: follow SIMOPS procedures for projects welding work on GNN-6ST1 flowline on platform below Texas deck & rig floor. | 23 | WHITE | 2023-03-06 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 5.5 | RIG 141 | MENAM
1500 | 1500 | Continue prepare for welding pad eyes & torch cutting operations on Texas deck, R/U weld tent on Texas deck. GNN-6ST1 projects activities on platform: - HI press hose exists from rig standpipe manifold to GNN-6ST1 X-mass wing flow line. 2 - flush hose with rig pump with 7 BBL diesel, soak same, cont. pumping 5 BBL diesel. R - soak diesel, then pump 20 BBL sea water to flush hose. U | 23 | WHITE | 2023-03-06 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 1.5 | RIG 141 | MENAM
1501 | 1501 | prepare for welding pad eyes & torch cutting operations on Texas deck, R/U weld tent on Texas deck. GNN-6ST1 projects activities on platform: - HI press hose exists from rig standpipe manifold to GNN-6ST1 X-mass wing flow line. - flush hose with rig pump with 7 BBL diesel, soak same, cont. pumping 5 BBL diesel. DEPTH INTERVAL DRILL - soak diesel, FthOeRnM pAuTmIOpN 20 BBL sea wateRr OtoT AfluRsYh hoWsTe.. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 23 | WHITE | 2023-03-06 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 0.5 | RIG 141 | MENAM
1502 | 1502 | P/U, M/U & RIH with 20" guide CSG JT'S through PLTF guides T/ 238' ORKB (7 FT inside 30" conductor above ML). -RIH with caution across PLTF guides, especially while coupling against PLTF guide. had strong CSG vibrations while RIH due to high wind speed & high sea swell. - RIH slowly before expected top of 30" conductor STUB @ 231' ORKB, monitor for any slack, pass OK. - USE 20" GESCO power tongue for M/U JTS, RIG tongue for support. | 12 | WHITE | 2023-03-06 | RUN CASING & CEMENT | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 4.5 | RIG 141 | MENAM
1503 | 1503 | 'Hold PJSM for running 20" casing AS A guide through PLTF guides, discussing risks, mitigation, and roles & responsibilities. | 23 | WHITE | 2023-03-06 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 0.5 | RIG 141 | MENAM
1504 | 1504 | Lower & position Texas deck & secure same. install gangway to platform. O T - RKB - ORKB= 11 FT. - RKB - PROD. DECK= 62 FT. - RKB - MSL= 111 FT. - water depth: 139 FT. | 23 | WHITE | 2023-03-06 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 2 | RIG 141 | MENAM
1505 | 1505 | Wait on weather due to high wind speed. weather tracking as follows: TIME: 00:00 TO 1:00, WIND SPEED 37 - 40 KNOTS. 1 TIME: 01:00 TO 3:00, WIND SPEED 38 - 41 KNOTS. R TIME: 03:00 TO 4:30, WIND SPEED 37 - 39 KNOTS. U | 23 | WHITE | 2023-03-06 | OTHER3 | 141 | Pre job safety meeting with all personal discussed procedures and plan for Pick up make up running 17. Plug Back with 20" casing to 274 feet 18. Squeeze Cement 19. Fishing 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 7.50 7.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Pre job safety meeting with all personal discussed procedures and plan for prepare for P/U, M/U & TOTAL DAYWORK 0.00 0.00 RIH with 20" guide welding bad eyes on plat form NO. OF DAYS 2 FROM SPUD CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: 141 Job:141-23-3 GNN-3 Rpt No: 2 Date: 06-Mar-23 | 141-23-3 GNN-3 | GNN-3 | Mar-23 | 4.5 | RIG 141 | MENAM
1506 | 1506 | Rigged up drilling bail on TDS pipe handler. U Install 5" elevator on the bail. O T Connect link tilt chains on drilling bail. Working on Rig Move check list. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 | 23 | WHITE | 2023-03-06 | OTHER3 | AD1 | Lower and Upper IBOP changed out on the 04 of march 2023 17. Plug Back Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. 18. Squeeze Cement Next: Change out date for Upper and Lower IBOP: September 03,2023. 19. Fishing Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 20. Directional Work 06/01/2025). 21. Run/Retrieve Riser Equip. Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the 22. Surface Testing seal- 12/01/2023). DRILLER: 23. Other 3 12.00 12.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. TIME I SIZE WEIGHT T C. Treating E IADC CODE GRADIENT L D. Swabbing MANUFACT. VISCOSITY P E. Testing M TYPE PV/YP O F. Other 4 SERIAL NO. GELS C G. Other 5 JETS FL. LOSS H. Other 6 TFA pH TOTALS 12.00 12.00 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY DEPTH IN 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING REMARKS: Lower and Upper IBOP changed out on the 30th of January 2022 TOTAL DAYWORK 0.00 0.00 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. NO. OF DAYS Next: Change out date for Upper and Lower IBOP: July 29,2022. 0 FROM SPUD Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- CUMULATIVE 06/01/2025). ROTATING HOURS Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the DAILY MUD COST ($) TOTAL MUD COST ($) seal- 12/01/2023). DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 Tour 2 Remarks (Continued...) Lower and Upper IBOP changed out on the 04 of march 2023 Upper IBOP . S/N: TC 47693810-01 and Lower IBOP S/N IBL A26U512. Next: Change out date for Upper and Lower IBOP: September 03,2023. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 04 March 2023. Saver Sub hours: =0 Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. Operations Activities (Continued...) Lower and Upper IBOP changed out on the 30th of January 2022 Upper IBOP . S/N: TC- 25710-01 and Lower IBOP S/N TC-2389911-03. Next: Change out date for Upper and Lower IBOP: July 29,2022. Change 13 5/8" BOP 5" fixed ram seals on 22/01/2022 (Ram block 5" S/N: 241, Expire date for the seal- 06/01/2025). Change 13 5/8" BOP 9 5/8" fixed ram seals on 22/01/2022 (Ram block for 9 5/8"csg. S/N: 414, Expire date for the seal- 12/01/2023). Change 13 5/8" BOP shear ram seals on 23/01/2022 (Ram block for shear ram S/N: 4501805719-04, 4501447839-01-05. Expire date for the seal- 02/01/2025). Installed forward air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1086). Installed Aft air tugger cable under rig floor 24/01/2022. Expired 25/01/2024. Length =250ft. (S/N-1084). Installed port air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length =450ft. (S/N-PL/S/5929). Size: 3/4" Installed starboard air tugger cable on the rig floor 16/07/2022. Expired 17/07/2024. Length=450ft (S/N-PL/S/5903). Size: 3/4" Installed Discharge and Suction Module on Mud pump #3 01/02/2022. (S/N- Discharge 6242, Suction 5244). Saver Sub S/N- PSTP 1938-1-1. Installed on 20th May 2022. Saver Sub hours: =203 (97 HRS left) Saver Sub / Wash pipe planned Change out hours=> 300hrs. Saver sub thread and shoulder inspected .OK. Annular closure times Today= (Total closure count = 12. Changed Annular Element on 26/01/2022(New S/N DGD 80NBRX 04210185). Installed rebuild wash pipe on the 17/05/2022. (S/N: 30123288). Install manual choke. S/N. 27301220. PARVEEN. Wash pipe Total hrs = 203 (97HRS left). Wash pipe inspected. OK. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: AD1 Job:AD1-23-1 Rpt No: 44 Date: 06-Mar-23 WIRE LINE | CONTRACT PREPARETION | AD1-23-1 | Mar-23 | 5 | ADIARTIC-I | WEST AFRICA
1507 | 1507 | CONTINUE RIH 8 1/2" BAKER LWD ASSY ON 5" X 5 1/2" DP F/ 226 M TO 1380 M. FILL UP EVERY 15 STAND & CIRCULATE AS PER BAKER INSTRUCTION. DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP PUMP PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 6 | WHITE | 2023-03-06 | TRIPS | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 2 | RON TAPPMEYER | INDIA
1508 | 1508 | PERFORM SHALLOW TEST WITH 200 GPM AND 850 PSI. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | 20 | WHITE | 2023-03-06 | DIRECTIONAL WORK | HI4 | PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR 17. Plug Back LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. 18. Squeeze Cement ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 19. Fishing FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , 20. Directional Work 1.00 REDUCE MUD WEIGHT 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 0.25 2.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 6.1 7.1 TIME 12:00 15:00 21:00 I 1 BIT 6.13 0.60 SIZE 6.13 6.13 WEIGHT 8.95 8.95 8.95 T C. Treating E 7 MWD 5.00 113.44 IADC CODE GRADIENT 0.4645 0.4645 0.4645 PL DE.. TSewsatibnbging 1 XO 5.00 2.74 MANUFACT. SMITH VISCOSITY 45 45 45 M 3 HWDP 4.00 92.37 TYPE PV/YP / / / O F. Other 4 1 JAR 4.81 29.78 SERIAL NO. 838186 SM1237 GELS / / / C G. Other 5 5 HWDP 4.00 153.44 JETS 3x12 FL. LOSS H. Other 6 15 DP 4.00 1,407.63 TFA 0.000 0.331 pH TOTALS 12.00 12.00 DEPTH OUT 10,847 SOLIDS DAYWORK TIME SUMMARY DEPTH IN 10,830 10,847 2 (OFFICE USE ONLY) TOTAL DRILL 17 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 0.25 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. STD. D.P. CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 1 1 BT A TOTAL 1,800.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 0 NO BHA REMARKS: PJSM, NO ACC OR POLL REPORTED. VISUALLY INSPECTED BOP AND ACCUMULATOR FOR TOTAL DAYWORK 0.00 0.00 LEAKS, CHECKED COM, KEMS, DERRICK CAMERA AND TALK BACK SYSTEM ARE WORKING PROPERLY. NO. OF DAYS ENSURED ALL WELL CONTROL EQUIPMENT IS LINED UP PROPERLY. 5'' TIW AND GRAY VALVE ON RIG 39 FROM SPUD FLOOR ARE IN OPEN POSITION. HELD DAILY CHECKS WITH CREW.REV TBRA MAKING CONNECTION , CUMULATIVE 74 REDUCE MUD WEIGHT ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI4 Job:BRRI 1003 Rpt No: 39 Date: 06-Mar-23 | HI4-23-1 | BRRI 1003 | Mar-23 | 0.25 | HIGH ISLAND IV | MENAM
1509 | 1509 | Held PJSM for POOH and lay down 3-1/2" upper completion. | 23 | WHITE | 2023-03-06 | OTHER3 | MP1 | P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick 17. Plug Back camera working. 18. Squeeze Cement At 0100 Hrs Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & Life 19. Fishing saving equipment. 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 3.50 1.00 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips 5.00 NO. ITEM O.D. LENGTH BIT NO. TIME 23:00 I 1 PCPM 3.50 2.00 SIZE WEIGHT 10.15 T C. Treating E 1 OTHER 6.95 7.62 IADC CODE GRADIENT 0.5268 PL DE.. TSewsatibnbging 3.50 5.00 1 XO 4.75 2.67 MANUFACT. VISCOSITY M 1 XO 4.69 2.88 TYPE PV/YP / O F. Other 4 1 XO 4.88 1.45 SERIAL NO. GELS / C G. Other 5 10 HWDP 4.00 923.21 JETS FL. LOSS H. Other 6 1 XO 5.00 2.43 TFA pH TOTALS 12.00 12.00 1 OTHER 4.75 4.86 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 JAR 4.75 11.16 DEPTH IN 2 (OFFICE USE ONLY) 1 XO 4.75 1.67 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 2 STD. D.P. 4.00 158.05 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 4.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 1,118.00 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 80,000 REMARKS: P.J.S.M/Env. meeting held with crews. Trip Crown-O-Matic with block and reset same and Derrick TOTAL DAYWORK 0.00 0.00 camera working. NO. OF DAYS At 1500 Hrs Held Stand Down Safety meeting. Discussed ARAMCO life saving rules, Proper use of PPE & Life 0 FROM SPUD saving equipment. CUMULATIVE ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 145.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: MP1 Job:BRRI-37 Rpt No: 5 Date: 06-Mar-23 | BRRI-37 | BRRI-37 | Mar-23 | 0.25 | MAIN PASS I | MENAM
1510 | 1510 | RIH WITH SLB 8-1/2" RSS/MWO/LWO/OLR/PBL ASSY ON 5" OP ·MONITOR WELL ALL TIME THRU TRIP TANK,WELL STATIC. | 6 | WHITE | 2023-03-06 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
1511 | 1511 | HPJSM.PU & MU 8-1/2" SMITH RR BIT [MSl616-B, S/N:SM2173) WITH SLB 1 RSS/MWO/LWO/DLRIPBUBIT SUB & FLOAT. R •HPJSM LOAD RADIOACTIVE SOURCE. U •P/U 6·1/2" NOV DRILLING JAR O T | 6 | WHITE | 2023-03-06 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 3.5 | HIGH ISLAND V | MENAM
1512 | 1512 | HPJSM,UO 6 1/2" ORLG JAR,SLB MTR/MWO ASSY. BIT GRADING:1 1-WT·A · X lNO-BHA | 6 | WHITE | 2023-03-06 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
1513 | 1513 | POOH 6" SLICK ASSY ON 5 1/2" DP F/2495M TO 999M. FURTHER POOH IN PROGRESS. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | 6 | WHITE | 2023-03-06 | TRIPS |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 3 | J T ANGEL | INDIA
1514 | 1514 | SHALLOW TEST MWD AT 450 GPM, 1400 PSI. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
1515 | 1515 | PUMP 25 BBL HI-VIS & CIRC OUT WITH 300 GPM/900 PSI. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
1516 | 1516 | FILL STRING. | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.25 | J T ANGEL | INDIA
1517 | 1517 | CONT RIH 6" SLICK ASSY F/1301M TO 2163M. O T | 6 | WHITE | 2023-03-06 | TRIPS |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.25 | J T ANGEL | INDIA
1518 | 1518 | FILL STRING. U | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.25 | J T ANGEL | INDIA
1519 | 1519 | RIH 6" SLICK ASSY ON 5 1/2" DP F/436M TO 1301M. R | 6 | WHITE | 2023-03-06 | TRIPS |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1 | J T ANGEL | INDIA
1520 | 1520 | FILL STRING. 2 | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.25 | J T ANGEL | INDIA
1521 | 1521 | M/UP 6" BIT SLICK ASSY WITH 6" BIT, JUNK SUB AND 6" STAB ON 4 3/4" DC + 3 1/2" HWDP + JAR & 3 1/2" DP. TO 436M. | 6 | WHITE | 2023-03-06 | TRIPS |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 1.5 | J T ANGEL | INDIA
1522 | 1522 | CONT RIH 6" SLICK ASSY F/2163M TO 2495M. BRIDGE PLUG DEPTH, TAG WITH 10 KIPS. | 6 | WHITE | 2023-03-06 | TRIPS |  | HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK 17. Plug Back COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 18. Squeeze Cement 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 19. Fishing TIMES INSTALLED ON 07TH MARCH 2022. 20. Directional Work 21-1/4'' ANNULAR OPERATED : 08 TIMES 21. Run/Retrieve Riser Equip. 8 1/4" JAR(SL.NO-(87284J) HRS-40 22. Surface Testing 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: 23. Other 3 0.25 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 10.3 TIME 12:00 18:00 23:55 I 1 BIT 6.00 0.85 SIZE 6.00 WEIGHT 8.60 8.60 8.60 T C. Treating E 1 JUNK 4.25 3.45 IADC CODE GRADIENT 0.4463 0.4463 0.4463 PL DE.. TSewsatibnbging 1 STAB 4.75 6.07 MANUFACT. BAKER VISCOSITY 26 26 26 M 6 DC 4.75 180.32 TYPE TD-505X PV/YP / / / O F. Other 4 9 HWDP 4.75 271.23 SERIAL NO. 5277210 GELS / / / C G. Other 5 1 JAR 4.75 29.89 JETS 5x12 FL. LOSS H. Other 6 3 HWDP 4.75 89.27 TFA 0.552 pH TOTALS 12.00 12.00 27 DP 4.75 850.16 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 1 XO 7.00 1.74 DEPTH IN 8,189 2 (OFFICE USE ONLY) TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 9 STD. D.P. 5.50 821.98 CUTTING STRUCTURE XC POLIMER 1 drill water 15 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN TOTAL 2,254.95 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 105,000 REMARKS: HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK TOTAL DAYWORK 0.00 0.00 COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC NO. OF DAYS 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 75 FROM SPUD TIMES INSTALLED ON 07TH MARCH 2022. CUMULATIVE 131 21-1/4'' ANNULAR OPERATED : 08 TIMES ROTATING HOURS 8 1/4" JAR(SL.NO-(87284J) HRS-40 DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 6 1/2 " JAR(OSC-1136456A) HRS-86.5 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 Tour 2 Remarks (Continued...) HELD PJSM REGARDING POOH 6" CLEAN OUT BHA. TOOK TOFS @ 02:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 239 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 933 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 10 Operations Activities (Continued...) HELD PJSM REGARDING RIH 6" CLEAN OUT BHA. TOOK TOFS @ 15:00 HRS. CHECK COLLISION CHECKLIST. SAVER SUB CONN 240 (NEW SAVER SUB HT- 55 INSTALLED ON 28TH DEC 2022).SWIVEL HRS: 934 (NEW WASH PIPE INSTALLED ON 06 SEPT 2022.13 5/8" ANNULAR OPERATED : 33 TIMES INSTALLED ON 07TH MARCH 2022. 21-1/4'' ANNULAR OPERATED : 08 TIMES 8 1/4" JAR(SL.NO-(87284J) HRS-40 6 1/2 " JAR(OSC-1136456A) HRS-86.5 4-3/4" JAR (79864J) HRS- 12 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: Job:C-26P#6Y Rpt No: 75 Date: 06-Mar-23 | C-26P#6Y | C_26P#6Y | Mar-23 | 0.5 | J T ANGEL | INDIA
1523 | 1523 | RIH WITH SLB 8-1/2'" RSS/MWD/LWD/DLR/PBL ASSY ON 5'" DP - MONITOR WELL ALL TIME THRU TRIP TANK, WELL STATIC | 6 | WHITE | 2023-03-06 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM
1524 | 1524 | CUMULTAIVE TIME TO FILL UP PIPE AND BREAK CIRCULATION WHILE RIH | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 0.5 | HIGH ISLAND V | MENAM
1525 | 1525 | PASS THRU WINDOW WITH 20 KLBS S/0 AND RIH FREELY IN OPEN HOLE WITH SLB 8-1/2'" RSS/MWD/LWD/DLRIPBL ASSY ON 5'" DP TO 5800 FT. -MONITOR WELL ALL TIME THRU TRIP TANK, WELL STATIC | 6 | WHITE | 2023-03-06 | TRIPS | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
1526 | 1526 | LOADED RADIO ACTIVE SOURCE. R/DN TEST ASSY. (BAKER LWD TOOL BRT @ 0900 HRS). | 20 | WHITE | 2023-03-06 | DIRECTIONAL WORK | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 0.5 | RON TAPPMEYER | INDIA
1527 | 1527 | M/UP TEST ASSY & PERFORMED SHALLOW TEST @ 500 GPM/1000 PSI OK. | 20 | WHITE | 2023-03-06 | DIRECTIONAL WORK | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1 | RON TAPPMEYER | INDIA
1528 | 1528 | HPJSM.P/UP BAKER RSS + LWD ASSY B/OFF & L/DN THE SAME. P/UP & M/UP 8 1/2" NEW PDC BIT WITH BAKER U ROTARY+LWD BHA & RIH UP TO 25M. O T | 6 | WHITE | 2023-03-06 | TRIPS | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 2.5 | RON TAPPMEYER | INDIA
1529 | 1529 | FLOW CHECK OK.CONTINUE POOH 8 1/2" SLICK ASSY ON BHA F/212 M TO SURFACE.B/OFF & L/DN JAR, S. STAB, BIT, & BIT 1 SUB. R | 6 | WHITE | 2023-03-06 | TRIPS | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1.5 | RON TAPPMEYER | INDIA
1530 | 1530 | POOH 8 ½” SLICK ASSY ON 5 1/2" X 5" DP. F/ 2334M TO 212 M. | 6 | WHITE | 2023-03-06 | TRIPS | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 2.5 | RON TAPPMEYER | INDIA
1531 | 1531 | R/DN SURF LINE & TEST ASSY.FLOW CHECK OK. PUMP SLUG. | 23 | WHITE | 2023-03-06 | OTHER3 | RTP | WASH PIPE HRS:1 HRS. 17. Plug Back TOTAL WASH PIPE HRS :- 768 HRS. 18. Squeeze Cement SAVER SUB :-3 CONNECTION. 19. Fishing TOTAL CONNECTIONS :- 183 CONNECTIONS. 20. Directional Work 1.50 INSTALLED SAVER SUB - 25/12/2022. 21. Run/Retrieve Riser Equip. INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) 22. Surface Testing DRILLER: 23. Other 3 1.00 5.50 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 9.1 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.79 SIZE 8.50 WEIGHT 13.00 13.00 13.00 T C. Treating E 1 BS 6.44 2.79 IADC CODE PDC GRADIENT 0.6747 0.6747 0.6747 PL DE.. TSewsatibnbging 8 OTHER 8.38 79.72 MANUFACT. NOV VISCOSITY 53 53 53 M 1 XO 6.25 2.26 TYPE TK56 DM-X PV/YP / / / O F. Other 4 6 DC 6.50 179.43 SERIAL NO. A- 291959 GELS / / / C G. Other 5 1 XO 6.50 3.15 JETS 18,4x16 FL. LOSS H. Other 6 9 HWDP 5.00 264.86 TFA 1.034 pH TOTALS 12.00 12.00 1 JAR 6.50 33.37 DEPTH OUT SOLIDS DAYWORK TIME SUMMARY 6 HWDP 5.00 176.97 DEPTH IN 7,415 2 (OFFICE USE ONLY) 60 DP 5.00 1,887.86 TOTAL DRILL MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 XO 7.00 2.76 TOTAL HRS TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 5 STD. D.P. 5.50 474.71 CUTTING STRUCTURE zen 4 PACRG 2 T HOURS WITHOUT D.P. SNG. D.P. 5.50 INNER OUTER DULL CHAR. LOCATION BARITE 6 HOURS STANDBY KELLY DOWN TOTAL 3,108.66 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: WASH PIPE HRS:1 HRS. TOTAL DAYWORK 0.00 0.00 TOTAL WASH PIPE HRS :- 769 HRS. NO. OF DAYS SAVER SUB :-3 CONNECTION. 50 FROM SPUD TOTAL CONNECTIONS :- 186 CONNECTIONS. CUMULATIVE INSTALLED SAVER SUB - 25/12/2022. ROTATING HOURS INSTALLED NEW WASH PIPE - 16 /Jan/ 23 (DEUBLIN) DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: RTP Job:MBS181HBA-A Rpt No: 50 Date: 06-Mar-23 | MBS181HBA-A | MBS181HBA-A | Mar-23 | 1 | RON TAPPMEYER | INDIA
1532 | 1532 | Drill 8 1/2 hole section as per D/D instruction from 1960m to 2021m ( 1722m TVD ), with 1800 lit/min, 2800 psi, 90 RPM, 8-14Kips WOB and 6000-9000ft/lb TRQ. 2 R U O T IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 21 Date: 06-Mar-23 | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 51 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 27/12.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3.5/7 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 4 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.3 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL 692 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS 36 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 61 STD. D.P. 5.00 5,778.94 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.69 TOTAL 6,630.58 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 21 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 186 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 21 Date: 06-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 12 | KEY MANHATTAN | MENAM
1533 | 1533 | Drill 8 1/2 hole section as per D/D instruction from 1880m to 1960m, with 1800 lit/min, 2800 psi, 90 RPM, 8-14Kips WOB and 6000- 9000ft/lb TRQ. 1 R U O T DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 3 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 6430 6631 Drill 100% Clay 95 15000 2700 6.000 56 6.000 56 469.224 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 6,460 37.34 115599..1199 5,513.0 6,557 37.5 115588..3399 5,590.4 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | KMN | Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and 17. Plug Back safety requirements regarding task in progress. 18. Squeeze Cement Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 19. Fishing the task all the time. Plan each task steps and explain new green hands SD policy and procedure 20. Directional Work 21. Run/Retrieve Riser Equip. 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 2.2 TIME 23:30 I 1 BIT 8.50 0.95 SIZE 8.50 WEIGHT 14.60 T C. Treating E 1 AUTOTR 7.50 10.50 IADC CODE GRADIENT 0.7577 PL DE.. TSewsatibnbging 2 OTHER 7.27 10.01 MANUFACT. BAKER VISCOSITY 51 M 1 ONTRAK 7.00 16.96 TYPE GTi65MHO PV/YP 27/12.2 O F. Other 4 1 STAB 8.38 4.20 SERIAL NO. 13896640 GELS 3.5/7 C G. Other 5 1 OTHER 7.00 10.63 JETS 4x13,2x12 FL. LOSS 4 H. Other 6 1 OTHER 6.75 1.71 TFA 0.739 pH 10.3 TOTALS 12.00 12.00 4 OTHER 6.75 22.05 DEPTH OUT SOLIDS 27 DAYWORK TIME SUMMARY 24 HWDP 5.00 717.62 DEPTH IN 5,938 2 (OFFICE USE ONLY) 1 JAR 6.63 27.17 TOTAL DRILL 692 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. 1 OTHER 6.88 2.17 TOTAL HRS 36 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 61 STD. D.P. 5.00 5,778.94 CUTTING STRUCTURE T HOURS WITHOUT D.P. SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION HOURS STANDBY KELLY DOWN 27.69 TOTAL 6,630.58 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 150,000 REMARKS: Held pre tour safety meeting with Drilling Planer. Discuss with crew members daily operations and TOTAL DAYWORK 0.00 0.00 safety requirements regarding task in progress. NO. OF DAYS Plan each task and use TBRA, Call TOFS and use Safety conversation process. One person designed to monitor 21 FROM SPUD the task all the time. Plan each task steps and explain new green hands SD policy and procedure CUMULATIVE 186 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: KMN Job:KMN-23-2 Rpt No: 21 Date: 06-Mar-23 | KMN-23-2 | KMN-23-2 | Mar-23 | 12 | KEY MANHATTAN | MENAM
1534 | 1534 | SLB DIRECTIONAL DRILL 8-1/2'" CURVE SECTION WITH RSS/MWD/LWD ASSY FROM 6255' TO 6540' WITH 84 PCF INNOVERT R OBM AND 100% CIRCULATION . U -FOLLOWING DIRECTIONAL PLAN OF SFNY-349 L-0-1 PLAN #8. O T -WASH UP AND REAM DOWN EACH DRILLED STAND. -RECORD SURVEY EVERY 45 FT AS PER GOC USING Ml-SWACO SKIP & SHIP SYSTEM. -PPT: SPURT 1 CC & TOTAL 2.2 CC. -CURRENT WELL PATH : 9.86 ABOVE & 20.9" RIGHT OF THE PLAN. IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 6.5 | HIGH ISLAND V | MENAM
1535 | 1535 | CIRC HOLE CLEAN WASH UP AND REAM DOWN WITH 100 RPM AS PER GOC TO REVISE DIRECTIONAL PLAN 2 | 5 | WHITE | 2023-03-06 | CONDITION MUD & CIRCULATE | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 1 | HIGH ISLAND V | MENAM
1536 | 1536 | DRILL 8.5 HOLE WITH SLB RSS TOOLS FROM 6058 FT TO 6300 FT WITH 580 GPM / 2850 PSI /120 RPM( P/UP=205 K S/O =175 K RO =160K ) | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 4.5 | HIGH ISLAND V | MENAM
1537 | 1537 | SLB DIRECTIONAL DRILL 8-1/2'" CURVE SECTION WITH RSS/MWD/LWD ASSY FROM 5890' TO 6058' WITH 84 PCF INNOVERT OBM AND 100% CIRCULATION . -FOLLOWING DIRECTIONAL PLAN OF SFNY-349 L-0-1 PLAN #7. -WASH UP AND REAM DOWN EACH DRILLED STAND DEPTH INTERVAL DRILL FORMATION ROTARY WT. PUMP NO 1 PUMP NO 2 PUMP PUMP TOTAL CORE PUMP REAM TABLE ON LINER LINER LINER LINER PUMP FROM TO CORE NO. (SHOW CORE RECOVERY) SPEED BIT PRESS SIZE SPM SIZE SPM SIZE SPM SIZE SPM OUTPUT 6058 6592 Drill SHALE 120 14000 2850 6.000 69 6.000 69 571.5822 HORIZ HORIZ HORIZ DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DEPTH DEV. DIR. TVD DISP. DISP. DISP. DEVIATION RECORD 6,066 63.25 331199..9988 5,245.5 2,568.4 6,162 68.54 332200..0077 5,284.5 2,655.6 6,258 73.87 331188..77 5,315.2 2,746.0 6,318 77.25 331177..3322 5,330.1 2,803.6 6,352 78.45 331177..2277 5,337.3 2,836.5 6,405 81.11 331166..5566 5,346.7 2,888.1 TIME LOG ELAPSED CODE DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS FROM TO TIME NO. | 2 | WHITE | 2023-03-06 | DRILL ACTUAL | HI5 | DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL 17. Plug Back TIME. 18. Squeeze Cement PRE JOB SAFETY METING. L/D MOTOR 19. Fishing PRE JOB SAFETY METING P/U B.H.A RSS MWD. 20. Directional Work 1.00 PRE JOB SAFETY METING.RIH 5' DP. 21. Run/Retrieve Riser Equip. PRE JOB SAFETY METING.DRILLING . 22. Surface Testing DRILLER: 23. Other 3 DRILLING ASSEMBLY BIT RECORD MUD RECORD N A. Perforating O B. Tubing Trips NO. ITEM O.D. LENGTH BIT NO. 1.2 TIME 12:00 18:00 23:59 I 1 BIT 8.50 0.78 SIZE 8.50 WEIGHT 11.20 11.20 11.20 T C. Treating E 1 MWD 6.75 75.79 IADC CODE M222 GRADIENT 0.5813 0.5813 0.5813 PL DE.. TSewsatibnbging 1 MWD 6.75 51.37 MANUFACT. SMITH VISCOSITY 65 65 65 M 1 PCPM 8.50 3.71 TYPE MS6168 PV/YP 26/20 26/20 26/20 O F. Other 4 1 OTHER 6.78 7.18 SERIAL NO. SM2173 GELS 10/14 10/14 10/14 C G. Other 5 1 PBL 6.75 20.89 JETS 6x13 FL. LOSS 0 0 0 H. Other 6 3 HWDP 5.00 92.42 TFA 0.778 pH 0 0 0 TOTALS 12.00 12.00 1 JAR 6.50 33.49 DEPTH OUT SOLIDS 25 25 25 DAYWORK TIME SUMMARY 1 HWDP 5.00 400.54 DEPTH IN 5,940 2 (OFFICE USE ONLY) TOTAL DRILL 652 MUD & CHEMICALS ADDED R HOURS W/ CONT. D.P. TOTAL HRS 12 TYPE AMT. TYPE AMT. U O HOURS W/ OPR. D.P. 63 STD. D.P. 5.00 5,905.83 CUTTING STRUCTURE steel seal 100 30 steel seal 50 30 T HOURS WITHOUT D.P. 3 SNG. D.P. 5.00 INNER OUTER DULL CHAR. LOCATION lime 14 marpil madim 2 HOURS STANDBY KELLY DOWN 96.21 3 TOTAL 6,688.21 BEARINGS GAUGE OTHER REASON SEALS DULL PULLED WT. OF STRING 205,000 REMARKS: DAILY CHECKED AS PER DRILLING CHECK LIST. DISCUSSED HAND FREE OPERATION AT ALL TOTAL DAYWORK 0.00 0.00 TIME. NO. OF DAYS PRE JOB SAFETY METING.DRILLING 23 FROM SPUD CUMULATIVE 32 ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 3,070.00 DRILLER: IADCDAILY DRILLING REPORT FORM - PROOF COPY NOT LICENSED BY IADC Generated by RIMDrill Drilling Information System DAILY DRILLING REPORT Rig No: HI5 Job:HI5-23-1 Rpt No: 23 Date: 06-Mar-23 | SFNY - 349 | SFNY - 349 | Mar-23 | 2 | HIGH ISLAND V | MENAM