## Sheet1
F/NAME | WELL_NO | WATER_DEPTH | RIG_NO | OPERATOR | DATE | ELAPSED_TIME | OPERATIONAL-CODE | DAILY_ACTIVITY | REMARKS-1 | COLOR
IADCRpt_Compact Driller_CMD-22-3_140_220926.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 26-Sep-22 | 4.50 | C | CONTINUE PERFORMING ACID STIMULATION JOB ON WELL LB-11.** HPJSM. CONTINUE PUMPING N2 INCREASED RATE TO 300SCFM WITH PUMPING PRESSURE 500-600 PSI FLUIDRETURNS ON SURFACE 50% OIL & 50% GAS & LIQUID(PH=3) TEMP: 53DEGREE. PUMPING NEUTRALIZERINTERMITTENTLY IN RETURN LINE GOING TO PRODUCTION HEADER. ** STOPPED N2 PUMPING. DISCONNECTED CT N2PUMPING LINE FROM A- ANNULUS. CAIRN PRODUCTION TEAM CONNECTED GAS INJECTION LINE TO A- ANNULUS.* PJSM. STARTED GAS INJECTION IN LB-11 WELL & CONT. PUMPING NEUTRALIZER IN RETURNS LINE GOING TOPRODUCTION HEADER AT 0.3BPM. RETURN FLUID PH=3** MEANWHILE DISMANTLE CT REEL & FRAME. MOVED CT REEL & CT FRAME FROM CANTILEVER DECK TO MAIN DECK& SECURE IN STAND | :PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP. 22. SURFACE TESTING :PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS140FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_140_220926.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 26-Sep-22 | 1.50 | 6 | HPJSM. STARTED BREAKING 5" DP TO SINGLES (15 JTS) USING MOUSE HOLE AND LAYING DOWN SAME DECK. NOTE-USING MANUAL TONG TO BREAK OUT SOME TOOL JOINT CONNECTION DUE HI- TORQUE** MEANWHILE CONT. PUMPING NEUTRALIZER IN RETURNS LINE GOING TO PRODUCTION HEADER AT 0.3BPM.RETURN FLUID PH=3** AS PER CAIRN PRODUCTION TEAM INSTRUCTION DISCONNECTED N2 PUMPING UNIT & READY FOR BACKLOAD. | :PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP. 22. SURFACE TESTING :PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS140FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_140_220926.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 26-Sep-22 | 6.00 | 6 | CONTINUE STARTED BREAKING 5" DP TO SINGLES (90 JTS) USING MOUSE HOLE AND LAYING DOWN SAME DECK.NOTE-USING MANUAL TONG TO BREAK OUT SOME TOOL JOINT CONNECTION DUE HI- TORQUE 2 RUOT DEPTH I NTERVAL DRILL FORMATION ROTARY WT.PUMP PUMP PUMP PUMP TOTALFROM TO REAM CORENO.(SHOW CORE RECOVERY) TABLE ON PUMPPRESS LINERSPM LINER SPM LINER SPM LINER SPM PUMP CORE SPEED BITSIZE SIZE SIZESIZEOUTPUT HORIZ HORIZ HORIZ DEVIATI ON DEP TH DEV . DI R. TVD DISP. DEPTH DEV. DIR.TVDDISP. DEPTHDEV. DIR.TVDDISP. RECOR D TIME LOG ELAPSED CODEFROM TO TIME NO.DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS | :PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP. 22. SURFACE TESTING :PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS140FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_140_220926.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 26-Sep-22 | 12.00 | 6 | HELD PJSM AND CONTINUE BREAK OUT AND L/DN 5” DP USING MOUSE HOLE AND LAYING DOWN SAME ON DECK.TOTAL L/DN 144 JOINTS. NOTE-USING MANUAL TONG TO BREAK OUT SOME TOOL JOINT CONNECTION DUE HI-TORQUE. MEAN WHILE BACKLOAD CT AND HLS EQUIPMENTS. IADC OFFICI AL DAILY DRILLING REPORT FORM | :PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP. 22. SURFACE TESTING :PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS140FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_141_220927.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 27-Sep-22 | 8.50 | 6 | INSTALL COVER PLATE ON LB WELL NO 11. CONTINUE TO BREAK OUT AND LOUT 5” DP STANDS FROM DERRICK TOTAL63JTS LAYED OUT. NOTE USING RIG TONGS AND EZ TORQUE TO BREAK OUT JOINTS DUE TO CONNECTIONS VERYTIGHT. MEAN WHILE OFF LOAD EMPTY AND BACK LOAD 2 X FOOD CONTAINER BACK LOAD 4 X BASKET AND 1 XCONTAINER OF CTU 7 X HLS LIFTS AND 11 PALLETS OF CHEMICALS. CLOSED ANNULAR | : PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP 22. SURFACE TESTING : PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS141FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 | RED
IADCRpt_Compact Driller_CMD-22-3_141_220927.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 27-Sep-22 | 1.50 | 6 | PJSM CHANGE HANDLING EQUIPMENT TO 5 1/2" LAY DOWN 9 SINGLE O 51/2" HWDP CLOSED ANNULAR | : PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP 22. SURFACE TESTING : PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS141FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00 | RED
IADCRpt_Compact Driller_CMD-22-3_141_220927.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 27-Sep-22 | 2.00 | 6 | DECK MANAGEMENT MAKE SPACE ON CANTILEVER DECK TO ACCOMMODATE 5 1/2" HWDP CRANE SHIFT HLSSLICKLINE AND HLB CTU EQUIPMENTS FROM PLATFORM TO RIG IN ORDER TO BACK LOAD RID DOWN HIGHPRESSURE HOSE RUNNING FROM RIG FLOOR TO PLATFORM AND STORED SAME. 2 RUOT DEPTH INTERVAL DRILL CORE FORMATIONROTARY WT. PUMP PUMP PUMP PUMP PUMP TOTALFROM TO REAM CORE NO. (SHOW CORE RECOVERY)TABLE SPEED ON BIT PRESS LINER SIZESPM LINER SIZE SPM LINERSIZE SPM LINERSIZE SPM PUMPOUTPUTDEVIATION RECORDDEPTH DEV. DIR. TVD HORIZ DISP. DEPTH DEV. DIR.TVDHORIZ DISP. DEPTHDEV. DIR.TVDHORIZ DISP. TIME LOG ELAPSEDTIME CODE NO.DETAILS OF OPERATIONS IN SEQUENCE AND REMARKSFROM TO | : PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP 22. SURFACE TESTING : PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS141FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_141_220927.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 27-Sep-22 | 2.00 | 6 | DECK MANAGEMENT MAKE SPACE ON CANTILEVER DECK TO ACCOMMODATE 5 1/2" HWDP MEANWHILE PREPAREEQUIPMENT FOR BACK LOAD AND RIG MOVE PREPARATION. | : PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP 22. SURFACE TESTING : PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS141FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_141_220927.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 27-Sep-22 | 4.50 | 6 | HELD PJSM BREAK OUT AND LOUT 5 1/2” HWDP STANDS FROM DERRICK TOTAL 72 JTS LAYED OUT. NOTE USING RIGTONGS AND EZ TORQUE TO BREAK OUT JOINTS DUE TO CONNECTIONS VERY TIGHT. | : PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP 22. SURFACE TESTING : PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS141FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_141_220927.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 27-Sep-22 | 5.50 | 1 | PREPARE FOR SKIDDING RIG TRANSVERSE. BREAK OUT HP MUD HOSES AND LAY OUT SAME BREAK OUT HIGHPRESSURE CEMENT AND TEST HOSE AND LAY OUT SAME. DISCONNECT AND REMOVE SKIMMER TANK HOSE.BACKLOAD HLS SLICK LINE EQUIPMENT TO COSTAL ABAR.BACK LOAD CHEMICALS TO OSV WRANGLER. MAKE ARRANGEMENTS ON MAIN DECK AND L/OUT 5 ½” DP ON MAINDECK. PREPARING FOR RIG MOVE IN PROGRESS. IADC OFFICIAL DAILY DRILLING REPORT FORM | : PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP 22. SURFACE TESTING : PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS141FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_142_220928.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 28-Sep-22 | 6.00 | 23 | CONTINUE TO L/OUT 5 ½” DP ON MAIN DECK PREPARING FOR RIG MOVE IN PROGRESS. OFF LOAD DRILL PIPE FROMOSV WRANGLER.CLEAN PLATFORM IN PROGRESS. | :PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP. 22. SURFACE TESTING :PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS142FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_142_220928.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 28-Sep-22 | 6.00 | 23 | CONTINUE LAY OUT 5 ½” DP ON MAIN DECK. CONTINUE BACK LOADING 5” RENTAL DP ON THE BOAT COSTAL AABHAR.REMOVED SCRAP PLATE FROM UNDER THE CANTILEVER AREA. SKID UPPER PACKAGE TO CENTER AND WELDINGSTOPPER. SECURING BOTH JUMPER HOSES AND SERVICE HOSES IN PROGRESS. 2 RUOT DEPTH I NTERVAL DRILL FORMATION ROTARY WT.PUMP PUMP PUMP PUMP TOTALFROM TO REAM CORENO.(SHOW CORE RECOVERY) TABLE ON PUMPPRESS LINERSPM LINER SPM LINER SPM LINER SPM PUMP CORE SPEED BITSIZE SIZE SIZESIZEOUTPUT HORIZ HORIZ HORIZ DEVIATI ON DEP TH DEV . DI R. TVD DISP. DEPTH DEV. DIR.TVDDISP. DEPTHDEV. DIR.TVDDISP. RECOR D TIME LOG ELAPSED CODEFROM TO TIME NO.DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS | :PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP. 22. SURFACE TESTING :PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS142FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00
IADCRpt_Compact Driller_CMD-22-3_142_220928.pdf | LB-13Z | 13.00 | CMD | CAIRN ENERGY INDIA | 28-Sep-22 | 12.00 | 1 | CONTINUE SECURING JUMPER HOSES AND SERVICE HOSES. MOVE CHICKSANS SLINGS HIGH PRESSURE HOSE ANDFIRE EXTINGUISHER FROM PLATFORM TO RIG CONTINUE CLEANING ON THE PLATFORM WELDING STOPPER FORUPPER PACKAGE SUB STRUCTURE CONTINUE CHIPPING UNDER SHALE SHAKER DECK. REMOVE DRILLING BAILSFROM TDS. CONTINUE TO SECURE RIG FOR RIG MOVE. DUMP AND CLEAN SLUG PIT. RECEIVE FUEL FROM OSVCOSTAL AABHAR 50KL. IADC OFFICI AL DAILY DRILLING REPORT FORM | :PREPARE FOR UP COMING JOB 17. PLUG BACK5" SAVER SUB CONNECTION- 0 TOTAL 230 18. SQUEEZE CEMENT5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 19. FISHING 20. DIRECTIONAL WORK 21. RUN/RETRIEVE RISER EQUIP. 22. SURFACE TESTING :PREPARE FOR UP COMING JOB TOTAL DAYWORK 0.00 0.00 5" SAVER SUB CONNECTION- 0 TOTAL 230 NO. OF DAYS142FROM SPUD5 1/2"SAVER SUB CONNECTIONS -0- TOTAL 293 CUMULATIVE107ROTATING HOURS DAILY MUD COST ($) 0.00 TOTAL MUD COST ($) 0.00