## 24hrs summary
Summary | csg_size | csd
SPUD THE WELL SA -0772 @ 13:00 HRS ON 31- DEC -2017 . DRILLED 22 " SURFACE SECTION WITH ROTARY BHA FROM 56 FT TO 504 FT. DROPPED TOTCO HOLE SURVEY. CONT'D DRILLING 22 " SECTION TO 675 FT.
CONT DRILLING 22" SURFACE SECTION WITH ROTARY BHA FROM 675 FT TO 1250 FT STD. CHC. POOH & L/D 22" ROTARY DRLG BHA. RU & RIH 18-5/8" CSG TO BTM.
CHC RIH w/ CMT STINGER CHC. PERFORMED 18-5/8" CEMENT JOB AS PER PLAN. POOH STINGER TO SURFACE LIFT DIVERTER. ROUGH CUT CSG & N/D DIVERTER FINAL CUT & DRESS 30" CP & 18-5/8" CSG. N/U CHH & P/T. WELD CHH BASE PLATE N/U 21-1/4" 2K BOP STACK & P/T SAME.
INSTALL W.B. P/U M/U & RIH 16" MOTOR BHA. DRILL OUT SHOE TRACK TO 20 FT ABOVE F. SHOE. P/T CSG. CONT D.O.C. DISPLACE WELL TO 8.8 PPG LOW SOLIDS BENTONITE MUD. DRILL AHEAD 16" HOLE SECTION F/1250 FT TO 2194 FT.
CONTINUE TO DRILL AHEAD 16" HOLE SECTION F/2194 FT TO 3650 FT. | 18.625 | 1249.00
CONTINUE TO DRILL AHEAD 16" HOLE SECTION TO 3915 FT. ENTER TAYARAT WITH 9.3 PPG MW @ 3915 FT. DRILL AHEAD TO 4592 FT. WELL FLOW KILL THE WELL w/9.6 PPG MUD. WELL ON STATIC LOSSES. RESUME DRILLING 16" HOLE SECTION F/4592 FT TO 4672 FT INCREASING MW TO 9.7 PPG. | 18.625 | 1249.00
CONTINUE TO DRILL AHEAD 16" HOLE SECTION F/4672 FT TO 4896 FT. WELL FLOW KILL THE WELL w/10.2 PPG MUD. WELL ON STATIC LOSSES. RESUME DRILLING 16" HOLE SECTION F/4896 FT TO 5284 FT. | 18.625 | 1249.00
CONTINUE TO DRILL AHEAD 16" HOLE SECTION F/5284 FT TO 5720 FT. KICK OFF IN SADI @ 5720 FT. DIRECTIONALLY DRILLED 16" SECTION TO 6124 FT. | 18.625 | 1249.00
CONTINUE TO DRILL DIRECTIONALLY 16" SECTION F/ 6124 FT TO SECTION TD @ 6165 FT. CHC. PERFORMED WIPER TRIP. POOH 16" DRLG BHA F/BTM TO 1665 FT. | 18.625 | 1249.00
CONTINUE TO POOH 16" MOTOR BHA TO 1 STD BELOW SHOE. DROP GYRO & CONT. POOH TO SURFACE L/D BHA. CHANGE PIPE RAMS TO 13-3/8" CSG RAMS. RETRIEVE W.B. P/T BONNETS SEAL. R/U 13-3/8" CRT & CSG HANDLING GEARS. RIH 13-3/8" INTERMEDIATE CSG TO BTM @ 6165 FT. | 18.625 | 1249.00
CHC. PERFORM 13-3/8" CMT JOB. LIFT BOP & SET CSG HANGER SLIPS. ROUGH CUT CSG & N/D 21-1/4" BOP. FINAL CUT CSG INSTALL CHS & P/T. N/U 13-5/8" BOP STACK & P/T. P/U M/U 5" DP STDS'. M/U & RIH 12-1/4" DRLG BHA TO 46 FT. | 13.375 | 6164.00
CONT. M/U & RIH 12-1/4" DRLG BHA. TO TOC DRILL OUT SHOE TRACK TO 20' ABOVE F.S. P/T CSG CONT. D/O SHOE TRACK & 10' NEW FORMATION TO 6175 FT. PERFORM FIT 12.5 PPG EMW. CONT. DRLG 12-1/4" HOLE SECTION WHILE DISPLACING WELL TO 11.2 PPG VERSADRIL OBM TO 6600 FT. | 13.375 | 6164.00
CONT. DRILLING 12-1/4" HOLE SECTION TO SECTION TO 7563 FT (TD). CHC. POOH 12-1/4" VTX BHA FROM TD TO 6825 FT. | 13.375 | 6164.00
CONT. TO POOH 12-1/4" VTX BHA TO SHOE. PERFORM WIPER TRIP. CIRCULATE AT BOTTOM. POOH TO SURFACE AND L/D BHA. RETRIEVE WEAR BUSHING. CHANGE RAMS TO 9-5/8" AND P/T BOP BONNET. R/U CDS AND RIH 9-5/8" CASING TO 5208 FT. | 13.375 | 6164.00
CONTINUE TO RIH CASING TO 7563 FT (BOTTOM). CIRCULATE. PERFORMED CEMENT JOB. LIFTED BOP AND SET 9-5/8" CASING SLIPS. CUT CASING AND MOVE BOP. FINAL CUT CASING. INSTALL & P/T WELLHEAD SECTION C. N/U AND P/T BOP. L/D DC FROM MAST. | 13.375 | 6164.00
CONTINUE TO RIH CASING TO 7563 FT (BOTTOM). CIRCULATE. PERFORMED CEMENT JOB. LIFTED BOP AND SET 9-5/8" CASING SLIPS. CUT CASING AND MOVE BOP. FINAL CUT CASING. INSTALL & P/T WELLHEAD SECTION C. N/U AND P/T BOP. L/D DC FROM MAST. | 13.375 | 6164.00
CONT. TO L/D 8.25" DC STANDS FROM MAST. M/U 8-1/2" PD ARCHER BHA RIH TO TOC DRLD OUT SHOE TRACK TO 20' ABOVE F.S P/T CSG CONT'D DRLG OUT SHOE TRACK & 10' OF NEW FORMATION TO 7573 FT CHC PERFORMED FIT TO 13.5 PPG EMW. CONTINUE DRILLING 8.5" DIRECTIONAL TO 7792 FT. | 13.375 | 6164.00
CONT. TO L/D 8.25" DC STANDS FROM MAST. M/U 8-1/2" PD ARCHER BHA RIH TO TOC DRLD OUT SHOE TRACK TO 20' ABOVE F.S P/T CSG CONT'D DRLG OUT SHOE TRACK & 10' OF NEW FORMATION TO 7573 FT CHC PERFORMED FIT TO 13.5 PPG EMW. CONTINUE DRILLING 8.5" DIRECTIONAL TO 7792 FT. | 13.375 | 6164.00
CONTINUE DRILLING 8.5" DIRECTIONAL TO 8210 FT. CIRCULATE. POOH IN WIPER TRIP TO CHECK WARA. RIH AND RE-LOG FROM SHOE (7600 FT) TO 7979 FT. CONT. TO RIH ON ELEVATOR TO 8210 FT (BOTTOM). CONT. DRILLING TO 8515 FT. | 9.625 | 7562.00
CONTINUE DRILLING 8.5" DIRECTIONAL TO 8536 FT. CIRCULATE. POOH IN WIPER TRIP TO SHOE. REAM DOWN THOUGH WARA AND CONT. RIH TO BOTTOM. CIRCULATE. POOH AND L/D BHA. R/U LINER RUNNING TOOLS AND RIH 7" LINER TO 2130 FT. | 9.625 | 7562.00
CONT'D RIH 7" LINER TO BTM @ 8536 FT CHC SET LINER HANGER RELEASED RUNNING TOOL SHEARED BALL SEAT CHC PERFORMED 7" LINER CMT JOB AS PER PLAN SET TOP PACKER REVERSE CIRCULATED POOH & L/D RUNNING TOOL P/U M/U & RIH TANDEM SCRAPERS C/O BHA TO 4140 FT. | 7.000 | 8534.00
CONT'D RIH TANDEM SCRAPERS C/O BHA TAGGED ON TOC @ 8457 FT DRILLED OUT CMT TO 20 FT ABOVE F.S. CHC WAIT ON WEATHER POOH TO SURFACE & L/D SCRAPERS RETRIEVED WEAR BUSHING N/D BELL NIPPLE & N/U SHOOTING NIPPLE. | 7.000 | 8534.00
CONT'D RIH WASHING DOWN TO TOC DRILLED OUT REMAINING SHOE TRACK WHILE DISPLACING WELL TO 8.8 PPG FLO-PRO WBM DRILLED AHEAD 6-1/8" SECTION FROM 8536 FT TO 9259 FT (PD NOT RESPONDING) CHC POOH TO SURFACE TO CHANGE PD & CLINK. | 7.000 | 8534.00
M/U BHA WITH NEW PD & CLINK RIH BACK TO BTM @ 9259 FT RESUMED DRILLING AHEAD 6-1/8" SECTION TO 10232 FT. | 7.000 | 8534.00
CONT'D DRILLING 6-1/8 " SECTION F/ 10232 FT TO WELL TD @ 10396 FT CHC WIPER TRIP TO LINER SHOE & RIH BACK TO BTM CHC POOH TO SURFACE & L/D 6-1/8 " VTX BHA. ** END OF LSTK OPERATIONS ON 24- JAN -2018 @ 03:00 AM. | 7.000 | 8534.00