## Sheet1
| index | notes | filename | flow_available | time_from | time_to | duration | depth_start | depth_end | kick_raw
62 | 4 | 00:45 01:30 0:45 4592 4592 16.000 Drilling Well Control N P WELL FLOW. SHUT IN WELL ON ANNULAR BOP & MONITOR. Observed well flowing while drilling @ 4592 ft with 900 gpm; SPP: 2480 psi. Well flow at 48 bbl/hr. Shut-in well immediately on annular BOP. Monitor well and discuss plan to kill the well. Stable SIDPP SICP 60 psi. Meanwhile increase surface active MW from 9.35 ppg to 9.6 ppg. Page 1 of 3 Printed: 05-Jan-2018 Daily Operations Report (DOR) 05-Jan-2018 6 Report No.: Casing Last Size (in) 18.625 Set MD (ft) 1249.00 Next Size (in) 13.375 Set MD (ft) 6230.00 Mud Volumes (bbl) Starting 2971.00 Built 816.00 Received Hole Loss 260.00 Surface Loss 180.00 Dumped 270.00 Returned Adjusted Consumed Ending 3077.00 Connection Gas Trip Gas Background Gas BHA BHA Number 16" Performance BHA 1 Description OD ID Length (in) (in) (ft) 16" TCI Bit 16.00 1.39 A962M5640XP (1.5 deg w/ FV) 9.63 7.88 32.64 15 3/4" ST STB 15.75 2.81 8.04 8 1/4" Pony NMDC 8.25 2.81 9.57 Telescope 925 HF (w/ Totco ring on top) 9.25 5.11 30.47 8 1/4" NMDC 8.25 2.81 30.98 X-Over 10.00 2.81 2.60 3 x 9 1/2" DC's 9.50 2.81 89.94 X-Over 10.00 2.88 2.50 9 x 8 1/4" DC's 8.25 2.81 270.87 8" Hydra-Jar 8.00 3.00 32.75 3 x 8 1/4" DC's 8.25 2.81 90.40 X-Over 8.25 2.81 2.61 15 x 5" HWDP's 5.00 3.00 461.89 BHA Length (ft) 1066.65 BHA Weight (1000 lbm) 0.00 Bit Last Prev. Bit Number 16" TCI Bit 22" MT Bit RR Bit Model GSI16BVECP S SDSC Bit Run 1 1 Type Insert Milled Tooth IADC Code 445 114 Serial # RG5237 RG 5946 Start Depth (ft) 3650.00 End Depth (ft) 4672.00 Drilled Length (ft) 1022.00 Bit Hours 17.00 Nozzles (# x 1/32 in) 4 x 16.00 4 x 14.00 TFA (in2) 0.79 0.60 I-O-D-L 2 3 WT A B-G-O-R E 5 NO TD Cumulative Drilled Length (ft) 3422.00 1194.00 Bit Hours 49.00 16.25 ROP (ft/h) 69.84 73.48 Comments ** Well Objective: To deliver Mauddud Single Producer Horizontal Well w/ 4-1/2 " ICD Completion in Sabriyah Field. * Two water wells are running with 330 BPH. Salinity of water 2600 mg/l and Hardness 640 mg/l. Water pit 70% full; OBM pit 90 % full; Steel water tanks x 3000 bbl. * Materials Received: 13 3/8 " CSG K -55 68# BTC x 54 joints + 1 PJ * Material Sent: None Time Breakdown Time (HH:mm) Measured Depth (ft) Section Operations Plan Time Vend Comments Start End Duration Start End Name Class | C:/Users/Jayaraj/Desktop/SOFTWARE TEST/INPUT/06 SP-295_SA-0772_DOR_05-01-2018.txt | TRUE | 00:45 | 01:30 | 0:45 | 4592 | 4592 | flow at 48 bbl/hr.
63 | 5 | 01:30 04:00 2:30 4592 4592 16.000 Drilling Well Control N P KILL THE WELL THRU FULLY OPEN CHOKE w/ 9.6 PPG MUD. Pump thru fully open choke 9.6 ppg kill mud. Pump at 300-400 gpm thru fully open choke. Final SIDPP SICP 0 psi Observed loss rate while killing @ 57 bbl/hr. Precautionary divert & dump last 150 bbl of mud to flare pit. B/U sample MW 8.9 ppg. pH dropped from 9.7 to 8.6 . Chlorides increased from 8400 mg/l to 22600 mg/l. | C:/Users/Jayaraj/Desktop/SOFTWARE TEST/INPUT/06 SP-295_SA-0772_DOR_05-01-2018.txt | TRUE | 01:30 | 04:00 | 2:30 | 4592 | 4592
66 | 1 | 11:30 12:00 0:30 4896 4896 16.000 Drilling Well Control N P WELL FLOW. SHUT IN WELL ON ANNULAR BOP & MONITOR. Observed well flowing while drilling @ 4896 ft with 900 gpm; SPP: 2480 psi. Well flow at 12 bbl/hr. Shut-in well immediately on annular BOP. Monitor well and discuss plan to kill the well. Stable SIDPP SICP 16 psi. Meanwhile increase surface active MW from 9.8 ppg to 10.2 ppg. * Conducted pit drill with the crew good response from the crew. Well secured in 60 sec. | C:/Users/Jayaraj/Desktop/SOFTWARE TEST/INPUT/07 SP-295_SA-0772_DOR_06-01-2018.txt | TRUE | 11:30 | 12:00 | 0:30 | 4896 | 4896 | flow at 12 bbl/hr.
67 | 2 | 12:00 14:00 2:00 4896 4896 16.000 Drilling Well Control N P KILL THE WELL w/ 10.2 PPG MUD. Final SIDPP SICP 0 psi Observed loss rate while killing @ 20 bbl/hr. Precautionary divert & dump last 100 bbl of mud to flare pit. B/U sample MW 9.7 ppg. pH dropped from 9.7 to 8.6 . Chlorides increased from 18000 mg/l to 30000 mg/l. | C:/Users/Jayaraj/Desktop/SOFTWARE TEST/INPUT/07 SP-295_SA-0772_DOR_06-01-2018.txt | TRUE | 12:00 | 14:00 | 2:00 | 4896 | 4896
111 | 11 | 18:00 22:00 4:00 6165 6165 16.000 Well Head Assembly Nipple Up BOP Y P N/U 13-5/8 " 5 K BOP STACK N/U Spacer Spool and Mud cross. N/U Double Rams (BSR & VBR 2-7/8 '' 5 ") & Annular BOP. Tighten all studs and nuts. Connected choke & kill lines. Connected hydraulic control lines to BOP. N/U Bell Nipple and Flow line. Flushed BOP stack. | C:/Users/Jayaraj/Desktop/SOFTWARE TEST/INPUT/11 SP-295_SA-0772_DOR_10-01-2018.txt | TRUE | 18:00 | 22:00 | 4:00 | 6165 | 6165
152 | 11 | 17:00 18:00 1:00 7563 7563 12.250 Well Head Assembly Change Rams Y P HELD PJSM & CHANGED VBR TO 9-5/8 " CSG RAMS. Closed BSR and circulated through kill line & choke manifold to MGS. Well Static. | C:/Users/Jayaraj/Desktop/SOFTWARE TEST/INPUT/14 SP-295_SA-0772_DOR_13-01-2018.txt | TRUE | 17:00 | 18:00 | 1:00 | 7563 | 7563